## Guide & Navigation
Templat Log Inspeksi Peralatan
A free Excel template for organizing equipment inspections, maintenance plans, repair history, and parts replacement in one workbook.
Kemajuan | Warna Tampilan | Tujuan
Primary | #2B4C7E | Title & Main Headers
Accent | #5B84B1 | Subcategories / Subheadings
Table Header | #EBF3FB | Headers / Item Names

## Dasbor
Dasbor
A free Excel template for organizing equipment inspections, maintenance plans, repair history, and parts replacement in one workbook.
Bulan | Planned Tasks | Tugas Selesai | Anomalies Count | Tingkat penyelesaian | Repair Cost | Parts Replacement Cost | Total Cost
Jumlah
Action Items Summary
Kemajuan | Count / Amount | Referenced Sheet | Verification Points

## Pengaturan
Pengaturan
A free Excel template for organizing equipment inspections, maintenance plans, repair history, and parts replacement in one workbook.
Equipment Status | Verdict | Fitur utama | Equipment Type | Assignee | Interval | Cycle Days | Plan Status | Repair Status | Part Status | Tindakan Diperlukan | Recording Required
Operating | Baik | Mendesak | Distribution Board | Manajemen | Harian | 43.0% | Status | Status | Standar | Ya | Wajib
Dihentikan | Tidak | Tinggi | Air Conditioner | Jordan Lee | Mingguan | 6 | Status | Investigating | Within 30 Days | Tidak | Opsional
Under Repair | Requires Check | Sedang | Compressor | Taylor Reed | Bulanan | 30 | Status | Waiting for Parts | Terlambat

## Daftar Peralatan
Daftar Peralatan
A free Excel template for organizing equipment inspections, maintenance plans, repair history, and parts replacement in one workbook.
ID Peralatan | Equipment Name | Equipment Type | Model | Control Serial No | Installation Date | Lokasi | Respons atau Catatan | Manajer | Fitur utama | Interval | Tanggal Inspeksi Berikutnya | Manufacturer | Purchase Price | Catatan
EQ-001 | 1st Distribution Board | Distribution Board | PD-500A | SN-PD-1001 | 2021/08/30 | 1st Factory Electrical Room | Operating | Manajemen | Tinggi | Bulanan |  | Toto Electric | ¥1,450,000 | Main Panel
EQ-002 | HVAC Unit AHU-1 | Air Conditioner | AHU-120 | SN-AHU-2031 | 2022/11/03 | 1st Factory Rooftop | Operating | Jordan Lee | Sedang | Bulanan |  | Hokushin HVAC | ¥980,000 | Check Filter Stock
EQ-003 | Compressor C-1 | Compressor | CP-75KW | SN-CP-7788 | 2020/09/14 | Utility Room | Under Repair | Taylor Reed | Mendesak | Mingguan |  | Aoba Machinery | ¥3,200,000 | Enhance oil temperature monitoring

## Inspection Item Library
Inspection Item Library
A free Excel template for organizing equipment inspections, maintenance plans, repair history, and parts replacement in one workbook.
Item ID | Equipment Type | Inspection Category | Inspection Item | Inspection Method | Standards / Thresholds | Satuan | Recommended Cycle | Standard Value (Lower) | Standard Value (Upper) | Fitur utama | Recording Required | Catatan
ITM-001 | Distribution Board | Tampilan | Panel odor & burn marks | Visual Check | No abnormal odor or burn marks |  | Bulanan |  |  | Tinggi | Wajib | Check when opening/closing door
ITM-002 | Distribution Board | Elektrikal | Terminal Temperature | Measurement | 60°C or less | ℃ | Bulanan | 0.0 | 60.0 | Tinggi | Wajib | Thermography Recommended
ITM-003 | Air Conditioner | Cleaning | Filter clogged | Visual Check | No clogging |  | Bulanan |  |  | Sedang | Wajib | Replace if differential pressure is high

## Rencana Inspeksi
Rencana Inspeksi
A free Excel template for organizing equipment inspections, maintenance plans, repair history, and parts replacement in one workbook.
ID Rencana | ID Peralatan | Equipment Name (Auto) | Tanggal Direncanakan | Interval | Pemeriksa | Fitur utama | Respons atau Catatan | Overdue Status (Auto) | Planned Month (Auto) | Catatan
PLN-001 | EQ-001 |  | 2026/06/12 |  | Manajemen |  | Proyek konstruksi pusat |  |  | Monthly Inspection
PLN-002 | EQ-002 |  | 2026/06/17 |  | Jordan Lee |  | Status |  |  | Check filter
PLN-003 | EQ-003 |  | 2026/06/14 |  | Taylor Reed |  | Status |  |  | Oil Temp & Pressure Focus

## Log Inspeksi
Log Inspeksi
A free Excel template for organizing equipment inspections, maintenance plans, repair history, and parts replacement in one workbook.
ID catatan | Tanggal Inspeksi | ID Peralatan | Equipment Name (Auto) | Inspection Item ID | Inspection Item (Auto) | Measured Value | Verdict | Respons atau Catatan | Petugas | Anomaly Details / Remarks | Corrective Action Required (Auto) | Related Repair ID | Photo / Attachment | Catatan
LOG-001 | 2026/06/12 | EQ-001 |  | ITM-001 |  |  | Baik | Proyek konstruksi pusat | Manajemen | No abnormal odor. Panel inside clean.
LOG-002 | 2026/06/12 | EQ-001 |  | ITM-002 |  | 48.0 | Baik | Proyek konstruksi pusat | Manajemen | Terminal temperature within standard.
LOG-003 | 2026/06/07 | EQ-002 |  | ITM-003 |  |  | Requires Check | Proyek konstruksi pusat | Jordan Lee | Filter differential pressure slightly high. |  |  |  | T-005

## Riwayat Perbaikan
Riwayat Perbaikan
A free Excel template for organizing equipment inspections, maintenance plans, repair history, and parts replacement in one workbook.
Repair ID | Identified Date | ID Peralatan | Equipment Name (Auto) | Related Record ID | Anomaly Details | Target Tanggal Tutup | Manajemen | Repair Cost | Respons atau Catatan | Planned Completion Date | Jumlah proyek yang saat ini terdaftar dalam template. | Assigned To | Downtime (h) | Additional Actions
REP-001 | 2026/06/14 | EQ-003 |  | LOG-004 | Oil smear & discharge pressure exceeded limit | Mendesak | Check seal, adjust pressure control valve | ¥85,000 | Under Repair | 2026/06/17 |  | Taylor Reed | 1.5 | Re-inspect after completion
REP-002 | 2026/05/26 | EQ-002 |  | LOG-003 | Filter differential pressure high | Sedang | Clean filter, recheck differential pressure | ¥12,000 | Proyek konstruksi pusat | 2026/05/31 | 2026/05/30 | Jordan Lee | 0.5 | Next Replacement Review
REP-003 | 2026/05/01 | EQ-005 |  |  | Lower belt tension | Tinggi | Adjust tension, clean rollers | ¥28,000 | Proyek konstruksi pusat | 2026/05/06 | 2026/05/05 | Eric Tan | 0.8

## Parts Replacement
Parts Replacement
A free Excel template for organizing equipment inspections, maintenance plans, repair history, and parts replacement in one workbook.
Replacement ID | ID Peralatan | Equipment Name (Auto) | Part Name | Part Code | Replacement Date | Replacement Cycle (Days) | Next Replacement Date (Auto) | Days Remaining (Auto) | Respons atau Catatan | Jumlah | Biaya satuan | Amount (Auto) | Assignee | Catatan
PRT-001 | EQ-002 |  | Medium Performance Filter | FLT-AHU-120 | 2026/04/26 | 90 |  |  | Standar | 3. Masukkan data bulanan | ¥8,500 |  | Jordan Lee | Next Inventory Check
PRT-002 | EQ-003 |  | Compressor Oil | OIL-CP-75 | 2025/12/22 | 180 |  |  | Within 30 Days | 43.0% | ¥18,000 |  | Taylor Reed | Preparing Replacement
PRT-003 | EQ-005 |  | Conveyor Belt | BELT-CV-300 | 2025/06/10 | 365 |  |  | Terlambat | 43.0% | ¥64,000 |  | Eric Tan | Replacement Plan Needed