## Panduan Penggunaan
Maintenance Plan and Repair History Template ¦ User Guide
This template is a professional Excel workbook designed to centrally manage maintenance plans, work logs, repair history, parts/consumables, and vendor information for vehicles, equipment, and facilities. It links planning, execution, repairs, inventory, and monthly reviews using a shared Asset ID, facilitating audits, improvements, and recurrence prevention.
Operation Flow (4 Steps)
Step 1: Register Assets |  |  | Set up the asset register, owners, sites, and criticality first, and use the same Asset ID in plans and repairs.
Step 2: Create Plans |  |  | Enter frequencies, scheduled dates, grace days, and staff, and monitor this month's plans and overdue schedules on the Dashboard.
Step 3: Record Work |  |  | Record inspections, maintenance work, abnormalities, materials, hours, and attachments in the Work Log.
Step 4: Complete Repairs |  |  | Document root causes, actions taken, costs, acceptance dates, and recurrence preventions in the Repair History for review and audits.
Legend (Color Coding)
| Light Blue | Cells requiring manual input
| Light Green | Cells to select from a dropdown list
| Light Gray | Formula cells with auto-calculation (Protected)
Key Operational Points
• Asset ID is used as a common key across all sheets. To prevent typos, select it from the dropdown in the Maintenance Plan, Work Log, and Repair History sheets.
• Asset names in the Maintenance Plan, stock status in Parts, and achievement rate or cost calculations in Monthly Summary are computed automatically. Gray cells are protected to prevent direct edits.
• Rows that are overdue, abnormal, pending, or require replenishment are highlighted with conditional formatting. Check the Dashboard regularly to monitor overall risks.
Unprotect Password | maintenance

## Dasbor
Dashboard
Cross-check all assets, this month's maintenance plans, pending repairs, and parts shortages.
Total Managed Assets |  | Maintenance Scheduled for Current Month |  | Pending Repair Requests |  | Parts Shortage (Replenishment Recommended)
Registered Assets Count |  | Schedules for Current Month |  | Status = Pending |  | Stock Status = Reorder
Asset Count by Operation Status and Criticality
Operation Status | High | Medium | Low | Total
Operating
Stopped
Disposed
Maintenance Plans by Status |  |  |  | Alert Level Abnormalities and Pending Summary
Status | Count | Ratio |  | Alert Item | Count | Judgment | Confirmation Notes
Not Started |  |  |  | Overdue Maintenance Plans
In Progress |  |  |  | Work Logs with Abnormalities
Completed |  |  |  | Uncompleted Repairs
Skipped |  |  |  | Parts Recommended for Replenishment

## Daftar Aset
Asset Register
This is the master list of managed vehicles, equipment, and facilities. Asset ID is used as a common key across other sheets.
Asset ID | Asset Name | Category | Site | Criticality | Owner | Purchase Date | Operation Status | Remarks

## Rencana Pemeliharaan
Maintenance Plan
Manage preventive maintenance schedules, frequencies, staff, and status. Overdue items are highlighted with conditional formatting.
Plan ID | Scheduled Date | Target Asset ID | Asset Name | Maintenance Frequency | Operator | Plan Details | Grace Days | Status | Remarks

## Log Kerja
Work Log
Record maintenance work performed based on plans, abnormalities, materials used, man-hours, and attachment links.
Work ID | Execution Date | Target Asset ID | Worker | Work Details | Parts/Materials Used | Required Hours (h) | Abnormality Status | Attachment Link/Photo | Verifier

## Riwayat Perbaikan
Repair History
Track causes, actions, costs, and recurrence preventions for sudden failures or abnormalities found in work logs.
Repair ID | Request Date | Target Asset ID | Issue Status | Root Cause | Action Taken | Repair Cost | Repair Status | Acceptance Date | Recurrence Prevention | Remarks

## Suku Cadang dan Habis Pakai
Parts and Consumables
Manage stock status and replenishment suggestions for parts and materials used in maintenance work.
Parts ID | Parts Name | Current Stock | Target Stock | Unit | Stock Status | Next Order Schedule | Remarks

## Vendor dan Staf
Vendors and Staff
Manage contact information for repair vendors, parts suppliers, manufacturers, etc.
Vendor ID | Vendor Name | Contact Point | Phone Number | Email Address | Assigned Business/Category | Address | Remarks

## Ringkasan Bulanan
Monthly Summary
Aggregate maintenance plan achievement rates, emergency repair counts, and repair costs by month. You can change the summary year in K3. | [6 empty] | Summary Year
Target Month | Planned Count | Completed Count | Achievement Rate | Emergency Repairs Count | Total Repair Cost | Parts Consumed Cost
Formulas:
Planned Count = COUNTIFS('Rencana Pemeliharaan'!$C5:C104,">="&[Target Month],'Rencana Pemeliharaan'!$C5:C104,"<"&EDATE([Target Month],1))
Completed Count = COUNTIFS('Rencana Pemeliharaan'!$C5:C104,">="&[Target Month],'Rencana Pemeliharaan'!$C5:C104,"<"&EDATE([Target Month],1),'Rencana Pemeliharaan'!$J5:J104,"完了")
Emergency Repairs Count = COUNTIFS('Riwayat Perbaikan'!$C5:C104,">="&[Target Month],'Riwayat Perbaikan'!$C5:C104,"<"&EDATE([Target Month],1))
Total Repair Cost = SUMIFS('Riwayat Perbaikan'!$H5:H104,'Riwayat Perbaikan'!$C5:C104,">="&[Target Month],'Riwayat Perbaikan'!$C5:C104,"<"&EDATE([Target Month],1))

## Pilihan
Dropdown Options
This is the master data used for dropdown lists on each sheet. You can add or modify values as needed.
Asset Category | Asset Criticality | Asset Operation Status | Maintenance Frequency | Maintenance Plan Status | Abnormality Status | Repair Status | Parts Unit | Vendor Category | Stock Status | Site Examples
Vehicle | High | Operating | Daily | Not Started | Normal | Pending | pcs | Repair Vendor | Reorder | Headquarters
Equipment | Medium | Stopped | Weekly | In Progress | Abnormal | In Progress | box | Parts Supplier | Adequate | Factory 1
Facility | Low | Disposed | Monthly | Completed |  | Completed | L | Manufacturer |  | Factory 2
|  |  | Quarterly | Skipped |  |  | kg | Inspection Agency |  | Warehouse
|  |  | Semi-annual |  |  |  | m | Other |  | Garage
|  |  | Annual |  |  |  | Formula
Ad-hoc
Maintenance Method
To add options, append them below the existing values in the corresponding column. Data validation rules refer to the initial range. If you significantly increase the number of candidates, expand the reference range in the script and regenerate.