## Corrective Action Overview
Corrective Action Management Template
Product Name |  | Total Tasks
Site | 1-2-3 | Not Started
Site Manager | Taro Yamada | In Progress
Start Date | 2026-04-01 | Done
Planned End Date | 2026-06-30 | Average Utilization
Review Date | 2026-04-18
Monthly Production Table 1 | 2026-04-01 | 1. Production Date Product Name 2. Production 3. / Weekly Schedule
Weekly Schedule | 2026-04-13
/
Production
Production + Monthly Production Table + Weekly Schedule + Quality Results Log 1..,.

## Production Master
Production
Product Name | [7 empty] | Total Tasks
Not Started
In Progress
No | Task Category | Task Name | Department | Staff | Planned Start
| Temporary Works | Fence / Temporary Power | Aoki Construction | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | 100%
| Earthworks | Layout / Excavation | Aoki Construction | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 | 100%
| Foundation Work | / | Sato Civil Works | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 100%
| Foundation Work |  |  | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 | 100% |  | Inspection
| Foundation Work |  |  | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  | 70%
| Foundation Work |  |  | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  | 50%
| Foundation Work | / |  | 4 | 2026-04-19 | 2026-04-22 |  |  | 0%
|  | 1F |  | 10 | 2026-04-23 | 2026-04-30 |  |  | 0% | 1F
|  |  |  | 4 | 2026-05-01 | 2026-05-04 |  |  | 0%
|  |  |  | 4 | 2026-05-06 | 2026-05-10 |  |  | 0%
|  |  |  | 5 | 2026-05-08 | 2026-05-16 |  |  | 0%
|  |  |  | 5 | 2026-05-08 | 2026-05-15 |  |  | 0%
|  |  |  | 6 | 2026-05-17 | 2026-05-21 |  |  | 0%
|  | PB |  | 7 | 2026-05-22 | 2026-05-27 |  |  | 0%
|  |  |  | 4 | 2026-05-28 | 2026-05-31 |  |  | 0%
|  | / |  | 4 | 2026-06-01 | 2026-06-08 |  |  | 0%
|  | / | Sato Civil Works | 5 | 2026-06-09 | 2026-06-16 |  |  | 0%
| Inspection | Inspection | / | 3 | 2026-06-20 | 2026-06-22 |  |  | 0%
|  |  | Department | 6 | 2026-06-23 | 2026-06-27 |  |  | 0%
|  |  | / | 2 | 2026-06-30 | 2026-06-30 |  |  | 0%
/. / /. 35.

## Monthly Production Table
Product Name |  |  |  |  | Review Date
No | Task Name | Department | Staff | Planned Start
Production Details.,. Review Date.

## Weekly Schedule
Product Name |  |  |  |  | Staff
No | Task Name | Department | Staff | Planned Start
Staff
Production. Staff Staff.

## Quality Results Log
Quality Results Log
Product Name | [5 empty] | Production / Inspection / Inspection
No | Date | Time | Category | Details
| 2026-04-13 | 8:00 | Safety | SafetyProduction | / Department |  | Done
| 2026-04-14 | 10:00 | Inspection | Inspection | / |  | Done
| 2026-04-17 | 13:00 | Inspection | Inspection |  |  | Done
| 2026-04-18 | 15:00 | Production | Post-Pour Foundation Concrete Check | /
| 2026-05-06 | 9:30 | Inspection | Inspection
| 2026-06-20 | 10:00 | Inspection | Inspection | /
Production / Inspection / Inspection.