## Guide
Plantilla de registro de asistencia del personal de obra
Un libro para controlar asistencia, intercambio de asignaciones y horas extra. Puede sobrescribir las filas de ejemplo según sea necesario y agregar más filas después.
How to use
1 | Prepare the roster | Set up the crew roster with each trade, company, foreman, planned headcount, and current crew status.
2 | Capture daily attendance | Record daily attendance by shift, work area, planned workers, actual attendance, absences, and overtime hours.
3 | Review staffing risk | Use the overtime and daily summary sheets to confirm approvals, safety briefings, staffing gaps, and next actions.
Legend
Input cell | Editable cells for direct entry.
Required cell | Must be filled before sharing the workbook.
Dropdown cell | Choose one value from the prepared list.
Computed cell | Calculated by formulas and protected from edits.
linked_sheets
sheet_id | sheet_name | kind | module_id
dashboard | Dashboard
attendance_records | Attendance log
crew_roster | Crew roster
overtime_control | Overtime control
daily_summary | Daily summary
lookups | Lookups
schema | Schema

## Dashboard
Dashboard
Un libro para controlar asistencia, intercambio de asignaciones y horas extra. Puede sobrescribir las filas de ejemplo según sea necesario y agregar más filas después.
Attendance rows | Planned workers | Present workers
Absent workers | Overtime hours

## Attendance log
Attendance log
Un libro para controlar asistencia, intercambio de asignaciones y horas extra. Puede sobrescribir las filas de ejemplo según sea necesario y agregar más filas después.
Attendance ID | Work date | Shift | Crew name | Trade | Work area | Planned workers | Present workers | Absent workers | Overtime hours | Attendance status | Approved by | Notes
AR-001 | 2026-04-01 | Day shift | Formwork crew A | Formwork | Tower A level 5 | 18 | 17 | 1 | 2.5 | Complete | Site supervisor | One planned worker absent; concrete deck setup stayed on schedule.
AR-002 | 2026-04-01 | Day shift | Rebar crew B | Rebar | Podium grid C3 | 12 | 12 | 0 | 0 | Complete | Site supervisor | Full attendance confirmed before morning toolbox talk.
AR-003 | 2026-04-02 | Night shift | Concrete crew C | Concrete | Basement pour zone | 16 | 14 | 2 | 4 | Needs review | Night manager | Two late arrivals require foreman confirmation.

## Crew roster
Crew roster
Un libro para controlar asistencia, intercambio de asignaciones y horas extra. Puede sobrescribir las filas de ejemplo según sea necesario y agregar más filas después.
Crew ID | Crew name | Trade | Company | Foreman | Planned headcount | Crew status | Notes
CR-001 | Formwork crew A | Formwork | Example Formwork Co. | Hiro Tanaka | 18 | Active | Assigned to structural deck cycle.
CR-002 | Rebar crew B | Rebar | North Rebar Partners | Mei Chen | 12 | Active | Reserve two workers for inspection support.

## Overtime control
Overtime control
Un libro para controlar asistencia, intercambio de asignaciones y horas extra. Puede sobrescribir las filas de ejemplo según sea necesario y agregar más filas después.
Overtime ID | Work date | Crew name | Reason | Requested hours | Approved hours | Approval status | Safety briefing | Notes
OT-001 | 2026-04-01 | Formwork crew A | Schedule recovery | 2.5 | 2 | Approved | Briefing done | Approved for deck edge protection closeout.
OT-002 | 2026-04-02 | Concrete crew C | Concrete pour | 4 | 0 | Submitted | Briefing pending | Hold approval until the night manager confirms safety briefing records.

## Daily summary
Daily summary
Un libro para controlar asistencia, intercambio de asignaciones y horas extra. Puede sobrescribir las filas de ejemplo según sea necesario y agregar más filas después.
Summary ID | Summary date | Total planned | Total present | Total absent | Total overtime hours | Manpower status | Action notes
DS-001 | 2026-04-01 | 30 | 29 | 1 | 2.5 | On plan | No staffing escalation. Confirm next-day formwork sequence in the coordination meeting.
DS-002 | 2026-04-02 | 16 | 14 | 2 | 4 | Short staffed | Review night-shift attendance and update overtime approval before payroll cutoff.

## Lookups (hidden)
Lookups
Un libro para controlar asistencia, intercambio de asignaciones y horas extra. Puede sobrescribir las filas de ejemplo según sea necesario y agregar más filas después.
shift | enum_shift_values | enum_shift_labels
option_set | value | label | sort | active
shift | day | Day shift | 10 | TRUE
shift | night | Night shift | 20 | TRUE
shift | weekend | Weekend shift | 30 | TRUE
trade | enum_trade_values | enum_trade_labels
option_set | value | label | sort | active
trade | formwork | Formwork | 10 | TRUE
trade | rebar | Rebar | 20 | TRUE
trade | concrete | Concrete | 30 | TRUE
trade | mep | MEP | 40 | TRUE
trade | finishing | Finishing | 50 | TRUE
attendance_status | enum_attendance_status_values | enum_attendance_status_labels
option_set | value | label | sort | active
attendance_status | complete | Complete | 10 | TRUE
attendance_status | missing_timesheet | Missing timesheet | 20 | TRUE
attendance_status | needs_review | Needs review | 30 | TRUE
manpower_status | enum_manpower_status_values | enum_manpower_status_labels
option_set | value | label | sort | active
manpower_status | on_plan | On plan | 10 | TRUE
manpower_status | short_staffed | Short staffed | 20 | TRUE
manpower_status | over_staffed | Over staffed | 30 | TRUE
manpower_status | blocked | Blocked | 40 | TRUE
overtime_reason | enum_overtime_reason_values | enum_overtime_reason_labels
option_set | value | label | sort | active
overtime_reason | schedule_recovery | Schedule recovery | 10 | TRUE
overtime_reason | concrete_pour | Concrete pour | 20 | TRUE
overtime_reason | delivery_delay | Delivery delay | 30 | TRUE
overtime_reason | safety_standby | Safety standby | 40 | TRUE
approval_status | enum_approval_status_values | enum_approval_status_labels
option_set | value | label | sort | active
approval_status | draft | Draft | 10 | TRUE
approval_status | submitted | Submitted | 20 | TRUE
approval_status | approved | Approved | 30 | TRUE
approval_status | rejected | Rejected | 40 | TRUE
briefing_status | enum_briefing_status_values | enum_briefing_status_labels
option_set | value | label | sort | active
briefing_status | done | Briefing done | 10 | TRUE
briefing_status | pending | Briefing pending | 20 | TRUE
briefing_status | exempt | Not required | 30 | TRUE
crew_status | enum_crew_status_values | enum_crew_status_labels
option_set | value | label | sort | active
crew_status | active | Active | 10 | TRUE
crew_status | standby | Standby | 20 | TRUE
crew_status | released | Released | 30 | TRUE
boolean | boolean_values | boolean_labels
option_set | value | label | sort | active
boolean | true | Yes | 10 | TRUE
boolean | false | No | 20 | TRUE

## Schema (hidden)
Schema
Un libro para controlar asistencia, intercambio de asignaciones y horas extra. Puede sobrescribir las filas de ejemplo según sea necesario y agregar más filas después.
modules
module_id | label | description
attendance_records | Attendance records
crew_roster | Crew roster
overtime_control | Overtime control
daily_summary | Daily summary
fields
module_id | field_id | label | type | role | enum_id | required
attendance_records | attendance_id | Attendance ID | text | primary_key |  | TRUE
attendance_records | work_date | Work date | date | created_at |  | TRUE
attendance_records | shift | Shift | enum | category | shift | TRUE
attendance_records | crew_name | Crew name | text | display_name |  | TRUE
attendance_records | trade | Trade | enum | category | trade | FALSE
attendance_records | work_area | Work area | text | category |  | FALSE
attendance_records | planned_workers | Planned workers | integer | quantity |  | FALSE
attendance_records | present_workers | Present workers | integer | quantity |  | FALSE
attendance_records | absent_workers | Absent workers | integer | quantity |  | FALSE
attendance_records | overtime_hours | Overtime hours | decimal | quantity |  | FALSE
attendance_records | attendance_status | Attendance status | enum | status | attendance_status | TRUE
attendance_records | approved_by | Approved by | text | owner |  | FALSE
attendance_records | notes | Notes | long_text | input |  | FALSE
crew_roster | crew_id | Crew ID | text | primary_key |  | TRUE
crew_roster | crew_name | Crew name | text | display_name |  | TRUE
crew_roster | trade | Trade | enum | category | trade | TRUE
crew_roster | company | Company | text | category |  | FALSE
crew_roster | foreman | Foreman | text | owner |  | FALSE
crew_roster | planned_headcount | Planned headcount | integer | quantity |  | FALSE
crew_roster | crew_status | Crew status | enum | status | crew_status | TRUE
crew_roster | notes | Notes | long_text | input |  | FALSE
overtime_control | overtime_id | Overtime ID | text | primary_key |  | TRUE
overtime_control | work_date | Work date | date | created_at |  | TRUE
overtime_control | crew_name | Crew name | text | display_name |  | TRUE
overtime_control | reason | Reason | enum | category | overtime_reason | FALSE
overtime_control | requested_hours | Requested hours | decimal | quantity |  | FALSE
overtime_control | approved_hours | Approved hours | decimal | quantity |  | FALSE
overtime_control | approval_status | Approval status | enum | status | approval_status | TRUE
overtime_control | safety_briefing_status | Safety briefing | enum | status | briefing_status | FALSE
overtime_control | notes | Notes | long_text | input |  | FALSE
daily_summary | summary_id | Summary ID | text | primary_key |  | TRUE
daily_summary | summary_date | Summary date | date | created_at |  | TRUE
daily_summary | total_planned | Total planned | integer | quantity |  | FALSE
daily_summary | total_present | Total present | integer | quantity |  | FALSE
daily_summary | total_absent | Total absent | integer | quantity |  | FALSE
daily_summary | total_overtime_hours | Total overtime hours | decimal | quantity |  | FALSE
daily_summary | manpower_status | Manpower status | enum | status | manpower_status | TRUE
daily_summary | action_notes | Action notes | long_text | input |  | FALSE
enum_values
enum_id | value | label | sort | tone
shift | day | Day shift | 10 | neutral
shift | night | Night shift | 20 | neutral
shift | weekend | Weekend shift | 30 | warning
trade | formwork | Formwork | 10 | neutral
trade | rebar | Rebar | 20 | neutral
trade | concrete | Concrete | 30 | neutral
trade | mep | MEP | 40 | neutral
trade | finishing | Finishing | 50 | neutral
attendance_status | complete | Complete | 10 | success
attendance_status | missing_timesheet | Missing timesheet | 20 | warning
attendance_status | needs_review | Needs review | 30 | danger
manpower_status | on_plan | On plan | 10 | success
manpower_status | short_staffed | Short staffed | 20 | warning
manpower_status | over_staffed | Over staffed | 30 | neutral
manpower_status | blocked | Blocked | 40 | danger
overtime_reason | schedule_recovery | Schedule recovery | 10 | warning
overtime_reason | concrete_pour | Concrete pour | 20 | neutral
overtime_reason | delivery_delay | Delivery delay | 30 | warning
overtime_reason | safety_standby | Safety standby | 40 | danger
approval_status | draft | Draft | 10 | neutral
approval_status | submitted | Submitted | 20 | warning
approval_status | approved | Approved | 30 | success
approval_status | rejected | Rejected | 40 | danger
briefing_status | done | Briefing done | 10 | success
briefing_status | pending | Briefing pending | 20 | warning
briefing_status | exempt | Not required | 30 | neutral
crew_status | active | Active | 10 | success
crew_status | standby | Standby | 20 | warning
crew_status | released | Released | 30 | neutral
relations
relation_id | from_module_id | from_field_id | to_module_id | to_field_id | cardinality