## 01_Guide
Ehitusobjekti päevaraporti mall
Töövihik päevaraportite, edenemise uuenduste ja probleemide jälgimise jaoks.
How to use
1 | Start the report | Enter the report date, shift, weather, site area, preparer, and manager before the daily meeting.
2 | Update production facts | Record worker counts, equipment hours, material notes, progress quantities, and photos before approval.
3 | Close issues | Log safety, quality, schedule, and coordination issues with an owner, due date, and corrective action.
Legend
Input cell | Editable cells for direct entry.
Required cell | Must be filled before sharing the workbook.
Dropdown cell | Choose one value from the prepared list.
Computed cell | Calculated by formulas and protected from edits.
linked_sheets
sheet_id | sheet_name | kind | module_id
dashboard | 02_Dashboard
daily_reports | 03_Daily Reports
progress_items | 04_Progress Items
issues | 05_Issues
lookups | 06_Lookups
schema | 07_Schema

## 02_Dashboard
02_Dashboard
Töövihik päevaraportite, edenemise uuenduste ja probleemide jälgimise jaoks.
Reports | Total workers | Equipment hours
Open issues | Photo records

## 03_Daily Reports
03_Daily Reports
Töövihik päevaraportite, edenemise uuenduste ja probleemide jälgimise jaoks.
Report ID | Report date | Shift | Weather | Area / zone | Prepared by | Site manager | Work summary | Total workers | Equipment hours | Material notes | Safety status | Quality status | Issue count | Photo count | Approval status | Next action
DR-001 | 2026-04-01 | Day | Sunny | East tower podium | Site office | Alex Carter | Formwork stripping, rebar tying, and embedded sleeve checks completed for the podium slab. | 42 | 18.5 | Rebar bundles and plywood were received and staged near gate B. | Watch | Accepted | 1 | 18 | Submitted | Confirm guardrail correction before tomorrow morning.
DR-002 | 2026-04-02 | Day | Cloudy | West basement ramp | Field engineer | Morgan Lee | Concrete surface preparation and drainage trench layout continued. | 37 | 15 | No critical shortage. Anchor bolts moved to the laydown area. | Clear | Rework required | 0 | 14 | Draft | Recheck trench slope after survey confirmation.

## 04_Progress Items
04_Progress Items
Töövihik päevaraportite, edenemise uuenduste ja probleemide jälgimise jaoks.
Progress ID | Work package | Trade | Location | Planned quantity | Completed quantity | Unit | Completion rate | Owner | Status | Notes
PR-001 | Podium slab reinforcement | Rebar crew | East tower L2 | 120 | 84 | m2 | 70% | Structure lead | In progress | Inspection request is planned after final chair spacing check.
PR-002 | Ramp drainage trench | Civil crew | West basement | 48 | 22 | m | 45.8% | Civil lead | Blocked | Waiting for revised invert level from survey.

## 05_Issues
05_Issues
Töövihik päevaraportite, edenemise uuenduste ja probleemide jälgimise jaoks.
Issue ID | Category | Severity | Description | Owner | Due date | Status | Corrective action | Related report
IS-001 | Safety | Medium | Temporary guardrail at the east stair opening is loose. | Safety supervisor | 2026-04-03 | Mitigating | Reinstall clamps and record photos before access opens. | DR-001
IS-002 | Quality | Low | Drainage trench marking does not match the latest sketch. | Civil lead | 2026-04-04 | Open | Confirm coordinates with survey and remark the line. | DR-002

## 06_Lookups (hidden)
06_Lookups
Töövihik päevaraportite, edenemise uuenduste ja probleemide jälgimise jaoks.
shift | enum_shift_values | enum_shift_labels
option_set | value | label | sort | active
shift | day | Day | 10 | TRUE
shift | night | Night | 20 | TRUE
shift | split | Split | 30 | TRUE
weather | enum_weather_values | enum_weather_labels
option_set | value | label | sort | active
weather | sunny | Sunny | 10 | TRUE
weather | cloudy | Cloudy | 20 | TRUE
weather | rain | Rain | 30 | TRUE
weather | snow | Snow | 40 | TRUE
weather | high_wind | High wind | 50 | TRUE
safety_status | enum_safety_status_values | enum_safety_status_labels
option_set | value | label | sort | active
safety_status | clear | Clear | 10 | TRUE
safety_status | watch | Watch | 20 | TRUE
safety_status | incident | Incident | 30 | TRUE
quality_status | enum_quality_status_values | enum_quality_status_labels
option_set | value | label | sort | active
quality_status | accepted | Accepted | 10 | TRUE
quality_status | rework_required | Rework required | 20 | TRUE
quality_status | hold | Hold | 30 | TRUE
approval_status | enum_approval_status_values | enum_approval_status_labels
option_set | value | label | sort | active
approval_status | draft | Draft | 10 | TRUE
approval_status | submitted | Submitted | 20 | TRUE
approval_status | approved | Approved | 30 | TRUE
approval_status | returned | Returned | 40 | TRUE
quantity_unit | enum_quantity_unit_values | enum_quantity_unit_labels
option_set | value | label | sort | active
quantity_unit | m2 | m2 | 10 | TRUE
quantity_unit | m3 | m3 | 20 | TRUE
quantity_unit | ton | ton | 30 | TRUE
quantity_unit | set | set | 40 | TRUE
work_status | enum_work_status_values | enum_work_status_labels
option_set | value | label | sort | active
work_status | not_started | Not started | 10 | TRUE
work_status | in_progress | In progress | 20 | TRUE
work_status | completed | Completed | 30 | TRUE
work_status | blocked | Blocked | 40 | TRUE
issue_category | enum_issue_category_values | enum_issue_category_labels
option_set | value | label | sort | active
issue_category | safety | Safety | 10 | TRUE
issue_category | quality | Quality | 20 | TRUE
issue_category | schedule | Schedule | 30 | TRUE
issue_category | coordination | Coordination | 40 | TRUE
severity | enum_severity_values | enum_severity_labels
option_set | value | label | sort | active
severity | low | Low | 10 | TRUE
severity | medium | Medium | 20 | TRUE
severity | high | High | 30 | TRUE
issue_status | enum_issue_status_values | enum_issue_status_labels
option_set | value | label | sort | active
issue_status | open | Open | 10 | TRUE
issue_status | mitigating | Mitigating | 20 | TRUE
issue_status | resolved | Resolved | 30 | TRUE
issue_status | closed | Closed | 40 | TRUE
boolean | boolean_values | boolean_labels
option_set | value | label | sort | active
boolean | true | Yes | 10 | TRUE
boolean | false | No | 20 | TRUE

## 07_Schema (hidden)
07_Schema
Töövihik päevaraportite, edenemise uuenduste ja probleemide jälgimise jaoks.
modules
module_id | label | description
daily_reports | Daily reports
progress_items | Progress items
issues | Issues
fields
module_id | field_id | label | type | role | enum_id | required
daily_reports | report_id | Report ID | text | primary_key |  | TRUE
daily_reports | report_date | Report date | date | created_at |  | TRUE
daily_reports | shift | Shift | enum | category | shift | TRUE
daily_reports | weather | Weather | enum | category | weather | FALSE
daily_reports | area | Area / zone | text | display_name |  | TRUE
daily_reports | prepared_by | Prepared by | text | owner |  | TRUE
daily_reports | site_manager | Site manager | text | owner |  | FALSE
daily_reports | work_summary | Work summary | long_text | input |  | FALSE
daily_reports | total_workers | Total workers | integer | quantity |  | FALSE
daily_reports | equipment_hours | Equipment hours | decimal | quantity |  | FALSE
daily_reports | material_notes | Material notes | long_text | input |  | FALSE
daily_reports | safety_status | Safety status | enum | status | safety_status | TRUE
daily_reports | quality_status | Quality status | enum | status | quality_status | TRUE
daily_reports | issue_count | Issue count | integer | quantity |  | FALSE
daily_reports | photo_count | Photo count | integer | quantity |  | FALSE
daily_reports | approval_status | Approval status | enum | status | approval_status | TRUE
daily_reports | next_action | Next action | long_text | input |  | FALSE
progress_items | progress_id | Progress ID | text | primary_key |  | TRUE
progress_items | work_package | Work package | text | display_name |  | TRUE
progress_items | trade | Trade | text | category |  | FALSE
progress_items | location | Location | text | category |  | FALSE
progress_items | planned_quantity | Planned quantity | decimal | quantity |  | FALSE
progress_items | completed_quantity | Completed quantity | decimal | quantity |  | FALSE
progress_items | unit | Unit | enum | category | quantity_unit | FALSE
progress_items | completion_rate | Completion rate | percent | computed |  | FALSE
progress_items | owner | Owner | text | owner |  | FALSE
progress_items | status | Status | enum | status | work_status | TRUE
progress_items | notes | Notes | long_text | input |  | FALSE
issues | issue_id | Issue ID | text | primary_key |  | TRUE
issues | category | Category | enum | category | issue_category | TRUE
issues | severity | Severity | enum | status | severity | TRUE
issues | description | Description | long_text | display_name |  | TRUE
issues | owner | Owner | text | owner |  | FALSE
issues | due_date | Due date | date | end_date |  | FALSE
issues | status | Status | enum | status | issue_status | TRUE
issues | corrective_action | Corrective action | long_text | input |  | FALSE
issues | related_report | Related report | text | foreign_key |  | FALSE
enum_values
enum_id | value | label | sort | tone
shift | day | Day | 10 | neutral
shift | night | Night | 20 | neutral
shift | split | Split | 30 | warning
weather | sunny | Sunny | 10 | success
weather | cloudy | Cloudy | 20 | neutral
weather | rain | Rain | 30 | warning
weather | snow | Snow | 40 | warning
weather | high_wind | High wind | 50 | danger
safety_status | clear | Clear | 10 | success
safety_status | watch | Watch | 20 | warning
safety_status | incident | Incident | 30 | danger
quality_status | accepted | Accepted | 10 | success
quality_status | rework_required | Rework required | 20 | warning
quality_status | hold | Hold | 30 | danger
approval_status | draft | Draft | 10 | neutral
approval_status | submitted | Submitted | 20 | warning
approval_status | approved | Approved | 30 | success
approval_status | returned | Returned | 40 | danger
quantity_unit | m2 | m2 | 10 | neutral
quantity_unit | m3 | m3 | 20 | neutral
quantity_unit | ton | ton | 30 | neutral
quantity_unit | set | set | 40 | neutral
work_status | not_started | Not started | 10 | neutral
work_status | in_progress | In progress | 20 | warning
work_status | completed | Completed | 30 | success
work_status | blocked | Blocked | 40 | danger
issue_category | safety | Safety | 10 | danger
issue_category | quality | Quality | 20 | warning
issue_category | schedule | Schedule | 30 | warning
issue_category | coordination | Coordination | 40 | neutral
severity | low | Low | 10 | neutral
severity | medium | Medium | 20 | warning
severity | high | High | 30 | danger
issue_status | open | Open | 10 | warning
issue_status | mitigating | Mitigating | 20 | warning
issue_status | resolved | Resolved | 30 | success
issue_status | closed | Closed | 40 | neutral
relations
relation_id | from_module_id | from_field_id | to_module_id | to_field_id | cardinality