## Guide
Plantilla de registro de inspección de equipos de construcción
Creado para distintas empresas, proyectos y sitios. Cubre datos maestros de equipos, planes de inspección, registros de campo, revisión fotográfica, reparaciones correctivas y resúmenes mensuales.
How to use
1 | Prepare the equipment register | Register equipment ID, category, owning company, responsible owner, criticality, frequency, and next inspection date.
2 | Record inspection work | Plan inspections by date and priority, then record results, defects, downtime, photos, and the next inspection date.
3 | Close repair actions | Convert failed checks into repair actions with due dates, cost, acceptance result, and monthly audit notes.
Legend
Input cell | Editable cells for direct entry.
Required cell | Must be filled before sharing the workbook.
Dropdown cell | Choose one value from the prepared list.
Computed cell | Calculated by formulas and protected from edits.
linked_sheets
sheet_id | sheet_name | kind | module_id
dashboard | Panel
equipment_register | Equipment register
inspection_plan | Inspection plan
inspection_log | Inspection log
photo_register | Photo register
repair_actions | Repair actions
monthly_summary | Monthly summary
lookups | Lookups
schema | Schema

## Panel
Panel
Creado para distintas empresas, proyectos y sitios. Cubre datos maestros de equipos, planes de inspección, registros de campo, revisión fotográfica, reparaciones correctivas y resúmenes mensuales.
Inspections | Defects | Downtime hours

## Equipment register
Equipment register
Creado para distintas empresas, proyectos y sitios. Cubre datos maestros de equipos, planes de inspección, registros de campo, revisión fotográfica, reparaciones correctivas y resúmenes mensuales.
Equipment ID | Equipment name | Category | Model | Serial or plate | Owning company | Site area | Owner | Criticality | Inspection frequency | Photo requirement | Next inspection date | Notes
EQ-001 | Excavator | Earthmoving equipment | ZX200-5 | EXC-005 | North Plant Hire | Excavation area | Equipment coordinator | High | Weekly | Required | 2026-04-08 | Check hydraulic oil, tracks, swing, and warning light before use.
EQ-002 | Construction hoist | Lifting equipment | SC200/200 | HOIST-003 | General contractor site office | Tower B south elevation | Hoist supervisor | Critical | Daily | Required | 2026-04-10 | Protective checks are required while the hoist is in service.

## Inspection plan
Inspection plan
Creado para distintas empresas, proyectos y sitios. Cubre datos maestros de equipos, planes de inspección, registros de campo, revisión fotográfica, reparaciones correctivas y resúmenes mensuales.
Plan ID | Planned date | Inspection type | Equipment ID | Equipment name | Owner | Priority | Planned count | Notes
PL-001 | 2026-04-08 | Pre-start inspection | EQ-001 | Excavator | Sarah Johnson | P3 within 3 days | 1 | Confirm hydraulic oil and warning light before morning excavation.
PL-002 | 2026-04-10 | Scheduled inspection | EQ-002 | Construction hoist | Michael Brown | P1 immediate | 1 | Focus on brake, limit switch, and passenger cage door lock.

## Inspection log
Inspection log
Creado para distintas empresas, proyectos y sitios. Cubre datos maestros de equipos, planes de inspección, registros de campo, revisión fotográfica, reparaciones correctivas y resúmenes mensuales.
Inspection ID | Inspection date | Equipment ID | Equipment name | Inspection type | Inspector | Result | Defect count | Downtime hours | Defect summary | Corrective action required | Photo status | Next inspection date
IN-001 | 2026-04-08 | EQ-001 | Excavator | Pre-start inspection | Sarah Johnson | Pass | 0 | 0 | No issue found. | Not required | Reviewed | 2026-04-15
IN-002 | 2026-04-10 | EQ-002 | Construction hoist | Scheduled inspection | Michael Brown | Failed | 2 | 6 | Upper limit switch is unstable and the warning light needs replacement. | Required | Uploaded | 2026-04-11

## Photo register
Photo register
Creado para distintas empresas, proyectos y sitios. Cubre datos maestros de equipos, planes de inspección, registros de campo, revisión fotográfica, reparaciones correctivas y resúmenes mensuales.
Photo ID | Inspection ID | Photo date | Equipment ID | File path | Reviewer | Review status | Notes
PH-001 | IN-001 | 2026-04-08 | EQ-001 | photos/EQ-001/20260408_prestart.jpg | Safety manager | Reviewed | Pre-start photos are complete.
PH-002 | IN-002 | 2026-04-10 | EQ-002 | photos/EQ-002/20260410_limit.jpg | Safety manager | Uploaded | Add a close-up of the replacement warning light after repair.

## Repair actions
Repair actions
Creado para distintas empresas, proyectos y sitios. Cubre datos maestros de equipos, planes de inspección, registros de campo, revisión fotográfica, reparaciones correctivas y resúmenes mensuales.
Action ID | Inspection ID | Equipment ID | Issue summary | Priority | Owner | Due date | Repair status | Completion date | Repair cost | Acceptance result | Notes
ACT-001 | IN-002 | EQ-002 | Upper limit switch is unstable | P1 immediate | Hoist supervisor | 2026-04-10 | Pending acceptance | 2026-04-10 | 850 | Accepted with conditions | Replace the switch, test travel limit, and upload acceptance photo.
ACT-002 | IN-002 | EQ-002 | Warning light does not activate | P2 within 24 hours | Electrical crew | 2026-04-11 | In progress |  | 0 | Accepted | Replace warning light and confirm wiring during reinspection.

## Monthly summary
Monthly summary
Creado para distintas empresas, proyectos y sitios. Cubre datos maestros de equipos, planes de inspección, registros de campo, revisión fotográfica, reparaciones correctivas y resúmenes mensuales.
Month ID | Month | Total inspections | Pass rate | Failed items | Open repairs | Repair cost | Audit notes
2026-04 | 2026-04-01 | 2 | 50% | 1 | 1 | 850 | Review hoist repair acceptance and attach photo evidence before the monthly safety meeting.

## Lookups (hidden)
Lookups
Creado para distintas empresas, proyectos y sitios. Cubre datos maestros de equipos, planes de inspección, registros de campo, revisión fotográfica, reparaciones correctivas y resúmenes mensuales.
equipment_category | enum_equipment_category_values | enum_equipment_category_labels
option_set | value | label | sort | active
equipment_category | earthmoving | Earthmoving equipment | 10 | TRUE
equipment_category | lifting | Lifting equipment | 20 | TRUE
equipment_category | temporary_power | Temporary power | 30 | TRUE
equipment_category | fire_safety | Fire safety equipment | 40 | TRUE
equipment_category | concrete_equipment | Concrete equipment | 50 | TRUE
criticality | enum_criticality_values | enum_criticality_labels
option_set | value | label | sort | active
criticality | low | Low | 10 | TRUE
criticality | medium | Medium | 20 | TRUE
criticality | high | High | 30 | TRUE
criticality | critical | Critical | 40 | TRUE
inspection_frequency | enum_inspection_frequency_values | enum_inspection_frequency_labels
option_set | value | label | sort | active
inspection_frequency | daily | Daily | 10 | TRUE
inspection_frequency | weekly | Weekly | 20 | TRUE
inspection_frequency | monthly | Monthly | 30 | TRUE
inspection_frequency | before_use | Before each use | 40 | TRUE
inspection_type | enum_inspection_type_values | enum_inspection_type_labels
option_set | value | label | sort | active
inspection_type | pre_start | Pre-start inspection | 10 | TRUE
inspection_type | scheduled | Scheduled inspection | 20 | TRUE
inspection_type | special | Special inspection | 30 | TRUE
inspection_type | reinspection | Reinspection | 40 | TRUE
inspection_result | enum_inspection_result_values | enum_inspection_result_labels
option_set | value | label | sort | active
inspection_result | pass | Pass | 10 | TRUE
inspection_result | observation | Observation | 20 | TRUE
inspection_result | fail | Failed | 30 | TRUE
inspection_result | stopped | Stopped | 40 | TRUE
required_flag | enum_required_flag_values | enum_required_flag_labels
option_set | value | label | sort | active
required_flag | required | Required | 10 | TRUE
required_flag | optional | Optional | 20 | TRUE
required_flag | not_required | Not required | 30 | TRUE
priority | enum_priority_values | enum_priority_labels
option_set | value | label | sort | active
priority | p1_immediate | P1 immediate | 10 | TRUE
priority | p2_24h | P2 within 24 hours | 20 | TRUE
priority | p3_3d | P3 within 3 days | 30 | TRUE
priority | p4_7d | P4 within 7 days | 40 | TRUE
repair_status | enum_repair_status_values | enum_repair_status_labels
option_set | value | label | sort | active
repair_status | not_started | Not started | 10 | TRUE
repair_status | in_progress | In progress | 20 | TRUE
repair_status | pending_acceptance | Pending acceptance | 30 | TRUE
repair_status | closed | Closed | 40 | TRUE
photo_status | enum_photo_status_values | enum_photo_status_labels
option_set | value | label | sort | active
photo_status | not_uploaded | Not uploaded | 10 | TRUE
photo_status | uploaded | Uploaded | 20 | TRUE
photo_status | reviewed | Reviewed | 30 | TRUE
acceptance_result | enum_acceptance_result_values | enum_acceptance_result_labels
option_set | value | label | sort | active
acceptance_result | accepted | Accepted | 10 | TRUE
acceptance_result | conditional | Accepted with conditions | 20 | TRUE
acceptance_result | rejected | Rejected | 30 | TRUE
boolean | boolean_values | boolean_labels
option_set | value | label | sort | active
boolean | true | Yes | 10 | TRUE
boolean | false | No | 20 | TRUE

## Schema (hidden)
Schema
Creado para distintas empresas, proyectos y sitios. Cubre datos maestros de equipos, planes de inspección, registros de campo, revisión fotográfica, reparaciones correctivas y resúmenes mensuales.
modules
module_id | label | description
equipment_register | Equipment register
inspection_plan | Inspection plan
inspection_log | Inspection log
photo_register | Photo register
repair_actions | Repair actions
monthly_summary | Monthly summary
fields
module_id | field_id | label | type | role | enum_id | required
equipment_register | equipment_id | Equipment ID | text | primary_key |  | TRUE
equipment_register | equipment_name | Equipment name | text | display_name |  | TRUE
equipment_register | category | Category | enum | category | equipment_category | TRUE
equipment_register | model | Model | text | input |  | FALSE
equipment_register | serial_or_plate | Serial or plate | text | input |  | FALSE
equipment_register | owning_company | Owning company | text | category |  | FALSE
equipment_register | site_area | Site area | text | category |  | FALSE
equipment_register | owner | Owner | text | owner |  | FALSE
equipment_register | criticality | Criticality | enum | status | criticality | TRUE
equipment_register | frequency | Inspection frequency | enum | category | inspection_frequency | FALSE
equipment_register | photo_requirement | Photo requirement | enum | status | required_flag | FALSE
equipment_register | next_inspection_date | Next inspection date | date | end_date |  | FALSE
equipment_register | notes | Notes | long_text | input |  | FALSE
inspection_plan | plan_id | Plan ID | text | primary_key |  | TRUE
inspection_plan | planned_date | Planned date | date | start_date |  | TRUE
inspection_plan | inspection_type | Inspection type | enum | category | inspection_type | TRUE
inspection_plan | equipment_id | Equipment ID | text | foreign_key |  | FALSE
inspection_plan | equipment_name | Equipment name | text | display_name |  | FALSE
inspection_plan | owner | Owner | text | owner |  | FALSE
inspection_plan | priority | Priority | enum | status | priority | FALSE
inspection_plan | planned_count | Planned count | integer | quantity |  | FALSE
inspection_plan | notes | Notes | long_text | input |  | FALSE
inspection_log | inspection_id | Inspection ID | text | primary_key |  | TRUE
inspection_log | inspection_date | Inspection date | date | created_at |  | TRUE
inspection_log | equipment_id | Equipment ID | text | foreign_key |  | FALSE
inspection_log | equipment_name | Equipment name | text | display_name |  | FALSE
inspection_log | inspection_type | Inspection type | enum | category | inspection_type | FALSE
inspection_log | inspector | Inspector | text | owner |  | FALSE
inspection_log | result | Result | enum | status | inspection_result | TRUE
inspection_log | defect_count | Defect count | integer | quantity |  | FALSE
inspection_log | downtime_hours | Downtime hours | decimal | quantity |  | FALSE
inspection_log | defect_summary | Defect summary | long_text | input |  | FALSE
inspection_log | corrective_required | Corrective action required | enum | status | required_flag | FALSE
inspection_log | photo_status | Photo status | enum | status | photo_status | FALSE
inspection_log | next_inspection_date | Next inspection date | date | end_date |  | FALSE
photo_register | photo_id | Photo ID | text | primary_key |  | TRUE
photo_register | inspection_id | Inspection ID | text | foreign_key |  | FALSE
photo_register | photo_date | Photo date | date | created_at |  | FALSE
photo_register | equipment_id | Equipment ID | text | foreign_key |  | FALSE
photo_register | file_path | File path | text | input |  | FALSE
photo_register | reviewer | Reviewer | text | owner |  | FALSE
photo_register | review_status | Review status | enum | status | photo_status | FALSE
photo_register | notes | Notes | long_text | input |  | FALSE
repair_actions | action_id | Action ID | text | primary_key |  | TRUE
repair_actions | inspection_id | Inspection ID | text | foreign_key |  | FALSE
repair_actions | equipment_id | Equipment ID | text | foreign_key |  | FALSE
repair_actions | issue_summary | Issue summary | long_text | display_name |  | TRUE
repair_actions | priority | Priority | enum | status | priority | TRUE
repair_actions | owner | Owner | text | owner |  | FALSE
repair_actions | due_date | Due date | date | end_date |  | FALSE
repair_actions | repair_status | Repair status | enum | status | repair_status | TRUE
repair_actions | completion_date | Completion date | date | updated_at |  | FALSE
repair_actions | repair_cost | Repair cost | currency | amount |  | FALSE
repair_actions | acceptance_result | Acceptance result | enum | status | acceptance_result | FALSE
repair_actions | notes | Notes | long_text | input |  | FALSE
monthly_summary | month_id | Month ID | text | primary_key |  | TRUE
monthly_summary | month | Month | date | created_at |  | FALSE
monthly_summary | total_inspections | Total inspections | integer | quantity |  | FALSE
monthly_summary | pass_rate | Pass rate | percent | computed |  | FALSE
monthly_summary | failed_items | Failed items | integer | quantity |  | FALSE
monthly_summary | open_repairs | Open repairs | integer | quantity |  | FALSE
monthly_summary | repair_cost | Repair cost | currency | amount |  | FALSE
monthly_summary | audit_notes | Audit notes | long_text | input |  | FALSE
enum_values
enum_id | value | label | sort | tone
equipment_category | earthmoving | Earthmoving equipment | 10 | neutral
equipment_category | lifting | Lifting equipment | 20 | warning
equipment_category | temporary_power | Temporary power | 30 | danger
equipment_category | fire_safety | Fire safety equipment | 40 | warning
equipment_category | concrete_equipment | Concrete equipment | 50 | neutral
criticality | low | Low | 10 | neutral
criticality | medium | Medium | 20 | warning
criticality | high | High | 30 | danger
criticality | critical | Critical | 40 | danger
inspection_frequency | daily | Daily | 10 | warning
inspection_frequency | weekly | Weekly | 20 | neutral
inspection_frequency | monthly | Monthly | 30 | neutral
inspection_frequency | before_use | Before each use | 40 | warning
inspection_type | pre_start | Pre-start inspection | 10 | warning
inspection_type | scheduled | Scheduled inspection | 20 | neutral
inspection_type | special | Special inspection | 30 | danger
inspection_type | reinspection | Reinspection | 40 | warning
inspection_result | pass | Pass | 10 | success
inspection_result | observation | Observation | 20 | warning
inspection_result | fail | Failed | 30 | danger
inspection_result | stopped | Stopped | 40 | danger
required_flag | required | Required | 10 | warning
required_flag | optional | Optional | 20 | neutral
required_flag | not_required | Not required | 30 | neutral
priority | p1_immediate | P1 immediate | 10 | danger
priority | p2_24h | P2 within 24 hours | 20 | danger
priority | p3_3d | P3 within 3 days | 30 | warning
priority | p4_7d | P4 within 7 days | 40 | neutral
repair_status | not_started | Not started | 10 | neutral
repair_status | in_progress | In progress | 20 | warning
repair_status | pending_acceptance | Pending acceptance | 30 | warning
repair_status | closed | Closed | 40 | success
photo_status | not_uploaded | Not uploaded | 10 | warning
photo_status | uploaded | Uploaded | 20 | success
photo_status | reviewed | Reviewed | 30 | success
acceptance_result | accepted | Accepted | 10 | success
acceptance_result | conditional | Accepted with conditions | 20 | warning
acceptance_result | rejected | Rejected | 30 | danger
relations
relation_id | from_module_id | from_field_id | to_module_id | to_field_id | cardinality