## Guide
Modèle de journal d'inspection des équipements de construction
Un classeur pour les contrôles d'équipements, les photos et le suivi des réparations. Vous pouvez remplacer les lignes d'exemple si nécessaire et ajouter d'autres lignes plus tard.
How to use
1 | Prepare the equipment register | Register equipment ID, category, owning company, responsible owner, criticality, frequency, and next inspection date.
2 | Record inspection work | Plan inspections by date and priority, then record results, defects, downtime, photos, and the next inspection date.
3 | Close repair actions | Convert failed checks into repair actions with due dates, cost, acceptance result, and monthly audit notes.
Legend
Input cell | Editable cells for direct entry.
Required cell | Must be filled before sharing the workbook.
Dropdown cell | Choose one value from the prepared list.
Computed cell | Calculated by formulas and protected from edits.
linked_sheets
sheet_id | sheet_name | kind | module_id
dashboard | Tableau de bord
equipment_register | Equipment register
inspection_plan | Inspection plan
inspection_log | Inspection log
photo_register | Photo register
repair_actions | Repair actions
monthly_summary | Monthly summary
lookups | Lookups
schema | Schema

## Tableau de bord
Tableau de bord
Un classeur pour les contrôles d'équipements, les photos et le suivi des réparations. Vous pouvez remplacer les lignes d'exemple si nécessaire et ajouter d'autres lignes plus tard.
Inspections | Defects | Downtime hours

## Equipment register
Equipment register
Un classeur pour les contrôles d'équipements, les photos et le suivi des réparations. Vous pouvez remplacer les lignes d'exemple si nécessaire et ajouter d'autres lignes plus tard.
Equipment ID | Equipment name | Category | Model | Serial or plate | Owning company | Site area | Owner | Criticality | Inspection frequency | Photo requirement | Next inspection date | Notes
EQ-001 | Excavator | Earthmoving equipment | ZX200-5 | EXC-005 | North Plant Hire | Excavation area | Equipment coordinator | High | Weekly | Required | 2026-04-08 | Check hydraulic oil, tracks, swing, and warning light before use.
EQ-002 | Construction hoist | Lifting equipment | SC200/200 | HOIST-003 | General contractor site office | Tower B south elevation | Hoist supervisor | Critical | Daily | Required | 2026-04-10 | Protective checks are required while the hoist is in service.

## Inspection plan
Inspection plan
Un classeur pour les contrôles d'équipements, les photos et le suivi des réparations. Vous pouvez remplacer les lignes d'exemple si nécessaire et ajouter d'autres lignes plus tard.
Plan ID | Planned date | Inspection type | Equipment ID | Equipment name | Owner | Priority | Planned count | Notes
PL-001 | 2026-04-08 | Pre-start inspection | EQ-001 | Excavator | Sarah Johnson | P3 within 3 days | 1 | Confirm hydraulic oil and warning light before morning excavation.
PL-002 | 2026-04-10 | Scheduled inspection | EQ-002 | Construction hoist | Michael Brown | P1 immediate | 1 | Focus on brake, limit switch, and passenger cage door lock.

## Inspection log
Inspection log
Un classeur pour les contrôles d'équipements, les photos et le suivi des réparations. Vous pouvez remplacer les lignes d'exemple si nécessaire et ajouter d'autres lignes plus tard.
Inspection ID | Inspection date | Equipment ID | Equipment name | Inspection type | Inspector | Result | Defect count | Downtime hours | Defect summary | Corrective action required | Photo status | Next inspection date
IN-001 | 2026-04-08 | EQ-001 | Excavator | Pre-start inspection | Sarah Johnson | Pass | 0 | 0 | No issue found. | Not required | Reviewed | 2026-04-15
IN-002 | 2026-04-10 | EQ-002 | Construction hoist | Scheduled inspection | Michael Brown | Failed | 2 | 6 | Upper limit switch is unstable and the warning light needs replacement. | Required | Uploaded | 2026-04-11

## Photo register
Photo register
Un classeur pour les contrôles d'équipements, les photos et le suivi des réparations. Vous pouvez remplacer les lignes d'exemple si nécessaire et ajouter d'autres lignes plus tard.
Photo ID | Inspection ID | Photo date | Equipment ID | File path | Reviewer | Review status | Notes
PH-001 | IN-001 | 2026-04-08 | EQ-001 | photos/EQ-001/20260408_prestart.jpg | Safety manager | Reviewed | Pre-start photos are complete.
PH-002 | IN-002 | 2026-04-10 | EQ-002 | photos/EQ-002/20260410_limit.jpg | Safety manager | Uploaded | Add a close-up of the replacement warning light after repair.

## Repair actions
Repair actions
Un classeur pour les contrôles d'équipements, les photos et le suivi des réparations. Vous pouvez remplacer les lignes d'exemple si nécessaire et ajouter d'autres lignes plus tard.
Action ID | Inspection ID | Equipment ID | Issue summary | Priority | Owner | Due date | Repair status | Completion date | Repair cost | Acceptance result | Notes
ACT-001 | IN-002 | EQ-002 | Upper limit switch is unstable | P1 immediate | Hoist supervisor | 2026-04-10 | Pending acceptance | 2026-04-10 | 850 | Accepted with conditions | Replace the switch, test travel limit, and upload acceptance photo.
ACT-002 | IN-002 | EQ-002 | Warning light does not activate | P2 within 24 hours | Electrical crew | 2026-04-11 | In progress |  | 0 | Accepted | Replace warning light and confirm wiring during reinspection.

## Monthly summary
Monthly summary
Un classeur pour les contrôles d'équipements, les photos et le suivi des réparations. Vous pouvez remplacer les lignes d'exemple si nécessaire et ajouter d'autres lignes plus tard.
Month ID | Month | Total inspections | Pass rate | Failed items | Open repairs | Repair cost | Audit notes
2026-04 | 2026-04-01 | 2 | 50% | 1 | 1 | 850 | Review hoist repair acceptance and attach photo evidence before the monthly safety meeting.

## Lookups (hidden)
Lookups
Un classeur pour les contrôles d'équipements, les photos et le suivi des réparations. Vous pouvez remplacer les lignes d'exemple si nécessaire et ajouter d'autres lignes plus tard.
equipment_category | enum_equipment_category_values | enum_equipment_category_labels
option_set | value | label | sort | active
equipment_category | earthmoving | Earthmoving equipment | 10 | TRUE
equipment_category | lifting | Lifting equipment | 20 | TRUE
equipment_category | temporary_power | Temporary power | 30 | TRUE
equipment_category | fire_safety | Fire safety equipment | 40 | TRUE
equipment_category | concrete_equipment | Concrete equipment | 50 | TRUE
criticality | enum_criticality_values | enum_criticality_labels
option_set | value | label | sort | active
criticality | low | Low | 10 | TRUE
criticality | medium | Medium | 20 | TRUE
criticality | high | High | 30 | TRUE
criticality | critical | Critical | 40 | TRUE
inspection_frequency | enum_inspection_frequency_values | enum_inspection_frequency_labels
option_set | value | label | sort | active
inspection_frequency | daily | Daily | 10 | TRUE
inspection_frequency | weekly | Weekly | 20 | TRUE
inspection_frequency | monthly | Monthly | 30 | TRUE
inspection_frequency | before_use | Before each use | 40 | TRUE
inspection_type | enum_inspection_type_values | enum_inspection_type_labels
option_set | value | label | sort | active
inspection_type | pre_start | Pre-start inspection | 10 | TRUE
inspection_type | scheduled | Scheduled inspection | 20 | TRUE
inspection_type | special | Special inspection | 30 | TRUE
inspection_type | reinspection | Reinspection | 40 | TRUE
inspection_result | enum_inspection_result_values | enum_inspection_result_labels
option_set | value | label | sort | active
inspection_result | pass | Pass | 10 | TRUE
inspection_result | observation | Observation | 20 | TRUE
inspection_result | fail | Failed | 30 | TRUE
inspection_result | stopped | Stopped | 40 | TRUE
required_flag | enum_required_flag_values | enum_required_flag_labels
option_set | value | label | sort | active
required_flag | required | Required | 10 | TRUE
required_flag | optional | Optional | 20 | TRUE
required_flag | not_required | Not required | 30 | TRUE
priority | enum_priority_values | enum_priority_labels
option_set | value | label | sort | active
priority | p1_immediate | P1 immediate | 10 | TRUE
priority | p2_24h | P2 within 24 hours | 20 | TRUE
priority | p3_3d | P3 within 3 days | 30 | TRUE
priority | p4_7d | P4 within 7 days | 40 | TRUE
repair_status | enum_repair_status_values | enum_repair_status_labels
option_set | value | label | sort | active
repair_status | not_started | Not started | 10 | TRUE
repair_status | in_progress | In progress | 20 | TRUE
repair_status | pending_acceptance | Pending acceptance | 30 | TRUE
repair_status | closed | Closed | 40 | TRUE
photo_status | enum_photo_status_values | enum_photo_status_labels
option_set | value | label | sort | active
photo_status | not_uploaded | Not uploaded | 10 | TRUE
photo_status | uploaded | Uploaded | 20 | TRUE
photo_status | reviewed | Reviewed | 30 | TRUE
acceptance_result | enum_acceptance_result_values | enum_acceptance_result_labels
option_set | value | label | sort | active
acceptance_result | accepted | Accepted | 10 | TRUE
acceptance_result | conditional | Accepted with conditions | 20 | TRUE
acceptance_result | rejected | Rejected | 30 | TRUE
boolean | boolean_values | boolean_labels
option_set | value | label | sort | active
boolean | true | Yes | 10 | TRUE
boolean | false | No | 20 | TRUE

## Schema (hidden)
Schema
Un classeur pour les contrôles d'équipements, les photos et le suivi des réparations. Vous pouvez remplacer les lignes d'exemple si nécessaire et ajouter d'autres lignes plus tard.
modules
module_id | label | description
equipment_register | Equipment register
inspection_plan | Inspection plan
inspection_log | Inspection log
photo_register | Photo register
repair_actions | Repair actions
monthly_summary | Monthly summary
fields
module_id | field_id | label | type | role | enum_id | required
equipment_register | equipment_id | Equipment ID | text | primary_key |  | TRUE
equipment_register | equipment_name | Equipment name | text | display_name |  | TRUE
equipment_register | category | Category | enum | category | equipment_category | TRUE
equipment_register | model | Model | text | input |  | FALSE
equipment_register | serial_or_plate | Serial or plate | text | input |  | FALSE
equipment_register | owning_company | Owning company | text | category |  | FALSE
equipment_register | site_area | Site area | text | category |  | FALSE
equipment_register | owner | Owner | text | owner |  | FALSE
equipment_register | criticality | Criticality | enum | status | criticality | TRUE
equipment_register | frequency | Inspection frequency | enum | category | inspection_frequency | FALSE
equipment_register | photo_requirement | Photo requirement | enum | status | required_flag | FALSE
equipment_register | next_inspection_date | Next inspection date | date | end_date |  | FALSE
equipment_register | notes | Notes | long_text | input |  | FALSE
inspection_plan | plan_id | Plan ID | text | primary_key |  | TRUE
inspection_plan | planned_date | Planned date | date | start_date |  | TRUE
inspection_plan | inspection_type | Inspection type | enum | category | inspection_type | TRUE
inspection_plan | equipment_id | Equipment ID | text | foreign_key |  | FALSE
inspection_plan | equipment_name | Equipment name | text | display_name |  | FALSE
inspection_plan | owner | Owner | text | owner |  | FALSE
inspection_plan | priority | Priority | enum | status | priority | FALSE
inspection_plan | planned_count | Planned count | integer | quantity |  | FALSE
inspection_plan | notes | Notes | long_text | input |  | FALSE
inspection_log | inspection_id | Inspection ID | text | primary_key |  | TRUE
inspection_log | inspection_date | Inspection date | date | created_at |  | TRUE
inspection_log | equipment_id | Equipment ID | text | foreign_key |  | FALSE
inspection_log | equipment_name | Equipment name | text | display_name |  | FALSE
inspection_log | inspection_type | Inspection type | enum | category | inspection_type | FALSE
inspection_log | inspector | Inspector | text | owner |  | FALSE
inspection_log | result | Result | enum | status | inspection_result | TRUE
inspection_log | defect_count | Defect count | integer | quantity |  | FALSE
inspection_log | downtime_hours | Downtime hours | decimal | quantity |  | FALSE
inspection_log | defect_summary | Defect summary | long_text | input |  | FALSE
inspection_log | corrective_required | Corrective action required | enum | status | required_flag | FALSE
inspection_log | photo_status | Photo status | enum | status | photo_status | FALSE
inspection_log | next_inspection_date | Next inspection date | date | end_date |  | FALSE
photo_register | photo_id | Photo ID | text | primary_key |  | TRUE
photo_register | inspection_id | Inspection ID | text | foreign_key |  | FALSE
photo_register | photo_date | Photo date | date | created_at |  | FALSE
photo_register | equipment_id | Equipment ID | text | foreign_key |  | FALSE
photo_register | file_path | File path | text | input |  | FALSE
photo_register | reviewer | Reviewer | text | owner |  | FALSE
photo_register | review_status | Review status | enum | status | photo_status | FALSE
photo_register | notes | Notes | long_text | input |  | FALSE
repair_actions | action_id | Action ID | text | primary_key |  | TRUE
repair_actions | inspection_id | Inspection ID | text | foreign_key |  | FALSE
repair_actions | equipment_id | Equipment ID | text | foreign_key |  | FALSE
repair_actions | issue_summary | Issue summary | long_text | display_name |  | TRUE
repair_actions | priority | Priority | enum | status | priority | TRUE
repair_actions | owner | Owner | text | owner |  | FALSE
repair_actions | due_date | Due date | date | end_date |  | FALSE
repair_actions | repair_status | Repair status | enum | status | repair_status | TRUE
repair_actions | completion_date | Completion date | date | updated_at |  | FALSE
repair_actions | repair_cost | Repair cost | currency | amount |  | FALSE
repair_actions | acceptance_result | Acceptance result | enum | status | acceptance_result | FALSE
repair_actions | notes | Notes | long_text | input |  | FALSE
monthly_summary | month_id | Month ID | text | primary_key |  | TRUE
monthly_summary | month | Month | date | created_at |  | FALSE
monthly_summary | total_inspections | Total inspections | integer | quantity |  | FALSE
monthly_summary | pass_rate | Pass rate | percent | computed |  | FALSE
monthly_summary | failed_items | Failed items | integer | quantity |  | FALSE
monthly_summary | open_repairs | Open repairs | integer | quantity |  | FALSE
monthly_summary | repair_cost | Repair cost | currency | amount |  | FALSE
monthly_summary | audit_notes | Audit notes | long_text | input |  | FALSE
enum_values
enum_id | value | label | sort | tone
equipment_category | earthmoving | Earthmoving equipment | 10 | neutral
equipment_category | lifting | Lifting equipment | 20 | warning
equipment_category | temporary_power | Temporary power | 30 | danger
equipment_category | fire_safety | Fire safety equipment | 40 | warning
equipment_category | concrete_equipment | Concrete equipment | 50 | neutral
criticality | low | Low | 10 | neutral
criticality | medium | Medium | 20 | warning
criticality | high | High | 30 | danger
criticality | critical | Critical | 40 | danger
inspection_frequency | daily | Daily | 10 | warning
inspection_frequency | weekly | Weekly | 20 | neutral
inspection_frequency | monthly | Monthly | 30 | neutral
inspection_frequency | before_use | Before each use | 40 | warning
inspection_type | pre_start | Pre-start inspection | 10 | warning
inspection_type | scheduled | Scheduled inspection | 20 | neutral
inspection_type | special | Special inspection | 30 | danger
inspection_type | reinspection | Reinspection | 40 | warning
inspection_result | pass | Pass | 10 | success
inspection_result | observation | Observation | 20 | warning
inspection_result | fail | Failed | 30 | danger
inspection_result | stopped | Stopped | 40 | danger
required_flag | required | Required | 10 | warning
required_flag | optional | Optional | 20 | neutral
required_flag | not_required | Not required | 30 | neutral
priority | p1_immediate | P1 immediate | 10 | danger
priority | p2_24h | P2 within 24 hours | 20 | danger
priority | p3_3d | P3 within 3 days | 30 | warning
priority | p4_7d | P4 within 7 days | 40 | neutral
repair_status | not_started | Not started | 10 | neutral
repair_status | in_progress | In progress | 20 | warning
repair_status | pending_acceptance | Pending acceptance | 30 | warning
repair_status | closed | Closed | 40 | success
photo_status | not_uploaded | Not uploaded | 10 | warning
photo_status | uploaded | Uploaded | 20 | success
photo_status | reviewed | Reviewed | 30 | success
acceptance_result | accepted | Accepted | 10 | success
acceptance_result | conditional | Accepted with conditions | 20 | warning
acceptance_result | rejected | Rejected | 30 | danger
relations
relation_id | from_module_id | from_field_id | to_module_id | to_field_id | cardinality