## Dashboard
Construction Earned Value Management Monitor
Designed for general contractors, EPC teams, trade contractors, multiple packages, multiple disciplines, and recurring reporting cycles. PV, EV, AC, SPI, CPI, EAC, and VAC are used to monitor schedule and cost together.
Project Overview | [6 empty] | Alert Summary
Company | General Construction Company | [5 empty] | Red WBS Count | 11 | Immediate Correction
Project | Sample Construction Project | [5 empty] | Yellow WBS Count | 6 | Focused Tracking
Period | P06 | [5 empty] | Open Alert Count | 0 | Correction Closure
Cutoff Date | 2026-06-30 | [5 empty] | Overdue Action Count | 0 | Owner Tracking
Contract Type | Lump-sum Contract
Core KPIs (Current Period) | [6 empty] | Applicable Business Scenarios
Metric | Value | Notes | Metric | Value | Notes |  | General Contractor / EPC | Multi-dimensional performance by package, discipline, and subcontractor
Total BAC Budget | 35758000 | Budget at Completion | SV | -1452600 | EV-PV |  | Trade Contractor | Focus on WBS and cost within the contract scope
PV | 12903500 | Planned Value | CV | -759100 | EV-AC |  | Owner / Development Manager | Compare contractor and package execution
EV | 11450900 | Earned Value | SPI | 0.88743 | EV/PV |  | Supervisor / Consultant | Monthly report review, alerts, and corrective-action closure
AC | 12210000 | Actual Cost | CPI | 0.93783 | EV/AC |  | Cost / Contract | Link changes, actual cost, and completion forecasts
EAC | 38128459.7717 | Estimate at Completion | VAC | -2370459.7717 | BAC-EAC
Completion Rate | 32.02% | EV/BAC | Overall Alert | Yellow | Red / Yellow / Green
Trend Monitor (linked from Period Summary and ready for conditional-format variance review)
Period | PV | EV | AC | SV | CV | SPI | CPI | Completion Rate | Cost Consumption Rate | Alert
P01 | 560000 | 488500 | 500000 | -71500 | -11500 | 0.87232 | 0.977 | 1.366% | 1.398% | Yellow
P02 | 2221300 | 1940700 | 1975000 | -280600 | -34300 | 0.87368 | 0.98263 | 5.427% | 5.523% | Yellow
P03 | 4655000 | 4116950 | 4050000 | -538050 | 66950 | 0.88441 | 1.0165 | 11.51% | 11.33% | Yellow
P04 | 7427000 | 6593600 | 6920000 | -833400 | -326400 | 0.88779 | 0.95283 | 18.44% | 19.35% | Yellow
P05 | 10250300 | 9176420 | 9630000 | -1073880 | -453580 | 0.89523 | 0.9529 | 25.66% | 26.93% | Yellow
P06 | 12903500 | 11450900 | 12210000 | -1452600 | -759100 | 0.88743 | 0.93783 | 32.02% | 34.15% | Yellow

## Project Information
Construction Earned Value Management Monitor - Project Information
Yellow cells are inputs and green cells are automatic summaries or formulas. The template has no company branding, so company, project, package, and contract-party names can be replaced directly.
Category | Parameter | Current Value | Notes | Editable | Example
Master Data | Company Name | General Construction Company | Replace with your company name | Yes | Example Construction Group
Master Data | Project Name | Sample Construction Project | Full project name | Yes | Industrial Park Phase 1 General Contract
Master Data | Project ID | PRJ-2026-001 | Internal project ID | Yes | PRJ-XXXX
Master Data | Current Reporting Period | P06 | Used by the dashboard and scenario analysis | Yes | P01/P02/...
Master Data | Reporting Frequency | Monthly | Weekly/Monthly/Quarterly | Yes | Monthly
Master Data | Planned Start | 46023 | Planned start date | Yes | 2026-01-01
Master Data | Planned Finish | 2026-12-31 | Planned finish date | Yes | 2026-12-31
Master Data | Data Cutoff | 2026-06-30 | Current report cutoff date | Yes | 2026-06-30
Master Data | Currency | CNY | Amount currency | Yes | CNY/USD
Master Data | Contract Type | Lump-sum Contract | General contractor / EPC / trade contractor, etc. | Yes | EPC
Automatic Summary | Total BAC Budget | 35758000 | Automatically summarize WBS BAC | No
Threshold | SPIYellowThreshold | 0.95 | Yellow alert if below threshold | Yes | 0.95
Threshold | SPIRedThreshold | 0.85 | Red alert if below threshold | Yes | 0.85
Threshold | CPIYellowThreshold | 0.95 | Yellow alert if below threshold | Yes | 0.95
Threshold | CPIRedThreshold | 0.85 | Red alert if below threshold | Yes | 0.85

## WBS Plan
WBS Plan and Baseline Budget
Enter baseline scope and budget by WBS, package, discipline, and phase. Column N is BAC, calculated by default as quantity times budget unit rate; column O is the budget weight.
WBS Code | Parent WBS | Project / Package | Discipline / System | Phase / Area | Work Package | Contract / Subcontractor | Owner / Department | Planned Start | Planned Finish | Planned Quantity | Unit | Budget Unit Rate | BAC | Weight % | Critical Path | Status | Remarks
WBS-001 |  | Package A | Civil | Preparation Works | Temporary Works and Site Preparation | Self-performed by GC | Project Engineering Department | 2026-01-01 | 2026-01-31 | 1 | item | 300000 | 300000 | 0.839% | Yes | Completed | Sample, replace as needed
WBS-002 |  | Package A | Civil | Foundation Works | Earthwork Excavation | Earthwork Subcontractor | Civil Team | 2026-01-10 | 2026-02-28 | 12000 | m³ | 65 | 780000 | 2.181% | Yes | Completed
WBS-003 |  | Package A | Structural | Foundation Works | Pile Foundation Works | Pile Foundation Subcontractor | Structural Team | 2026-01-20 | 2026-03-15 | 260 | pile | 2500 | 650000 | 1.818% | Yes | Completed
WBS-004 |  | Package A | Structural | Superstructure Works | Main Structure | Structural Labor Subcontractor | Structural Team | 2026-02-10 | 2026-08-31 | 18000 | m² | 850 | 15300000 | 42.79% | Yes | In Progress
WBS-005 |  | Package A | MEP | MEP Installation | MEP Sleeves and Embeds | MEP Subcontractor | MEP Team | 2026-02-15 | 2026-08-31 | 18000 | m² | 95 | 1710000 | 4.782% | No | In Progress
WBS-006 |  | Package A | Curtain Wall | Facade Works | Curtain Wall Works | Curtain Wall Subcontractor | Curtain Wall Team | 2026-07-01 | 2026-10-31 | 6800 | m² | 760 | 5168000 | 14.45% | No | Not Started
WBS-007 |  | Package A | Fit-out | Interior Works | Interior Fit-out | Fit-out Subcontractor | Fit-out Team | 2026-08-01 | 2026-11-30 | 15000 | m² | 650 | 9750000 | 27.27% | No | Not Started
WBS-008 |  | Package A | Landscape | External Works | External Landscape | Landscape Subcontractor | Landscape Team | 2026-10-01 | 2026-12-20 | 1 | item | 2100000 | 2100000 | 5.873% | No | Not Started

## Periodic Data
Periodic Data Entry (PV / EV / AC / SPI / CPI)
For each reporting period, enter planned completion, actual completion, quality acceptance rate, and cumulative actual cost for each WBS. Columns D:H and N:W are calculated automatically.
Period | Cutoff Date | WBS Code | Project / Package | Work Package | Discipline | Responsible Party | BAC | Planned Completion % | Actual Completion % | Quality Acceptance % | AC | Approved Changes | PV | EV | SV | CV | SPI | CPI | EAC | ETC | VAC | Alert | Risk Level | Data Source | Prepared By | Remarks
P01 | 2026-01-31 | WBS-001 | Package A | Temporary Works and Site Preparation | Civil | Self-performed by GC | 300000 | 100% | 100% | 100% | 310000 | 0 | 300000 | 300000 | 0 | -10000 | 1 | 0.96774 | 310000 | 0 | -10000 | Green | Low | Sample Register | Planning Engineer
P01 | 2026-01-31 | WBS-002 | Package A | Earthwork Excavation | Civil | Earthwork Subcontractor | 780000 | 25% | 20% | 100% | 150000 | 0 | 195000 | 156000 | -39000 | 6000 | 0.8 | 1.04 | 750000 | 600000 | 30000 | Red | Medium | Sample Register | Planning Engineer
P01 | 2026-01-31 | WBS-003 | Package A | Pile Foundation Works | Structural | Pile Foundation Subcontractor | 650000 | 10% | 5% | 100% | 40000 | 0 | 65000 | 32500 | -32500 | -7500 | 0.5 | 0.8125 | 800000 | 760000 | -150000 | Red | Medium | Sample Register | Planning Engineer
P01 | 2026-01-31 | WBS-004 | Package A | Main Structure | Structural | Structural Labor Subcontractor | 15300000 | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 15300000 | 15300000 | 0 | Red | Low | Sample Register | Planning Engineer
P01 | 2026-01-31 | WBS-005 | Package A | MEP Sleeves and Embeds | MEP | MEP Subcontractor | 1710000 | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1710000 | 1710000 | 0 | Red | Low | Sample Register | Planning Engineer
P02 | 2026-02-28 | WBS-001 | Package A | Temporary Works and Site Preparation | Civil | Self-performed by GC | 300000 | 100% | 100% | 100% | 310000 | 0 | 300000 | 300000 | 0 | -10000 | 1 | 0.96774 | 310000 | 0 | -10000 | Green | Low | Sample Register | Planning Engineer
P02 | 2026-02-28 | WBS-002 | Package A | Earthwork Excavation | Civil | Earthwork Subcontractor | 780000 | 100% | 90% | 100% | 650000 | 0 | 780000 | 702000 | -78000 | 52000 | 0.9 | 1.08 | 722222.2222 | 72222.2222 | 57777.7778 | Yellow | Medium | Sample Register | Planning Engineer
P02 | 2026-02-28 | WBS-003 | Package A | Pile Foundation Works | Structural | Pile Foundation Subcontractor | 650000 | 50% | 45% | 100% | 330000 | 0 | 325000 | 292500 | -32500 | -37500 | 0.9 | 0.88636 | 733333.3333 | 403333.3333 | -83333.3333 | Yellow | Medium | Sample Register | Planning Engineer
P02 | 2026-02-28 | WBS-004 | Package A | Main Structure | Structural | Structural Labor Subcontractor | 15300000 | 5% | 4% | 100% | 650000 | 0 | 765000 | 612000 | -153000 | -38000 | 0.8 | 0.94154 | 16250000 | 15600000 | -950000 | Red | Low | Sample Register | Planning Engineer
P02 | 2026-02-28 | WBS-005 | Package A | MEP Sleeves and Embeds | MEP | MEP Subcontractor | 1710000 | 3% | 2% | 100% | 35000 | 0 | 51300 | 34200 | -17100 | -800 | 0.66667 | 0.97714 | 1750000 | 1715000 | -40000 | Red | Low | Sample Register | Planning Engineer
P03 | 2026-03-31 | WBS-001 | Package A | Temporary Works and Site Preparation | Civil | Self-performed by GC | 300000 | 100% | 100% | 100% | 310000 | 0 | 300000 | 300000 | 0 | -10000 | 1 | 0.96774 | 310000 | 0 | -10000 | Green | Low | Sample Register | Planning Engineer
P03 | 2026-03-31 | WBS-002 | Package A | Earthwork Excavation | Civil | Earthwork Subcontractor | 780000 | 100% | 100% | 100% | 760000 | 0 | 780000 | 780000 | 0 | 20000 | 1 | 1.0263 | 760000 | -1.1642e-10 | 20000 | Green | Low | Sample Register | Planning Engineer
P03 | 2026-03-31 | WBS-003 | Package A | Pile Foundation Works | Structural | Pile Foundation Subcontractor | 650000 | 100% | 95% | 98% | 650000 | 0 | 650000 | 605150 | -44850 | -44850 | 0.931 | 0.931 | 698174.0064 | 48174.0064 | -48174.0064 | Yellow | Medium | Sample Register | Planning Engineer
P03 | 2026-03-31 | WBS-004 | Package A | Main Structure | Structural | Structural Labor Subcontractor | 15300000 | 18% | 15% | 100% | 2200000 | 0 | 2754000 | 2295000 | -459000 | 95000 | 0.83333 | 1.0432 | 14666666.6667 | 12466666.6667 | 633333.3333 | Red | Medium | Sample Register | Planning Engineer
P03 | 2026-03-31 | WBS-005 | Package A | MEP Sleeves and Embeds | MEP | MEP Subcontractor | 1710000 | 10% | 8% | 100% | 130000 | 0 | 171000 | 136800 | -34200 | 6800 | 0.8 | 1.0523 | 1625000 | 1495000 | 85000 | Red | Low | Sample Register | Planning Engineer
P04 | 2026-04-30 | WBS-001 | Package A | Temporary Works and Site Preparation | Civil | Self-performed by GC | 300000 | 100% | 100% | 100% | 310000 | 0 | 300000 | 300000 | 0 | -10000 | 1 | 0.96774 | 310000 | 0 | -10000 | Green | Low | Sample Register | Planning Engineer
P04 | 2026-04-30 | WBS-002 | Package A | Earthwork Excavation | Civil | Earthwork Subcontractor | 780000 | 100% | 100% | 100% | 780000 | 0 | 780000 | 780000 | 0 | 0 | 1 | 1 | 780000 | 0 | 0 | Green | Low | Sample Register | Planning Engineer
P04 | 2026-04-30 | WBS-003 | Package A | Pile Foundation Works | Structural | Pile Foundation Subcontractor | 650000 | 100% | 100% | 100% | 670000 | 0 | 650000 | 650000 | 0 | -20000 | 1 | 0.97015 | 670000 | 0 | -20000 | Green | Low | Sample Register | Planning Engineer
P04 | 2026-04-30 | WBS-004 | Package A | Main Structure | Structural | Structural Labor Subcontractor | 15300000 | 35% | 30% | 100% | 4900000 | 0 | 5355000 | 4590000 | -765000 | -310000 | 0.85714 | 0.93673 | 16333333.3333 | 11433333.3333 | -1033333.3333 | Yellow | Medium | Sample Register | Planning Engineer
P04 | 2026-04-30 | WBS-005 | Package A | MEP Sleeves and Embeds | MEP | MEP Subcontractor | 1710000 | 20% | 16% | 100% | 260000 | 0 | 342000 | 273600 | -68400 | 13600 | 0.8 | 1.0523 | 1625000 | 1365000 | 85000 | Red | Medium | Sample Register | Planning Engineer
P05 | 2026-05-31 | WBS-001 | Package A | Temporary Works and Site Preparation | Civil | Self-performed by GC | 300000 | 100% | 100% | 100% | 310000 | 0 | 300000 | 300000 | 0 | -10000 | 1 | 0.96774 | 310000 | 0 | -10000 | Green | Low | Sample Register | Planning Engineer
P05 | 2026-05-31 | WBS-002 | Package A | Earthwork Excavation | Civil | Earthwork Subcontractor | 780000 | 100% | 100% | 100% | 780000 | 0 | 780000 | 780000 | 0 | 0 | 1 | 1 | 780000 | 0 | 0 | Green | Low | Sample Register | Planning Engineer
P05 | 2026-05-31 | WBS-003 | Package A | Pile Foundation Works | Structural | Pile Foundation Subcontractor | 650000 | 100% | 100% | 100% | 670000 | 0 | 650000 | 650000 | 0 | -20000 | 1 | 0.97015 | 670000 | 0 | -20000 | Green | Low | Sample Register | Planning Engineer
P05 | 2026-05-31 | WBS-004 | Package A | Main Structure | Structural | Structural Labor Subcontractor | 15300000 | 52% | 46% | 99% | 7400000 | 0 | 7956000 | 6967620 | -988380 | -432380 | 0.87577 | 0.94157 | 16249451.0321 | 8849451.0321 | -949451.0321 | Yellow | High | Sample Register | Planning Engineer
P05 | 2026-05-31 | WBS-005 | Package A | MEP Sleeves and Embeds | MEP | MEP Subcontractor | 1710000 | 33% | 28% | 100% | 470000 | 0 | 564300 | 478800 | -85500 | 8800 | 0.84848 | 1.0187 | 1678571.4286 | 1208571.4286 | 31428.5714 | Red | Medium | Sample Register | Planning Engineer
P06 | 2026-06-30 | WBS-001 | Package A | Temporary Works and Site Preparation | Civil | Self-performed by GC | 300000 | 100% | 100% | 100% | 310000 | 0 | 300000 | 300000 | 0 | -10000 | 1 | 0.96774 | 310000 | 0 | -10000 | Green | Low | Sample Register | Planning Engineer
P06 | 2026-06-30 | WBS-002 | Package A | Earthwork Excavation | Civil | Earthwork Subcontractor | 780000 | 100% | 100% | 100% | 780000 | 0 | 780000 | 780000 | 0 | 0 | 1 | 1 | 780000 | 0 | 0 | Green | Low | Sample Register | Planning Engineer
P06 | 2026-06-30 | WBS-003 | Package A | Pile Foundation Works | Structural | Pile Foundation Subcontractor | 650000 | 100% | 100% | 100% | 670000 | 0 | 650000 | 650000 | 0 | -20000 | 1 | 0.97015 | 670000 | 0 | -20000 | Green | Low | Sample Register | Planning Engineer
P06 | 2026-06-30 | WBS-004 | Package A | Main Structure | Structural | Structural Labor Subcontractor | 15300000 | 68% | 60% | 99% | 9800000 | 0 | 10404000 | 9088200 | -1315800 | -711800 | 0.87353 | 0.92737 | 16498316.4983 | 6698316.4983 | -1198316.4983 | Yellow | High | Sample Register | Planning Engineer
P06 | 2026-06-30 | WBS-005 | Package A | MEP Sleeves and Embeds | MEP | MEP Subcontractor | 1710000 | 45% | 37% | 100% | 650000 | 0 | 769500 | 632700 | -136800 | -17300 | 0.82222 | 0.97338 | 1756756.7568 | 1106756.7568 | -46756.7568 | Red | Medium | Sample Register | Planning Engineer

## Period Summary
Period Summary Analysis
Automatically summarizes cumulative PV, EV, AC, variances, performance indexes, and completion forecasts by reporting period.
Period | Cutoff Date | PV | EV | AC | SV | CV | SPI | CPI | EAC | ETC | VAC | Completion Rate | Cost Consumption Rate | Alert
P01 | 2026-01-01 | 560000 | 488500 | 500000 | -71500 | -11500 | 0.87232 | 0.977 | 36599795.2917 | 36099795.2917 | -841795.2917 | 1.366% | 1.398% | Yellow
P02 | 2026-02-01 | 2221300 | 1940700 | 1975000 | -280600 | -34300 | 0.87368 | 0.98263 | 36389988.1486 | 34414988.1486 | -631988.1486 | 5.427% | 5.523% | Yellow
P03 | 2026-03-01 | 4655000 | 4116950 | 4050000 | -538050 | 66950 | 0.88441 | 1.0165 | 35176502.0221 | 31126502.0221 | 581497.9779 | 11.51% | 11.33% | Yellow
P04 | 2026-04-01 | 7427000 | 6593600 | 6920000 | -833400 | -326400 | 0.88779 | 0.95283 | 37528112.1087 | 30608112.1087 | -1770112.1087 | 18.44% | 19.35% | Yellow
P05 | 2026-05-01 | 10250300 | 9176420 | 9630000 | -1073880 | -453580 | 0.89523 | 0.9529 | 37525477.2558 | 27895477.2558 | -1767477.2558 | 25.66% | 26.93% | Yellow
P06 | 2026-06-01 | 12903500 | 11450900 | 12210000 | -1452600 | -759100 | 0.88743 | 0.93783 | 38128459.7717 | 25918459.7717 | -2370459.7717 | 32.02% | 34.15% | Yellow

## Scenario Analysis
Segment Scenario Analysis (Multiple Packages / Disciplines / Contract Parties)
Select the reporting period in B4 to summarize current-period PV, EV, AC, and performance by project package, discipline or system, and contract party or subcontractor.
Current Period | P06
Dimension | Category | BAC | PV | EV | AC | SV | CV | SPI | CPI | Alert
Project / Package | Package A | 35758000 | 12903500 | 11450900 | 12210000 | -1452600 | -759100 | 0.88743 | 0.93783 | Yellow
Project / Package | Package B | 0 | 0 | 0 | 0 | 0 | 0
Project / Package | Package C | 0 | 0 | 0 | 0 | 0 | 0
Discipline / System | Civil | 1080000 | 1080000 | 1080000 | 1090000 | 0 | -10000 | 1 | 0.99083 | Green
Discipline / System | Structural | 15950000 | 11054000 | 9738200 | 10470000 | -1315800 | -731800 | 0.88097 | 0.93011 | Yellow
Discipline / System | MEP | 1710000 | 769500 | 632700 | 650000 | -136800 | -17300 | 0.82222 | 0.97338 | Red
Discipline / System | Curtain Wall | 5168000 | 0 | 0 | 0 | 0 | 0 |  |  | Red
Discipline / System | Fit-out | 9750000 | 0 | 0 | 0 | 0 | 0 |  |  | Red
Discipline / System | Landscape | 2100000 | 0 | 0 | 0 | 0 | 0 |  |  | Red
Contract / Subcontractor | Self-performed by GC | 300000 | 300000 | 300000 | 310000 | 0 | -10000 | 1 | 0.96774 | Green
Contract / Subcontractor | Earthwork Subcontractor | 780000 | 780000 | 780000 | 780000 | 0 | 0 | 1 | 1 | Green
Contract / Subcontractor | Pile Foundation Subcontractor | 650000 | 650000 | 650000 | 670000 | 0 | -20000 | 1 | 0.97015 | Green
Contract / Subcontractor | Structural Labor Subcontractor | 15300000 | 10404000 | 9088200 | 9800000 | -1315800 | -711800 | 0.87353 | 0.92737 | Yellow
Contract / Subcontractor | MEP Subcontractor | 1710000 | 769500 | 632700 | 650000 | -136800 | -17300 | 0.82222 | 0.97338 | Red

## Risk Correction
Risk Alert and Corrective Action Register
Record causes, actions, owners, planned closure dates, and closure evidence after red or yellow alerts to create closed-loop control.
Alert ID | Period | WBS Code | Project / Package | Discipline | Trigger Metric | Risk Level | Cause Category | Cause Description | Corrective Action | Owner | Closure Date | Correction Status | Closure Evidence | Linked SPI | Linked CPI | Overdue
R-001 | P06 | WBS-004 | Package A | Structural | SPI/CPI | High | Insufficient Resources | Main structure actual completion is below plan | Add labor crews, adjust work sections, and review the critical path weekly | Project Manager | 2026-07-15 | In Progress |  | 0.87353 | 0.92737
R-002 | P06 | WBS-005 | Package A | MEP | SPI | Medium | Supply Delay | MEP sleeve and embed materials arrived late | Lock delivery plans and activate backup suppliers | MEP Manager | 2026-07-10 | Not Started |  | 0.82222 | 0.97338
Formulas:
Overdue = IF([Alert ID]="","",IF(AND([Correction Status]<>"Closed",[Closure Date]<TODAY()),"Overdue",""))

## Formula Sources
Formula Notes and Sources
Uses standard earned value management formulas. Organizations can adjust the EAC method, thresholds, and quality discount rules to match PMO or contract requirements.
Metric | Chinese Name | English Name | Formula / Logic | Business Meaning | Applicable Scenario | Notes | Source URL
BAC | Budget at Completion | Budget at Completion | Sum of WBS baseline budgets | Total project baseline budget | General contractor / EPC / trade contractor / multiple packages | Control changes after baseline freeze | https://www.vertex42.com/ExcelTemplates/earned-value-management.html
PV/BCWS | Planned Value / Budgeted Cost of Work Scheduled | Planned Value | BAC x planned completion % | Budgeted value of work scheduled to be completed | Weekly report / monthly report / milestone | Planned completion should come from the approved schedule | https://www.233.com/jzs2/zhishiku/189/202604/03102535181665.html
EV/BCWP | Earned Value / Budgeted Cost of Work Performed | Earned Value | BAC x actual completion % x quality acceptance % | Budgeted value of completed and accepted work | Progress measurement, monthly output value, and acceptance | Unaccepted or reworked items can reduce EV | https://www.233.com/jzs2/zhishiku/189/202604/03102535181665.html
AC/ACWP | Actual Cost | Actual Cost | Cumulative Actual Cost | Actual cost incurred | Cost ledger, ERP, materials, and labor cost | Enter using a cumulative basis | https://www.vertex42.com/ExcelTemplates/earned-value-management.html
SV | Schedule Variance | Schedule Variance | EV-PV | Positive means ahead; negative means behind | Schedule Alert | A monetary measure, not directly equal to days | https://www.pmi.org/learning/library/earned-value-management-systems-document-integration-excel-9284
CV | Cost Variance | Cost Variance | EV-AC | Positive means savings; negative means overrun | Cost Control | Interpret together with changes and procurement basis | https://www.pmi.org/learning/library/earned-value-management-systems-document-integration-excel-9284
SPI | Schedule Performance Index | Schedule Performance Index | EV/PV | Above 1 means ahead; below 1 means behind | Red-yellow-green Schedule Alert | Do not calculate when PV is zero | https://www.vertex42.com/ExcelTemplates/earned-value-management.html
CPI | Cost Performance Index | Cost Performance Index | EV/AC | Above 1 means savings; below 1 means overrun | Cost Performance Alert | Do not calculate when AC is zero | https://www.vertex42.com/ExcelTemplates/earned-value-management.html
EAC | Estimate at Completion | Estimate at Completion | If CPI > 0, BAC / CPI; otherwise AC + (BAC - EV) | Forecast total cost at completion | Rolling forecast and management monthly report | Can be changed to the company standard method | https://www.projectmanagement.com/deliverables/544342/evm-worksheet-package
ETC | Estimate to Complete | Estimate to Complete | EAC-AC | Forecast remaining cost | Cash planning and resource planning | Depends on the EAC method | https://www.vertex42.com/ExcelTemplates/earned-value-management.html
VAC | Variance at Completion | Variance at Completion | BAC-EAC | Forecast savings or overrun at completion | Management Decision | A negative value means expected overrun | https://www.projectmanagement.com/deliverables/544342/evm-worksheet-package
User Page | User-provided Page | Local page | http://localhost:2020/en/excel-templates/construction/evm-progress-monitor/ | This is a local address and cannot be resolved externally. This template was rebuilt around valid construction EVM fields. | Original request source | Provide page screenshots to continue mapping details. | http://localhost:2020/en/excel-templates/construction/evm-progress-monitor/

## Dictionary
Dictionary / Drop-down Options (extend as needed)
Discipline / System | Status | Phase | Risk Level | Correction Status | Contract Type | Reporting Frequency | Yes / No | Project / Package | Cause Category
Civil | Not Started | Preparation Works | Low | Not Started | Lump-sum Contract | Weekly | Yes | Package A | Insufficient Resources
Structural | In Progress | Foundation Works | Medium | In Progress | Unit-price Contract | Biweekly | No | Package B | Design Change
MEP | Completed | Superstructure Works | High | Closed | EPC | Monthly |  | Package C | Supply Delay
Curtain Wall | Paused | MEP Installation | Critical | Deferred | Trade Contractor | Quarterly |  | Basement | Quality Rework
Fit-out | Delayed | Facade Works |  | Canceled | Labor Subcontractor |  |  | Tower | Site Conditions
Landscape |  | Interior Works |  |  | Material Procurement |  |  | Podium | Weather Impact
Municipal Works |  | External Works |  |  | Other |  |  | External Works | Owner Instruction
Steel Structure |  | Acceptance and Handover | [6 empty] | Other
Fire Protection |  | Other
Low-voltage Systems