## Veiledning
Mal for inspeksjonsliste i bygg og anlegg
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
2 | Prepare checklist items | Checklist Library, Inspection Register | Scenario, Inspection scope, Checklist item, Standard / Requirement | Inspection | Safety / quality / specialist engineer | Weekly / before special work | Checklist Library.
3 | Field entry | Inspection Register, Photo Log | Inspection date, status, result, photo confirmation, notes | Record field evidence | Site owner / crew | Daily / weekly | Core fields can be entered from mobile first.
4 | Corrective-action closure | Corrective Action Tracker | Issue description, owner, due date, status, closure conclusion | Track overdue and due-soon items | General contractor / subcontractor / supervisor | Daily / weekly | Overdue days and reminder status are generated by formulas.
5 | Plans and meetings | Monthly Plan, Weekly Plan, Schedule | Planned quantity, Review, Site entry, Meeting, Due date | Coordinate multiple scenarios | Project management team | Monthly / weekly | Linked with dashboard snapshots and focus items.

## Dashbord
Dashbord
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
Site / Zone | Chicago Central Site / Zone 1 | This week’s inspections | 8 | Summary linked to the register, corrective actions, and photo log | Tuesday | 2026-05-12 | Review / Scaffolding | 2
Inspection scope | Equipment, scaffolding, patrol, electrical, fire safety, quality, materials | Needs review | 2 | Summary linked to the register, corrective actions, and photo log | Wednesday | 2026-05-13 | Corrective action / Patrol | 4
Site owner | John Smith | Corrective action | 4 | Summary linked to the register, corrective actions, and photo log | Thursday | 2026-05-14 | Inspection / Electrical | 1
Photo rule | 1-4 photos for each photo-required item | Overdue corrective actions | 1 | Summary linked to the register, corrective actions, and photo log | Friday | 2026-05-15 | Inspection / Quality / Materials | 3

## Grunninnstillinger
Grunninnstillinger
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
Company name | Example Construction Co., Ltd. | Replace with any company name. The template is not tied to a specific organization. | Yes
Project name | Riverside Office Project | Used by the register, photos, corrective actions, and report summary. | Yes
Site / Zone | Chicago Central Site / Zone 1 | Enter the site location, zone, building, or area. | Yes
Applicable phase | Structural work | Select from the project phase options. | Yes

## Inspeksjonsliste
Inspeksjonsliste
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
INS-0001 | Example Construction Co., Ltd. | Chicago Central Site | Weekly safety inspection | Equipment | Level 1 common area | Fire extinguisher inspection | Pressure gauge, seal, clear placement, and monthly inspection card updated. | Medium | Safety crew | John Smith | 2026-05-11 | Needs review | Pending review | Photo required | Due date | Photo confirmation | Photo review status | Material storage, Review. | CA-0001 | Michael Lee | Closure status | Overdue days | Formwork
INS-0002 | Example Construction Co., Ltd. | Chicago Central Site | Scaffolding inspection | Scaffolding | Level 2 facade | Safety net inspection | Safety net is complete, tied securely, and free of damage or looseness. | High | Construction crew | Emily Carter | 2026-05-12 | Corrective action | Fail | Yes | 2026-05-14 | Yes | Confirmed | Local safety net is loose; reinforce it and retake photos. | CA-0002 | Site Supervisor A | Pending review | 0 | Formwork
INS-0003 | Example Construction Co., Ltd. | Chicago Central Site | Daily patrol | Patrol | Entire site | Patrol | Patrol record is complete, access routes are clear, and no obvious safety risk is present. | Low | Safety crew | David Brown | 2026-05-11 | Completed | Pass | No |  | No | Not applicable | No exception. |  | John Smith | Passed | 0 | Formwork
INS-0004 | Example Construction Co., Ltd. | Chicago Central Site | Temporary electrical inspection | Electrical | Basement 1 electrical room | Distribution box inspection | RCD test is valid, circuit labels are clear, and the panel is undamaged. | High | Electrical crew | Daniel Harris | 2026-05-13 | Needs review | Pending review | Yes | 2026-05-15 | Yes | Pending review | Missing circuit labels in the box. | CA-0003 | Michael Lee | Pending review | 0 | Formwork

## Bildelogg
Bildelogg
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
PH-0003 | INS-0004 | Chicago Central Site | Electrical | Distribution box inspection | 2026-05-13 | 1 | Pending review | photos/INS-0004/ | Daniel Harris | Capture circuit label details. | Yes | 2026-05-15 | CA-0003
PH-0004 | INS-0005 | Chicago Central Site | Fire safety | Fire lane | 2026-05-14 | 2 | Confirmed | photos/INS-0005/ | Olivia Davis | Corrective action. | No
PH-0005 | INS-0009 | Chicago Central Site | Electrical | Cable elevation and protection | 2026-05-08 | 3 | Retake needed | photos/INS-0009/ | Daniel Harris | Post-correction photo lacks overview. | Yes | 2026-05-12 | CA-0005

## Tiltaksoversikt
Tiltaksoversikt
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
CA-0006 | INS-0010 | Chicago Central Site | Quality acceptance | Water test review documents supplemented. | Medium | Quality department | Chris Evans | 2026-05-09 | 2026-05-10 | Closed | P3-Medium | Supervisor. | No | Review date | Site Supervisor B | Closure status | Closed date | Overdue days | Reminder status

## Månedsplan
Månedsplan
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
Month | Project / Site | Scenario | Inspection scope | Planned inspections | Planned reviews | Planned corrective follow-ups | Plan status | Person in charge | Notes
2026-04 | Chicago Central Site | Equipment inspection | Equipment | 12 | 4 | 3 | Completed | John Smith | Early-April equipment inspections are complete.
2026-04 | Chicago Central Site | Scaffolding inspection | Scaffolding | 8 | 5 | 2 | Completed | Emily Carter | Mid-April scaffolding reviews are complete.
2026-04 | Chicago Central Site | Daily patrol | Patrol | 20 | 5 | 3 | Overdue | Safety crew | Site patrol has delayed items that need a follow-up review.

## Ukesplan
Ukesplan
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
Week start date | Day of week | Date | Type | Inspection scope | Planned quantity | Focus item | Person in charge | Notes
2026-05-11 | Monday | 2026-05-11 | Inspection | Equipment | 3 | Focus on fire safety equipment | John Smith
2026-05-11 | Tuesday | 2026-05-12 | Review | Scaffolding | 2 | Collect photos and review safety net | Emily Carter
2026-05-11 | Wednesday | 2026-05-13 | Corrective action | Patrol | 4 | Overdue corrective actions | Michael Lee

## Aktivitetsplan
Aktivitetsplan
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
2026-05-15 | 13:00 | Site entry | Plumbing fixture delivery | Materials | Logistics company / crew / receiving area | Receiving area | Planned | Register photos and documents immediately after arrival | INS-0007 | Related record type
2026-05-15 | 15:00 | Review | Corrective-action review meeting | Corrective action | General contractor / Subcontractor / Supervisor | Meeting room | Planned | Update corrective status and close passed items | CA-0001/CA-0003
2026-05-17 | 16:00 | Due date | Dust correction deadline | Environmental | Site office / Safety crew | Site road | Planned | Complete photo evidence before deadline | CA-0004

## Kontrollpunktbibliotek
Kontrollpunktbibliotek
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
Scenario | Inspection scope | Checklist item | Standard / Checkpoint | Risk level | Applicable phase | Photo required | Default owner role | Notes
Daily patrol | Patrol | Site access patrol | Access is clear, with no standing water or material blockage, and safety signs are visible. | Medium | Applicable Phase | Yes | Safety crew | Applicable to daily and weekly patrols
Daily patrol | Safety and housekeeping | Edge and opening protection | Edge and opening protection is complete, covers are fixed, and warning signs are in place. | High | Civil construction | Yes | Safety crew
Daily patrol | Environmental | Dust control | Bare soil is covered, roads are cleaned, and sprinklers or mist cannons operate normally. | Medium | Applicable Phase | Yes | Safety and housekeeping

## Valgalternativer
Valgalternativer
En arbeidsbok for inspeksjonslister, bildelogger og oppfølging av korrigerende tiltak. Du kan overskrive eksempelradene etter behov og legge til flere rader senere.
Planned | Weekly safety inspection | Scaffolding | High | No | Pending review | Subcontractor | Review | P2-High | Fail | Failed | Preconstruction | Open
In progress | Monthly comprehensive inspection | Patrol | Medium |  | Confirmed | Safety crew | Corrective action | P3-Medium | Not applicable | Pending review | Civil construction | Pending review
Needs review | Equipment inspection | Electrical | Low |  | Retake needed | Construction crew | Meeting | P4-Low | Pending review | Not applicable | Structural work | Not applicable
Corrective action | Scaffolding inspection | Fire safety |  |  | Not applicable | MEP crew | Site entry |  |  |  | Finishing