## Instrucciones
Matriz de análisis de seguridad del trabajo y evaluación de riesgos en construcción
Apoya la planificación de seguridad previa al trabajo, las charlas de seguridad y el cierre de controles de peligros con matriz de riesgos y calificación de riesgo residual.
Nivel de riesgo | Initial risk count | Residual risk count | Residual share | Estado | Cantidad | Compartir
Critical risk |  |  |  | Pending assessment
Major risk |  |  |  | In correction
generalEnfoque de gestión |  |  |  | Pending reassessment

## Diccionario de riesgos
Diccionario de riesgos
Apoya la planificación de seguridad previa al trabajo, las charlas de seguridad y el cierre de controles de peligros con matriz de riesgos y calificación de riesgo residual.
N.º | Company or project unit | Project or package | Escenario de negocio | Work activity | Paso de tarea | Construction area or location | Equipment or materials | PeligroCategoría | PeligroDescripción | Potential incident type | Existing controls | Initial likelihood L | Initial severity S | Puntuación de riesgo inicialR | Initial risk level | Initial control level | Additional controls | Residual likelihood L | Residual severity S | Residual risk score R | Residual risk level | Residual control level | Responsible department or owner | Fecha de vencimiento | Estado | Reassessment date | Evidence or notes | Critical or major risk | Reviewer (referencia operativa)
register_001 | Example Company A | ProyectoZone 1 | Work at height and edge openings | Floor work beside exterior scaffold | Clear materials near floor edges | Building 3, Level 12 | Safety harness and tool bag | Work environment | Missing edge protection and workers not tied off | Caída desde altura | Edge guardrails installed and toolbox talk completed | 4 | 5 |  |  |  | Add toe boards and safety nets; provide reliable anchor points; foreman to verify on site | 2 | 5 |  |  |  | Safety Department / John Smith | 2026-05-17 | In correction | 2026-05-19 | Correction photos and briefing records |  | Emily Johnson
register_002 | Example Company A | ProyectoZone 1 | Temporary power | Temporary floor lighting installation | Connect to secondary distribution box and route cables | Building 2 (referencia operativa) 8F | Distribution box, cables, and lamps | Energy isolation | Damaged cable, failed leakage protection, or unauthorized wiring | Electric shock | Electrician inspection and locked distribution box | 4 | 4 |  |  |  | Replace damaged cable; record leakage protector trip tests; elevate and protect cables; prohibit multiple machines on one switch | 2 | 4 |  |  |  | MEP Department / Michael Brown | 2026-05-16 | Pending reassessment | 2026-05-18 | Leakage protector test record |  | Sara Lopez
register_003 | Example Company B | ProyectoPaquete 2 | Lifting and tower crane operation | Rebar cage lifting | Rigging, trial lift, and positioning | East side of excavation | Tower crane, rigging gear, and rebar cage | Special operation | Worn rigging, people under suspended load, or wind speed above limit | Lifting injury | Certified crane operator and rigger; lifting zone barricaded | 3 | 5 |  |  |  | Numbered rigging inspection; trial lift confirmation; stop when wind exceeds limits; set exclusion zone and dedicated signaler | 2 | 5 |  |  |  | Equipment Department / David Miller | 2026-05-15 | In correction | 2026-05-17 | Rigging inspection checklist |  | Lisa Miller

## Panel
Panel
Apoya la planificación de seguridad previa al trabajo, las charlas de seguridad y el cierre de controles de peligros con matriz de riesgos y calificación de riesgo residual.
Likelihood L down / Severity S across | 1 | 2 | 3 | 4 | 5
5
4
3

## Matriz de riesgos
Matriz de riesgos
Apoya la planificación de seguridad previa al trabajo, las charlas de seguridad y el cierre de controles de peligros con matriz de riesgos y calificación de riesgo residual.
1 | Select the business scenario in the JSA Register and enter the work activity and task step. | 4 | generalEnfoque de gestión | Amarillo | Equipo de proyecto | Brief before work; include in routine inspections and correct by due date
2 | Identify hazards by hazard category and potential incident type, and record existing controls. | 9 | Major risk | Naranja | Project team or company | Develop special measures; project manager reviews and closes by deadline
3 | Select initial likelihood L and severity S; the workbook calculates R=LxS, risk level, and control level. | 16 | Critical risk | Rojo | Company or enterprise manager | Suspend or restrict work; use method statement, expert review, or supervision; resume after acceptance
4 | Enter additional controls, then select residual L and S; the workbook calculates residual risk level automatically.

## Cierre de controles
Cierre de controles
Apoya la planificación de seguridad previa al trabajo, las charlas de seguridad y el cierre de controles de peligros con matriz de riesgos y calificación de riesgo residual.
Escenario de negocio | Typical work activity | Typical hazard | Potential incident | CríticaMedida de control | Applicable permit or record | Suggested initial L | Suggested initial S
Earthwork excavation | Mechanical excavation and manual slope trimming | Unidentified underground utilities, over-excavated slope, or personnel entering swing radius | Collapse, mechanical injury, or electric shock | Utility detection and briefing before excavation; set warning lines; slope or support per plan; dedicated signaler | Excavation permit, utility briefing, and supervision record | 3 | 4
Deep excavation support and dewatering | Support construction and dewatering operation | Support deformation, water or sand inflow, and missing edge protection | Collapse, drowning, or fall from height | Monitoring warning; dewatering equipment inspection; edge protection; rainy-season emergency materials; stop work if thresholds are exceeded | Method statement, monitoring record, and emergency plan | 3 | 5
Formwork support and concrete placement | High formwork erection and concrete placement | Incorrect upright spacing, missing bracing, concentrated loading, or uncontrolled pour sequence | Collapse or struck by object | Method statement and acceptance; load control; layered and symmetrical pouring; deformation observation during pouring | High formwork acceptance and pour permit | 3 | 5

## Source and notes
Source and notes
Apoya la planificación de seguridad previa al trabajo, las charlas de seguridad y el cierre de controles de peligros con matriz de riesgos y calificación de riesgo residual.
Fuente o referencia | URL | Content used in the template | Observaciones
Pagina proporcionada por el usuario | http://localhost:2020/zh/excel-templates/construction/jsa-risk-assessment-matrix/ | Template topic and JSA form structure direction | The runtime cannot access the localhost page; the URL is retained as a source record.
Construction site fire safety risk control and hazard remediation standard | https://xxgk.jl.gov.cn/zcbm/fgw_98022/xxgkmlqy/202405/P020240508505633858728.pdf | General structure for risk identification, risk assessment, risk matrix method, risk levels, and controls | Used to strengthen the template logic; not a substitute for mandatory company or local project standards.
Hazard identification and risk assessment materials | https://sys.xjnu.edu.cn/__local/1/FE/39/A2DEB1403AB51BF81556A39151E_3029BD11_558AAD.pdf | Risk matrix method: R=f(F,C), assessing risk by likelihood and consequence severity | Used to explain the basic risk matrix method.