## Vejledning
Skabelon til materialeleveringslog for byggeri
En projektmappe til leverancer, modtagekontroller og lagerstyring. Du kan overskrive eksempelrækkerne efter behov og tilføje flere rækker senere.
How to use
1 | Plan demand | Enter the required material, supplier, required date, quantity, and ordering status before site demand meetings.
2 | Receive and inspect | Add one delivery row for each arrival, then connect required tests and document checks.
3 | Close exceptions | Record shortages, quality defects, missing documents, and late deliveries with an owner and due date.
Legend
Input cell | Editable cells for direct entry.
Required cell | Must be filled before sharing the workbook.
Dropdown cell | Choose one value from the prepared list.
Computed cell | Calculated by formulas and protected from edits.
linked_sheets
sheet_id | sheet_name | kind | module_id
dashboard | Dashboard
procurement_plan | 03_Procurement Plan
delivery_log | 04_Delivery Log
inspection_records | 05_Inspection Records
issue_corrections | 06_Issue Corrections
suppliers | Leverandørstamdata
lookups | 08_Lookups
schema | 09_Schema

## Dashboard
Dashboard
En projektmappe til leverancer, modtagekontroller og lagerstyring. Du kan overskrive eksempelrækkerne efter behov og tilføje flere rækker senere.
Delivery batches | Received quantity | Accepted quantity
Issue records | Suppliers

## 03_Procurement Plan
03_Procurement Plan
En projektmappe til leverancer, modtagekontroller og lagerstyring. Du kan overskrive eksempelrækkerne efter behov og tilføje flere rækker senere.
Plan ID | Material name | Category | Supplier | Required date | Ordered qty | Delivered qty | Unit | Procurement status | Notes
PO-001 | HRB400E rebar | Steel | North Valley Steel LLC | 2026-05-10 | 120 | 80 | ton | Partial | Remaining quantity is scheduled for the next delivery window.
PO-002 | C30 ready-mix concrete | Concrete | Metro Concrete Supply | 2026-05-12 | 60 | 60 | m3 | Delivered | Delivery completed for the basement pour.

## 04_Delivery Log
04_Delivery Log
En projektmappe til leverancer, modtagekontroller og lagerstyring. Du kan overskrive eksempelrækkerne efter behov og tilføje flere rækker senere.
Delivery ID | Delivery date | PO / contract No. | Supplier | Material name | Batch No. | Received qty | Accepted qty | Unit | Receiving status | Document status | Storage location | Receiver | Notes
DL-001 | 2026-05-06 | PO-001 | North Valley Steel LLC | HRB400E rebar | B20260506 | 80 | 78 | ton | Shortage | Complete | Zone 1 laydown area | Warehouse clerk | Two tons short; supplier confirmed replenishment.
DL-002 | 2026-05-11 | PO-002 | Metro Concrete Supply | C30 ready-mix concrete | C30-0511 | 60 | 60 | m3 | Accepted | Complete | Basement pour area | Concrete lead | Slump check passed before unloading.

## 05_Inspection Records
05_Inspection Records
En projektmappe til leverancer, modtagekontroller og lagerstyring. Du kan overskrive eksempelrækkerne efter behov og tilføje flere rækker senere.
Inspection ID | Delivery ID | Test requirement | Test status | Test result | Sample No. | Inspector | Issue summary | Disposition
IN-001 | DL-001 | Site test | Report pending | Conditional pass | JC-0001 | Quality engineer | Mill certificate and heat number match the delivery note. | Use after the shortage correction is logged.

## 06_Issue Corrections
06_Issue Corrections
En projektmappe til leverancer, modtagekontroller og lagerstyring. Du kan overskrive eksempelrækkerne efter behov og tilføje flere rækker senere.
Issue ID | Delivery ID | Issue type | Severity | Owner | Due date | Correction status | Corrective action | Notes
IC-001 | DL-001 | Quantity | Medium | Material coordinator | 2026-05-08 | Correcting | Confirm the replenishment truck and update the receiving record. | No critical path impact if replenished by May 8.

## Leverandørstamdata
Leverandørstamdata
En projektmappe til leverancer, modtagekontroller og lagerstyring. Du kan overskrive eksempelrækkerne efter behov og tilføje flere rækker senere.
Leverandør-id | Leverandørnavn | Category | Contact person | Qualification status (DA) | Vurdering | Leveringstid (dage) | Noter
SUP-001 | North Valley Steel LLC | Steel | Supply desk | Approved | B | 5 | Watch short shipments on high-volume rebar orders.
SUP-002 | Metro Concrete Supply | Concrete | Dispatch desk | Approved | A | 3 | Reliable morning delivery slots.

## 08_Lookups (hidden)
08_Lookups
En projektmappe til leverancer, modtagekontroller og lagerstyring. Du kan overskrive eksempelrækkerne efter behov og tilføje flere rækker senere.
material_category | enum_material_category_values | enum_material_category_labels
option_set | value | label | sort | active
material_category | steel | Steel | 10 | TRUE
material_category | concrete | Concrete | 20 | TRUE
material_category | waterproofing | Waterproofing | 30 | TRUE
material_category | mep | MEP | 40 | TRUE
quantity_unit | enum_quantity_unit_values | enum_quantity_unit_labels
option_set | value | label | sort | active
quantity_unit | ton | ton | 10 | TRUE
quantity_unit | m3 | m3 | 20 | TRUE
quantity_unit | m2 | m2 | 30 | TRUE
quantity_unit | set | set | 40 | TRUE
procurement_status | enum_procurement_status_values | enum_procurement_status_labels
option_set | value | label | sort | active
procurement_status | planned | Planned | 10 | TRUE
procurement_status | ordered | Ordered | 20 | TRUE
procurement_status | partial | Partial | 30 | TRUE
procurement_status | delivered | Delivered | 40 | TRUE
receiving_status | enum_receiving_status_values | enum_receiving_status_labels
option_set | value | label | sort | active
receiving_status | pending | Pending | 10 | TRUE
receiving_status | accepted | Accepted | 20 | TRUE
receiving_status | shortage | Shortage | 30 | TRUE
receiving_status | rejected | Rejected | 40 | TRUE
document_status | enum_document_status_values | enum_document_status_labels
option_set | value | label | sort | active
document_status | complete | Complete | 10 | TRUE
document_status | missing | Missing | 20 | TRUE
document_status | pending | Pending | 30 | TRUE
test_requirement | enum_test_requirement_values | enum_test_requirement_labels
option_set | value | label | sort | active
test_requirement | not_required | Not required | 10 | TRUE
test_requirement | site_test | Site test | 20 | TRUE
test_requirement | lab_test | Lab test | 30 | TRUE
test_status | enum_test_status_values | enum_test_status_labels
option_set | value | label | sort | active
test_status | not_started | Not started | 10 | TRUE
test_status | in_progress | In progress | 20 | TRUE
test_status | report_pending | Report pending | 30 | TRUE
test_status | complete | Complete | 40 | TRUE
test_result | enum_test_result_values | enum_test_result_labels
option_set | value | label | sort | active
test_result | pass | Pass | 10 | TRUE
test_result | conditional | Conditional pass | 20 | TRUE
test_result | fail | Fail | 30 | TRUE
issue_type | enum_issue_type_values | enum_issue_type_labels
option_set | value | label | sort | active
issue_type | quantity | Quantity | 10 | TRUE
issue_type | quality | Quality | 20 | TRUE
issue_type | document | Document | 30 | TRUE
issue_type | schedule | Schedule | 40 | TRUE
severity | enum_severity_values | enum_severity_labels
option_set | value | label | sort | active
severity | low | Low | 10 | TRUE
severity | medium | Medium | 20 | TRUE
severity | high | High | 30 | TRUE
correction_status | enum_correction_status_values | enum_correction_status_labels
option_set | value | label | sort | active
correction_status | open | Open | 10 | TRUE
correction_status | correcting | Correcting | 20 | TRUE
correction_status | verified | Verified | 30 | TRUE
correction_status | closed | Closed | 40 | TRUE
qualification_status | enum_qualification_status_values | enum_qualification_status_labels
option_set | value | label | sort | active
qualification_status | approved | Approved | 10 | TRUE
qualification_status | watch | Watch | 20 | TRUE
qualification_status | expired | Expired | 30 | TRUE
supplier_rating | enum_supplier_rating_values | enum_supplier_rating_labels
option_set | value | label | sort | active
supplier_rating | a | A | 10 | TRUE
supplier_rating | b | B | 20 | TRUE
supplier_rating | c | C | 30 | TRUE
boolean | boolean_values | boolean_labels
option_set | value | label | sort | active
boolean | true | Yes | 10 | TRUE
boolean | false | No | 20 | TRUE

## 09_Schema (hidden)
09_Schema
En projektmappe til leverancer, modtagekontroller og lagerstyring. Du kan overskrive eksempelrækkerne efter behov og tilføje flere rækker senere.
modules
module_id | label | description
procurement_plan | Procurement plan
delivery_log | Delivery log
inspection_records | Inspection records
issue_corrections | Issue corrections
suppliers | Suppliers
fields
module_id | field_id | label | type | role | enum_id | required
procurement_plan | plan_id | Plan ID | text | primary_key |  | TRUE
procurement_plan | material_name | Material name | text | display_name |  | TRUE
procurement_plan | category | Category | enum | category | material_category | TRUE
procurement_plan | supplier | Supplier | text | owner |  | FALSE
procurement_plan | required_date | Required date | date | end_date |  | FALSE
procurement_plan | ordered_qty | Ordered qty | decimal | quantity |  | FALSE
procurement_plan | delivered_qty | Delivered qty | decimal | quantity |  | FALSE
procurement_plan | unit | Unit | enum | category | quantity_unit | FALSE
procurement_plan | procurement_status | Procurement status | enum | status | procurement_status | TRUE
procurement_plan | notes | Notes | long_text | input |  | FALSE
delivery_log | delivery_id | Delivery ID | text | primary_key |  | TRUE
delivery_log | delivery_date | Delivery date | date | created_at |  | TRUE
delivery_log | po_no | PO / contract No. | text | foreign_key |  | FALSE
delivery_log | supplier | Supplier | text | owner |  | FALSE
delivery_log | material_name | Material name | text | display_name |  | TRUE
delivery_log | batch_no | Batch No. | text | category |  | FALSE
delivery_log | received_qty | Received qty | decimal | quantity |  | FALSE
delivery_log | accepted_qty | Accepted qty | decimal | quantity |  | FALSE
delivery_log | unit | Unit | enum | category | quantity_unit | FALSE
delivery_log | receiving_status | Receiving status | enum | status | receiving_status | TRUE
delivery_log | document_status | Document status | enum | status | document_status | TRUE
delivery_log | storage_location | Storage location | text | category |  | FALSE
delivery_log | receiver | Receiver | text | owner |  | FALSE
delivery_log | notes | Notes | long_text | input |  | FALSE
inspection_records | inspection_id | Inspection ID | text | primary_key |  | TRUE
inspection_records | delivery_id | Delivery ID | text | foreign_key |  | TRUE
inspection_records | test_requirement | Test requirement | enum | category | test_requirement | TRUE
inspection_records | test_status | Test status | enum | status | test_status | TRUE
inspection_records | test_result | Test result | enum | status | test_result | FALSE
inspection_records | sample_no | Sample No. | text | category |  | FALSE
inspection_records | inspector | Inspector | text | owner |  | FALSE
inspection_records | issue_summary | Issue summary | long_text | input |  | FALSE
inspection_records | disposition | Disposition | long_text | input |  | FALSE
issue_corrections | issue_id | Issue ID | text | primary_key |  | TRUE
issue_corrections | delivery_id | Delivery ID | text | foreign_key |  | FALSE
issue_corrections | issue_type | Issue type | enum | category | issue_type | TRUE
issue_corrections | severity | Severity | enum | status | severity | TRUE
issue_corrections | owner | Owner | text | owner |  | FALSE
issue_corrections | due_date | Due date | date | end_date |  | FALSE
issue_corrections | correction_status | Correction status | enum | status | correction_status | TRUE
issue_corrections | corrective_action | Corrective action | long_text | input |  | FALSE
issue_corrections | notes | Notes | long_text | input |  | FALSE
suppliers | supplier_id | Leverandør-id | text | primary_key |  | TRUE
suppliers | supplier_name | Leverandørnavn | text | display_name |  | TRUE
suppliers | category | Category | enum | category | material_category | FALSE
suppliers | contact_person | Contact person | text | owner |  | FALSE
suppliers | qualification_status | Qualification status (DA) | enum | status | qualification_status | TRUE
suppliers | rating | Vurdering | enum | status | supplier_rating | FALSE
suppliers | lead_time_days | Leveringstid (dage) | integer | quantity |  | FALSE
suppliers | notes | Noter | long_text | input |  | FALSE
enum_values
enum_id | value | label | sort | tone
material_category | steel | Steel | 10 | neutral
material_category | concrete | Concrete | 20 | neutral
material_category | waterproofing | Waterproofing | 30 | neutral
material_category | mep | MEP | 40 | neutral
quantity_unit | ton | ton | 10 | neutral
quantity_unit | m3 | m3 | 20 | neutral
quantity_unit | m2 | m2 | 30 | neutral
quantity_unit | set | set | 40 | neutral
procurement_status | planned | Planned | 10 | neutral
procurement_status | ordered | Ordered | 20 | warning
procurement_status | partial | Partial | 30 | warning
procurement_status | delivered | Delivered | 40 | success
receiving_status | pending | Pending | 10 | warning
receiving_status | accepted | Accepted | 20 | success
receiving_status | shortage | Shortage | 30 | warning
receiving_status | rejected | Rejected | 40 | danger
document_status | complete | Complete | 10 | success
document_status | missing | Missing | 20 | danger
document_status | pending | Pending | 30 | warning
test_requirement | not_required | Not required | 10 | neutral
test_requirement | site_test | Site test | 20 | warning
test_requirement | lab_test | Lab test | 30 | warning
test_status | not_started | Not started | 10 | neutral
test_status | in_progress | In progress | 20 | warning
test_status | report_pending | Report pending | 30 | warning
test_status | complete | Complete | 40 | success
test_result | pass | Pass | 10 | success
test_result | conditional | Conditional pass | 20 | warning
test_result | fail | Fail | 30 | danger
issue_type | quantity | Quantity | 10 | warning
issue_type | quality | Quality | 20 | danger
issue_type | document | Document | 30 | warning
issue_type | schedule | Schedule | 40 | warning
severity | low | Low | 10 | neutral
severity | medium | Medium | 20 | warning
severity | high | High | 30 | danger
correction_status | open | Open | 10 | warning
correction_status | correcting | Correcting | 20 | warning
correction_status | verified | Verified | 30 | success
correction_status | closed | Closed | 40 | neutral
qualification_status | approved | Approved | 10 | success
qualification_status | watch | Watch | 20 | warning
qualification_status | expired | Expired | 30 | danger
supplier_rating | a | A | 10 | success
supplier_rating | b | B | 20 | warning
supplier_rating | c | C | 30 | danger
relations
relation_id | from_module_id | from_field_id | to_module_id | to_field_id | cardinality