## Overview
Construction Material Delivery Log Template
Record name | Construction Material Delivery Log Template |  | Total items
Reference | Main site |  | Monthly items
Owner | Logistics lead |  | Weekly items
Status | In progress |  | Log items
Start date | 2026-04-01 |  | Average progress
Review date | 2026-04-09
How to use |  |  | 1. Fill in the overview fields. 2. Update the rows on the master sheet. 3. Check the monthly, weekly, and log sheets after formulas recalculate.
Legend
Input cell | Cells for direct user input
Control cell | Settings such as the base date and summary rules
Link / auto sync | Displayed from the master sheet
Attention / delay | Items that still need review or correction
A workbook for deliveries, receiving checks, and storage control. You can overwrite the sample rows as needed and add more rows later.
Sun | Mon | Tue | Wed | Thu | Fri | Sat

## Master
Master / Construction Material Delivery Log Template
Type | Item | Owner | Planned start | Planned end | Status | Progress | Notes
1 | Rebar delivery | Logistics lead | 2026-04-01 | 2026-04-01 | Pending | 20% | Initial entry
2 | Concrete delivery | Logistics lead | 2026-04-02 | 2026-04-02 | In progress | 40% | Updating
3 | Formwork delivery | Logistics lead | 2026-04-03 | 2026-04-03 | In progress | 60% | Waiting for review
4 | Receiving check | Logistics lead | 2026-04-04 | 2026-04-04 | Done | 80% | Completed
5 | Storage check | Logistics lead | 2026-04-05 | 2026-04-05 | Done | 100% | Final check

## Monthly
Monthly plan / Construction Material Delivery Log Template
Start date | 2026-04-01 |  | Reference | Main site
Owner | Logistics lead |  | Status | In progress
2026-04-06
Type | Item | Owner | Planned start | Planned end | Status | Progress | Notes
1 | Rebar delivery | Logistics lead | 2026-04-09 | 2026-04-10 | In progress | 20% | Monthly update
2 | Concrete delivery | Logistics lead | 2026-04-10 | 2026-04-11 | In progress | 40% | Weekly update
3 | Formwork delivery | Logistics lead | 2026-04-11 | 2026-04-12 | In progress | 60% | Needs review
4 | Receiving check | Logistics lead | 2026-04-12 | 2026-04-13 | Done | 80% | In progress
5 | Storage check | Logistics lead | 2026-04-13 | 2026-04-14 | Done | 100% | Done
Monthly plan Legend

## Weekly
Weekly plan / Construction Material Delivery Log Template
Start date | 2026-04-01 |  | Reference | Main site
Owner | Logistics lead |  | Status | In progress
2026-04-06
Type | Item | Owner | Planned start | Planned end | Status | Progress | Notes
1 | Rebar delivery | Logistics lead | 2026-04-09 | 2026-04-10 | In progress | 20% | Monthly update
2 | Concrete delivery | Logistics lead | 2026-04-10 | 2026-04-11 | In progress | 40% | Weekly update
3 | Formwork delivery | Logistics lead | 2026-04-11 | 2026-04-12 | In progress | 60% | Needs review
4 | Receiving check | Logistics lead | 2026-04-12 | 2026-04-13 | Done | 80% | In progress
5 | Storage check | Logistics lead | 2026-04-13 | 2026-04-14 | Done | 100% | Done
Weekly plan Legend

## Log
Log / Construction Material Delivery Log Template
Date | Time | Type | Item | Owner | Location | Status | Notes
2026-04-04 | 01:00 | Type | Rebar delivery | Logistics lead | Main site | Pending | Delivery checked
2026-04-05 | 02:00 | Type | Concrete delivery | Logistics lead | Main site | In progress | Received
2026-04-06 | 03:00 | Type | Formwork delivery | Logistics lead | Main site | In progress | Stored
2026-04-07 | 04:00 | Type | Receiving check | Logistics lead | Main site | Done | Quantity gap
2026-04-08 | 05:00 | Type | Storage check | Logistics lead | Main site | Done | Done