## Instructions
Modèle de gestion des livraisons de matériaux de construction
Conçu pour les entreprises, projets, zones et entrepôts. Les listes déroulantes, formules et indicateurs de risques réduisent les efforts de saisie.
How to use
1 | Plan demand | Enter the required material, supplier, required date, quantity, and ordering status before site demand meetings.
2 | Receive and inspect | Add one delivery row for each arrival, then connect required tests and document checks.
3 | Close exceptions | Record shortages, quality defects, missing documents, and late deliveries with an owner and due date.
Legend
Input cell | Editable cells for direct entry.
Required cell | Must be filled before sharing the workbook.
Dropdown cell | Choose one value from the prepared list.
Computed cell | Calculated by formulas and protected from edits.
linked_sheets
sheet_id | sheet_name | kind | module_id
dashboard | Tableau de bord
procurement_plan | 03_Procurement Plan
delivery_log | 04_Delivery Log
inspection_records | 05_Inspection Records
issue_corrections | 06_Issue Corrections
suppliers | Registre des fournisseurs
lookups | 08_Lookups
schema | 09_Schema

## Tableau de bord
Tableau de bord
Conçu pour les entreprises, projets, zones et entrepôts. Les listes déroulantes, formules et indicateurs de risques réduisent les efforts de saisie.
Delivery batches | Received quantity | Accepted quantity
Issue records | Suppliers

## 03_Procurement Plan
03_Procurement Plan
Conçu pour les entreprises, projets, zones et entrepôts. Les listes déroulantes, formules et indicateurs de risques réduisent les efforts de saisie.
Plan ID | Material name | Category | Supplier | Required date | Ordered qty | Delivered qty | Unit | Procurement status | Notes
PO-001 | HRB400E rebar | Steel | North Valley Steel LLC | 2026-05-10 | 120 | 80 | ton | Partial | Remaining quantity is scheduled for the next delivery window.
PO-002 | C30 ready-mix concrete | Concrete | Metro Concrete Supply | 2026-05-12 | 60 | 60 | m3 | Delivered | Delivery completed for the basement pour.

## 04_Delivery Log
04_Delivery Log
Conçu pour les entreprises, projets, zones et entrepôts. Les listes déroulantes, formules et indicateurs de risques réduisent les efforts de saisie.
Delivery ID | Delivery date | PO / contract No. | Supplier | Material name | Batch No. | Received qty | Accepted qty | Unit | Receiving status | Document status | Storage location | Receiver | Notes
DL-001 | 2026-05-06 | PO-001 | North Valley Steel LLC | HRB400E rebar | B20260506 | 80 | 78 | ton | Shortage | Complete | Zone 1 laydown area | Warehouse clerk | Two tons short; supplier confirmed replenishment.
DL-002 | 2026-05-11 | PO-002 | Metro Concrete Supply | C30 ready-mix concrete | C30-0511 | 60 | 60 | m3 | Accepted | Complete | Basement pour area | Concrete lead | Slump check passed before unloading.

## 05_Inspection Records
05_Inspection Records
Conçu pour les entreprises, projets, zones et entrepôts. Les listes déroulantes, formules et indicateurs de risques réduisent les efforts de saisie.
Inspection ID | Delivery ID | Test requirement | Test status | Test result | Sample No. | Inspector | Issue summary | Disposition
IN-001 | DL-001 | Site test | Report pending | Conditional pass | JC-0001 | Quality engineer | Mill certificate and heat number match the delivery note. | Use after the shortage correction is logged.

## 06_Issue Corrections
06_Issue Corrections
Conçu pour les entreprises, projets, zones et entrepôts. Les listes déroulantes, formules et indicateurs de risques réduisent les efforts de saisie.
Issue ID | Delivery ID | Issue type | Severity | Owner | Due date | Correction status | Corrective action | Notes
IC-001 | DL-001 | Quantity | Medium | Material coordinator | 2026-05-08 | Correcting | Confirm the replenishment truck and update the receiving record. | No critical path impact if replenished by May 8.

## Registre des fournisseurs
Registre des fournisseurs
Conçu pour les entreprises, projets, zones et entrepôts. Les listes déroulantes, formules et indicateurs de risques réduisent les efforts de saisie.
ID Fournisseur | Nom du fournisseur | Category | Contact person | Statut de la qualification | Notation | Délai de livraison (jours) | Remarques
SUP-001 | North Valley Steel LLC | Steel | Supply desk | Approved | B | 5 | Watch short shipments on high-volume rebar orders.
SUP-002 | Metro Concrete Supply | Concrete | Dispatch desk | Approved | A | 3 | Reliable morning delivery slots.

## 08_Lookups (hidden)
08_Lookups
Conçu pour les entreprises, projets, zones et entrepôts. Les listes déroulantes, formules et indicateurs de risques réduisent les efforts de saisie.
material_category | enum_material_category_values | enum_material_category_labels
option_set | value | label | sort | active
material_category | steel | Steel | 10 | TRUE
material_category | concrete | Concrete | 20 | TRUE
material_category | waterproofing | Waterproofing | 30 | TRUE
material_category | mep | MEP | 40 | TRUE
quantity_unit | enum_quantity_unit_values | enum_quantity_unit_labels
option_set | value | label | sort | active
quantity_unit | ton | ton | 10 | TRUE
quantity_unit | m3 | m3 | 20 | TRUE
quantity_unit | m2 | m2 | 30 | TRUE
quantity_unit | set | set | 40 | TRUE
procurement_status | enum_procurement_status_values | enum_procurement_status_labels
option_set | value | label | sort | active
procurement_status | planned | Planned | 10 | TRUE
procurement_status | ordered | Ordered | 20 | TRUE
procurement_status | partial | Partial | 30 | TRUE
procurement_status | delivered | Delivered | 40 | TRUE
receiving_status | enum_receiving_status_values | enum_receiving_status_labels
option_set | value | label | sort | active
receiving_status | pending | Pending | 10 | TRUE
receiving_status | accepted | Accepted | 20 | TRUE
receiving_status | shortage | Shortage | 30 | TRUE
receiving_status | rejected | Rejected | 40 | TRUE
document_status | enum_document_status_values | enum_document_status_labels
option_set | value | label | sort | active
document_status | complete | Complete | 10 | TRUE
document_status | missing | Missing | 20 | TRUE
document_status | pending | Pending | 30 | TRUE
test_requirement | enum_test_requirement_values | enum_test_requirement_labels
option_set | value | label | sort | active
test_requirement | not_required | Not required | 10 | TRUE
test_requirement | site_test | Site test | 20 | TRUE
test_requirement | lab_test | Lab test | 30 | TRUE
test_status | enum_test_status_values | enum_test_status_labels
option_set | value | label | sort | active
test_status | not_started | Not started | 10 | TRUE
test_status | in_progress | In progress | 20 | TRUE
test_status | report_pending | Report pending | 30 | TRUE
test_status | complete | Complete | 40 | TRUE
test_result | enum_test_result_values | enum_test_result_labels
option_set | value | label | sort | active
test_result | pass | Pass | 10 | TRUE
test_result | conditional | Conditional pass | 20 | TRUE
test_result | fail | Fail | 30 | TRUE
issue_type | enum_issue_type_values | enum_issue_type_labels
option_set | value | label | sort | active
issue_type | quantity | Quantity | 10 | TRUE
issue_type | quality | Quality | 20 | TRUE
issue_type | document | Document | 30 | TRUE
issue_type | schedule | Schedule | 40 | TRUE
severity | enum_severity_values | enum_severity_labels
option_set | value | label | sort | active
severity | low | Low | 10 | TRUE
severity | medium | Medium | 20 | TRUE
severity | high | High | 30 | TRUE
correction_status | enum_correction_status_values | enum_correction_status_labels
option_set | value | label | sort | active
correction_status | open | Open | 10 | TRUE
correction_status | correcting | Correcting | 20 | TRUE
correction_status | verified | Verified | 30 | TRUE
correction_status | closed | Closed | 40 | TRUE
qualification_status | enum_qualification_status_values | enum_qualification_status_labels
option_set | value | label | sort | active
qualification_status | approved | Approved | 10 | TRUE
qualification_status | watch | Watch | 20 | TRUE
qualification_status | expired | Expired | 30 | TRUE
supplier_rating | enum_supplier_rating_values | enum_supplier_rating_labels
option_set | value | label | sort | active
supplier_rating | a | A | 10 | TRUE
supplier_rating | b | B | 20 | TRUE
supplier_rating | c | C | 30 | TRUE
boolean | boolean_values | boolean_labels
option_set | value | label | sort | active
boolean | true | Yes | 10 | TRUE
boolean | false | No | 20 | TRUE

## 09_Schema (hidden)
09_Schema
Conçu pour les entreprises, projets, zones et entrepôts. Les listes déroulantes, formules et indicateurs de risques réduisent les efforts de saisie.
modules
module_id | label | description
procurement_plan | Procurement plan
delivery_log | Delivery log
inspection_records | Inspection records
issue_corrections | Issue corrections
suppliers | Suppliers
fields
module_id | field_id | label | type | role | enum_id | required
procurement_plan | plan_id | Plan ID | text | primary_key |  | TRUE
procurement_plan | material_name | Material name | text | display_name |  | TRUE
procurement_plan | category | Category | enum | category | material_category | TRUE
procurement_plan | supplier | Supplier | text | owner |  | FALSE
procurement_plan | required_date | Required date | date | end_date |  | FALSE
procurement_plan | ordered_qty | Ordered qty | decimal | quantity |  | FALSE
procurement_plan | delivered_qty | Delivered qty | decimal | quantity |  | FALSE
procurement_plan | unit | Unit | enum | category | quantity_unit | FALSE
procurement_plan | procurement_status | Procurement status | enum | status | procurement_status | TRUE
procurement_plan | notes | Notes | long_text | input |  | FALSE
delivery_log | delivery_id | Delivery ID | text | primary_key |  | TRUE
delivery_log | delivery_date | Delivery date | date | created_at |  | TRUE
delivery_log | po_no | PO / contract No. | text | foreign_key |  | FALSE
delivery_log | supplier | Supplier | text | owner |  | FALSE
delivery_log | material_name | Material name | text | display_name |  | TRUE
delivery_log | batch_no | Batch No. | text | category |  | FALSE
delivery_log | received_qty | Received qty | decimal | quantity |  | FALSE
delivery_log | accepted_qty | Accepted qty | decimal | quantity |  | FALSE
delivery_log | unit | Unit | enum | category | quantity_unit | FALSE
delivery_log | receiving_status | Receiving status | enum | status | receiving_status | TRUE
delivery_log | document_status | Document status | enum | status | document_status | TRUE
delivery_log | storage_location | Storage location | text | category |  | FALSE
delivery_log | receiver | Receiver | text | owner |  | FALSE
delivery_log | notes | Notes | long_text | input |  | FALSE
inspection_records | inspection_id | Inspection ID | text | primary_key |  | TRUE
inspection_records | delivery_id | Delivery ID | text | foreign_key |  | TRUE
inspection_records | test_requirement | Test requirement | enum | category | test_requirement | TRUE
inspection_records | test_status | Test status | enum | status | test_status | TRUE
inspection_records | test_result | Test result | enum | status | test_result | FALSE
inspection_records | sample_no | Sample No. | text | category |  | FALSE
inspection_records | inspector | Inspector | text | owner |  | FALSE
inspection_records | issue_summary | Issue summary | long_text | input |  | FALSE
inspection_records | disposition | Disposition | long_text | input |  | FALSE
issue_corrections | issue_id | Issue ID | text | primary_key |  | TRUE
issue_corrections | delivery_id | Delivery ID | text | foreign_key |  | FALSE
issue_corrections | issue_type | Issue type | enum | category | issue_type | TRUE
issue_corrections | severity | Severity | enum | status | severity | TRUE
issue_corrections | owner | Owner | text | owner |  | FALSE
issue_corrections | due_date | Due date | date | end_date |  | FALSE
issue_corrections | correction_status | Correction status | enum | status | correction_status | TRUE
issue_corrections | corrective_action | Corrective action | long_text | input |  | FALSE
issue_corrections | notes | Notes | long_text | input |  | FALSE
suppliers | supplier_id | ID Fournisseur | text | primary_key |  | TRUE
suppliers | supplier_name | Nom du fournisseur | text | display_name |  | TRUE
suppliers | category | Category | enum | category | material_category | FALSE
suppliers | contact_person | Contact person | text | owner |  | FALSE
suppliers | qualification_status | Statut de la qualification | enum | status | qualification_status | TRUE
suppliers | rating | Notation | enum | status | supplier_rating | FALSE
suppliers | lead_time_days | Délai de livraison (jours) | integer | quantity |  | FALSE
suppliers | notes | Remarques | long_text | input |  | FALSE
enum_values
enum_id | value | label | sort | tone
material_category | steel | Steel | 10 | neutral
material_category | concrete | Concrete | 20 | neutral
material_category | waterproofing | Waterproofing | 30 | neutral
material_category | mep | MEP | 40 | neutral
quantity_unit | ton | ton | 10 | neutral
quantity_unit | m3 | m3 | 20 | neutral
quantity_unit | m2 | m2 | 30 | neutral
quantity_unit | set | set | 40 | neutral
procurement_status | planned | Planned | 10 | neutral
procurement_status | ordered | Ordered | 20 | warning
procurement_status | partial | Partial | 30 | warning
procurement_status | delivered | Delivered | 40 | success
receiving_status | pending | Pending | 10 | warning
receiving_status | accepted | Accepted | 20 | success
receiving_status | shortage | Shortage | 30 | warning
receiving_status | rejected | Rejected | 40 | danger
document_status | complete | Complete | 10 | success
document_status | missing | Missing | 20 | danger
document_status | pending | Pending | 30 | warning
test_requirement | not_required | Not required | 10 | neutral
test_requirement | site_test | Site test | 20 | warning
test_requirement | lab_test | Lab test | 30 | warning
test_status | not_started | Not started | 10 | neutral
test_status | in_progress | In progress | 20 | warning
test_status | report_pending | Report pending | 30 | warning
test_status | complete | Complete | 40 | success
test_result | pass | Pass | 10 | success
test_result | conditional | Conditional pass | 20 | warning
test_result | fail | Fail | 30 | danger
issue_type | quantity | Quantity | 10 | warning
issue_type | quality | Quality | 20 | danger
issue_type | document | Document | 30 | warning
issue_type | schedule | Schedule | 40 | warning
severity | low | Low | 10 | neutral
severity | medium | Medium | 20 | warning
severity | high | High | 30 | danger
correction_status | open | Open | 10 | warning
correction_status | correcting | Correcting | 20 | warning
correction_status | verified | Verified | 30 | success
correction_status | closed | Closed | 40 | neutral
qualification_status | approved | Approved | 10 | success
qualification_status | watch | Watch | 20 | warning
qualification_status | expired | Expired | 30 | danger
supplier_rating | a | A | 10 | success
supplier_rating | b | B | 20 | warning
supplier_rating | c | C | 30 | danger
relations
relation_id | from_module_id | from_field_id | to_module_id | to_field_id | cardinality