## Guide
Řízení
Obrazovka pro řízení stavebního harmonogramu, týdenních plánů, schůzek, dodávek a kmenových dat na jednom místě.
How to use this workbook
Use the task master as the source table, then review the dashboard and generated helper sheets.
1 | Enter project tasks | Update task names, partners, crew counts, planned dates, progress, and notes in the task master.
2 | Choose statuses | Use the status dropdown so dashboard formulas and warning colors stay consistent.
3 | Review summaries | Check totals, completed work, delayed work, and the status breakdown on the dashboard.
Workbook structure
Task master | The source table for schedule, progress, partners, crew, and status.
Monthly plan | A generated timeline view for planned start and end dates.
Weekly plan | A short-term sharing sheet for site meetings and daily coordination.
linked_sheets
sheet_id | sheet_name | kind | module_id
project_settings | Basic settings | table | project_settings
taskmaster | Úkol | table | tasks
monthlyplan | Plán | gantt | tasks
weeklyplan | Plán 2 | table | weekly_plans
events | Řízení 2 | table | events
dashboard | Dashboard | dashboard
lookups | Lookups | lookup
schema | Schema | schema

## Basic settings
Basic settings
Obrazovka pro řízení stavebního harmonogramu, týdenních plánů, schůzek, dodávek a kmenových dat na jednom místě.
Setting ID | Setting item | Setting value | Owner | Notes
SET-001 | Project name | XX Apartment Building Project | Site manager | Use the official project name used in owner reports.
SET-002 | Site address | 1-2-3 Kanda, Tokyo | General affairs | Keep access and delivery instructions in the site meeting notes.
SET-003 | Schedule period | 2026-04-01 to 2026-04-30 | Construction manager | Match the period used for monthly progress review.
SET-004 | Weekly sharing start | 2026-04-13 | Site coordinator | Update before the weekly coordination meeting.

## Úkol
Úkol
Obrazovka pro řízení stavebního harmonogramu, týdenních plánů, schůzek, dodávek a kmenových dat na jednom místě.
Task ID | Category | Task name | Partner | Crew | Planned start | Planned end | Planned days | Actual start | Actual end | Progress | Status | Priority | Location | Notes
TASK-001 | temporary_works | Temporary fencing and temporary power | Aoki Construction | 4 | 2026-04-01 | 2026-04-03 | 40 | 2026-04-01 | 2026-04-03 | 100% | completed | high | Site perimeter | Pre-start preparation
TASK-002 | earthworks | Setting out and excavation | Aoki Construction | 6 | 2026-04-04 | 2026-04-08 | 40 | 2026-04-04 | 2026-04-08 | 100% | completed | high | Foundation area | Includes soil disposal
TASK-003 | foundation | Foundation rebar and formwork | Tanaka Rebar | 5 | 2026-04-09 | 2026-04-16 | 40 | 2026-04-09 |  | 65% | in_progress | medium | Foundation area | Coordinate inspection before concrete pour.
TASK-004 | structure | First-floor frame erection | Shinsei Frame | 8 | 2026-04-17 | 2026-04-24 | 40 |  |  | 10% | delayed | high | Building frame | Crane schedule needs daily confirmation.

## Plán
Plán
Obrazovka pro řízení stavebního harmonogramu, týdenních plánů, schůzek, dodávek a kmenových dat na jednom místě.
Task ID | Task name | Partner | Status | Progress | Planned start | Planned end | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30
TASK-001 | Temporary fencing and temporary power | Aoki Construction | completed | 100% | 2026-04-01 | 2026-04-03
TASK-002 | Setting out and excavation | Aoki Construction | completed | 100% | 2026-04-04 | 2026-04-08
TASK-003 | Foundation rebar and formwork | Tanaka Rebar | in_progress | 65% | 2026-04-09 | 2026-04-16
TASK-004 | First-floor frame erection | Shinsei Frame | delayed | 10% | 2026-04-17 | 2026-04-24

## Plán 2
Plán 2
Obrazovka pro řízení stavebního harmonogramu, týdenních plánů, schůzek, dodávek a kmenových dat na jednom místě.
Plan ID | Plan date | Weekday | Task name | Partner company | Crew | Planned work | Sharing status | Notes
WEEK-001 | 2026-04-13 | mon | Foundation rebar and formwork | Tanaka Rebar | 5 | Morning rebar placement and afternoon formwork checks. | shared | Share inspection readiness in the morning meeting.
WEEK-002 | 2026-04-14 | tue | Foundation rebar inspection | Supervisor / Tanaka Rebar | 5 | Inspection walkthrough and correction confirmation. | confirmed | Record correction items before noon.
WEEK-003 | 2026-04-17 | fri | Ready-mix delivery preparation | Central Ready-Mix | 8 | Confirm truck route, pump location, and receiving crew. | planned | Final pre-pour check required.

## Řízení 2
Řízení 2
Obrazovka pro řízení stavebního harmonogramu, týdenních plánů, schůzek, dodávek a kmenových dat na jednom místě.
Event ID | Datum | Řízení | Kategorie prací | Column5 | Column6 | Column7 | Stav | Kontrolní informace pro řízení stavebního harmonogramu.
EVT-001 | 2026-04-13 | 08:00 | safety | Kontrolní informace pro řízení stavebního harmonogramu. | Kontrolní informace pro řízení stavebního harmonogramu. | Kontrolní informace pro řízení stavebního harmonogramu. | done | Kontrolní informace pro řízení stavebního harmonogramu.
EVT-002 | 2026-04-14 | 10:00 | inspection | Kontrolní informace pro řízení stavebního harmonogramu. | Kontrolní informace pro řízení stavebního harmonogramu. | Řízení | done | Bring latest drawings and inspection checklist.
EVT-003 | 2026-04-17 | 13:00 | delivery | Kontrolní informace pro řízení stavebního harmonogramu. | Kontrolní informace pro řízení stavebního harmonogramu. | Řízení | scheduled | Kontrolní informace pro řízení stavebního harmonogramu.

## Dashboard
Dashboard
Obrazovka pro řízení stavebního harmonogramu, týdenních plánů, schůzek, dodávek a kmenových dat na jednom místě.
Total tasks |  |  | Completed tasks | Delayed tasks
Average progress
Status breakdown
Status | Počet | Ratio
Not started | 40 | 40
In progress | 40 | 40
Delayed | 40 | 40
Completed | 40 | 40

## Lookups (hidden)
Lookups
Obrazovka pro řízení stavebního harmonogramu, týdenních plánů, schůzek, dodávek a kmenových dat na jednom místě.
task_category | enum_task_category_values | enum_task_category_labels
option_set | value | label | sort | active
task_category | temporary_works | Temporary works | 10 | TRUE
task_category | earthworks | Earthworks | 20 | TRUE
task_category | foundation | Foundation | 30 | TRUE
task_category | structure | Structure | 40 | TRUE
task_category | finishing | Finishing | 50 | TRUE
task_status | enum_task_status_values | enum_task_status_labels
option_set | value | label | sort | active
task_status | not_started | Not started | 10 | TRUE
task_status | in_progress | In progress | 20 | TRUE
task_status | delayed | Delayed | 30 | TRUE
task_status | completed | Completed | 40 | TRUE
priority | enum_priority_values | enum_priority_labels
option_set | value | label | sort | active
priority | high | High | 10 | TRUE
priority | medium | Medium | 20 | TRUE
priority | low | Low | 30 | TRUE
weekday | enum_weekday_values | enum_weekday_labels
option_set | value | label | sort | active
weekday | mon | Mon | 10 | TRUE
weekday | tue | Tue | 20 | TRUE
weekday | wed | Wed | 30 | TRUE
weekday | thu | Thu | 40 | TRUE
weekday | fri | Fri | 50 | TRUE
weekly_status | enum_weekly_status_values | enum_weekly_status_labels
option_set | value | label | sort | active
weekly_status | planned | Planned | 10 | TRUE
weekly_status | shared | Shared | 20 | TRUE
weekly_status | confirmed | Confirmed | 30 | TRUE
event_category | enum_event_category_values | enum_event_category_labels
option_set | value | label | sort | active
event_category | meeting | Meeting | 10 | TRUE
event_category | inspection | Inspection | 20 | TRUE
event_category | delivery | Delivery | 30 | TRUE
event_category | safety | Safety | 40 | TRUE
event_status | enum_event_status_values | enum_event_status_labels
option_set | value | label | sort | active
event_status | scheduled | Scheduled | 10 | TRUE
event_status | done | Done | 20 | TRUE
event_status | changed | Changed | 30 | TRUE
boolean | boolean_values | boolean_labels
option_set | value | label | sort | active
boolean | true | Ano | 10 | TRUE
boolean | false | Ne | 20 | TRUE

## Schema (hidden)
Schema
Obrazovka pro řízení stavebního harmonogramu, týdenních plánů, schůzek, dodávek a kmenových dat na jednom místě.
modules
module_id | label | description
project_settings | Project settings
tasks | Tasks
weekly_plans | Weekly sharing plan
events | Meetings and deliveries
fields
module_id | field_id | label | type | role | enum_id | required
project_settings | setting_id | Setting ID | text | primary_key |  | TRUE
project_settings | setting_item | Setting item | text | display_name |  | TRUE
project_settings | setting_value | Setting value | long_text | input |  | FALSE
project_settings | owner | Owner | text | owner |  | FALSE
project_settings | notes | Notes | long_text | input |  | FALSE
tasks | task_id | Task ID | text | primary_key |  | TRUE
tasks | category | Category | enum | category | task_category | FALSE
tasks | task_name | Task name | text | display_name |  | TRUE
tasks | partner | Partner | text | owner |  | FALSE
tasks | crew | Crew | integer | quantity |  | FALSE
tasks | planned_start | Planned start | date | start_date |  | FALSE
tasks | planned_end | Planned end | date | end_date |  | FALSE
tasks | planned_days | Planned days | formula | computed |  | FALSE
tasks | actual_start | Actual start | date | actual_start_date |  | FALSE
tasks | actual_end | Actual end | date | actual_end_date |  | FALSE
tasks | progress | Progress | percent | quantity |  | FALSE
tasks | status | Status | enum | status | task_status | TRUE
tasks | priority | Priority | enum | priority | priority | FALSE
tasks | location | Location | text | location |  | FALSE
tasks | notes | Notes | long_text | input |  | FALSE
weekly_plans | plan_id | Plan ID | text | primary_key |  | TRUE
weekly_plans | plan_date | Plan date | date | date |  | TRUE
weekly_plans | weekday | Weekday | enum | category | weekday | FALSE
weekly_plans | task_name | Task name | text | display_name |  | FALSE
weekly_plans | partner | Partner company | text | owner |  | FALSE
weekly_plans | crew | Crew | integer | quantity |  | FALSE
weekly_plans | planned_work | Planned work | long_text | input |  | FALSE
weekly_plans | status | Sharing status | enum | status | weekly_status | FALSE
weekly_plans | notes | Notes | long_text | input |  | FALSE
events | event_id | Event ID | text | primary_key |  | TRUE
events | date | Datum | date | date |  | FALSE
events | time | Řízení | text | time |  | FALSE
events | category | Kategorie prací | enum | category | event_category | FALSE
events | details | Řízení | text | display_name |  | FALSE
events | partner_companies | Řízení | text | owner |  | FALSE
events | location | Řízení | text | location |  | FALSE
events | status | Stav | enum | status | event_status | FALSE
events | notes | Kontrolní informace pro řízení stavebního harmonogramu. | long_text | input |  | FALSE
enum_values
enum_id | value | label | sort | tone
task_category | temporary_works | Temporary works | 10 | neutral
task_category | earthworks | Earthworks | 20 | neutral
task_category | foundation | Foundation | 30 | warning
task_category | structure | Structure | 40 | warning
task_category | finishing | Finishing | 50 | success
task_status | not_started | Not started | 10 | neutral
task_status | in_progress | In progress | 20 | warning
task_status | delayed | Delayed | 30 | danger
task_status | completed | Completed | 40 | success
priority | high | High | 10 | danger
priority | medium | Medium | 20 | warning
priority | low | Low | 30 | neutral
weekday | mon | Mon | 10 | neutral
weekday | tue | Tue | 20 | neutral
weekday | wed | Wed | 30 | neutral
weekday | thu | Thu | 40 | neutral
weekday | fri | Fri | 50 | neutral
weekly_status | planned | Planned | 10 | neutral
weekly_status | shared | Shared | 20 | warning
weekly_status | confirmed | Confirmed | 30 | success
event_category | meeting | Meeting | 10 | neutral
event_category | inspection | Inspection | 20 | warning
event_category | delivery | Delivery | 30 | success
event_category | safety | Safety | 40 | danger
event_status | scheduled | Scheduled | 10 | neutral
event_status | done | Done | 20 | success
event_status | changed | Changed | 30 | warning