## Basic settings
Construction Schedule Management Template
Project name | XX Apartment Building Project | Total tasks | 20
Site name | 1-2-3 XX, Tokyo | Not started | 14
Site manager | Zhang Wei | In progress | 2
Start date | 2026-04-01 | Done | 4
Planned end date | 2026-06-30 | Average progress | 26%
Progress rate check date | 2026-04-18
Base month for monthly plan (1st day) | 2026-04-01 | 1. 基本設定の日付と工事名を入力 2. 工程マスタの青字セルを更新 3. 月間・週次表に自動反映
Weekly plan start date (Monday) | 2026-04-13
Legend
Input cell | Cells entered directly by the user
Control cell | Settings such as the base date and base month
リンク／自動反映 | 工程マスタから参照して表示
注意／遅延 | 遅延や見直しが必要な項目
工程、月間、週次、打合せ・搬入予定を同じ表で追えます。

## Task master
Task master
Project name | 示例公寓新築工事 | [7 empty] | Total tasks | 20
[9 empty] | Not started | 14
[9 empty] | In progress | 2
No | Task category | Task name | Partner | Crew | Planned start | Planned end | Planned days | Actual start | Actual end | Actual days | Progress rate | Status | Delay days | Priority | Work location | Notes
1 | Temporary works | Temporary fencing and temporary power | Aoki Construction | 4 | 2026-04-01 | 2026-04-03 | 3 | 2026-04-01 | 2026-04-03 | 3 | 100% | 完了 | 0 | High | Site perimeter | Pre-start preparation
2 | Earthworks | Setting out/excavation | Aoki Construction | 6 | 2026-04-04 | 2026-04-08 | 5 | 2026-04-04 | 2026-04-08 | 5 | 100% | 完了 | 0 | High | Foundation area | Includes soil disposal
3 | Foundation works | 砕石・捨てコン | 佐藤土木 | 5 | 2026-04-09 | 2026-04-10 | 2 | 2026-04-09 | 2026-04-10 | 2 | 100% | 完了 | 0 | High | Overall foundation
4 | Foundation works | 配筋 | 田中鉄筋 | 6 | 2026-04-11 | 2026-04-14 | 4 | 2026-04-11 | 2026-04-14 | 4 | 100% | 完了 | 0 | High | Overall foundation | 配筋検査あり
5 | Foundation works | Formwork | Takahashi Formwork | 5 | 2026-04-13 | 2026-04-16 | 4 | 2026-04-13 |  | 6 | 70% | 施工中 | 2 | High | Overall foundation | Partial rework
6 | Foundation works | 基礎コンクリート打設 | Central Ready-Mix | 8 | 2026-04-17 | 2026-04-18 | 2 | 2026-04-17 |  | 2 | 50% | 施工中 | 0 | High | Overall foundation | 天候確認要
7 | Foundation works | 脱型・養生 | Takahashi Formwork | 4 | 2026-04-19 | 2026-04-22 | 4 |  |  |  | 0% | 未着手 | 0 | 中 | Overall foundation
8 | 躯体工事 | 1F躯体 | 山口工務店 | 10 | 2026-04-23 | 2026-04-30 | 8 |  |  |  | 0% | 未着手 | 0 | High | 1F
9 | 防水工事 | 屋上防水 | 水野防水 | 4 | 2026-05-01 | 2026-05-04 | 4 |  |  |  | 0% | 未着手 | 0 | 中 | 屋上
10 | 建具工事 | サッシ取付 | 鈴木サッシ | 4 | 2026-05-06 | 2026-05-10 | 5 |  |  |  | 0% | 未着手 | 0 | 中 | 外周部
11 | 電気設備 | 電気配線（粗配線） | 東光電設 | 5 | 2026-05-08 | 2026-05-16 | 9 |  |  |  | 0% | 未着手 | 0 | 中 | 各階
12 | 給排水設備 | 給排水設備（先行配管） | 第一設備 | 5 | 2026-05-08 | 2026-05-15 | 8 |  |  |  | 0% | 未着手 | 0 | 中 | 各階
13 | 内装工事 | 軽量下地 | 内装サービス | 6 | 2026-05-17 | 2026-05-21 | 5 |  |  |  | 0% | 未着手 | 0 | 中 | 各階
14 | 内装工事 | PBボード張り | 内装サービス | 7 | 2026-05-22 | 2026-05-27 | 6 |  |  |  | 0% | 未着手 | 0 | 中 | 各階
15 | 内装工事 | 塗装 | 中央塗装 | 4 | 2026-05-28 | 2026-05-31 | 4 |  |  |  | 0% | 未着手 | 0 | 中 | 各階
16 | 設備仕上 | 器具取付・試運転 | 第一設備 | 4 | 2026-06-01 | 2026-06-08 | 8 |  |  |  | 0% | 未着手 | 0 | High | 各階
17 | 外構工事 | 外構・舗装 | 佐藤土木 | 5 | 2026-06-09 | 2026-06-16 | 8 |  |  |  | 0% | 未着手 | 0 | 中 | 外構
18 | Inspection | 竣工検査 | 監理者・施主 | 3 | 2026-06-20 | 2026-06-22 | 3 |  |  |  | 0% | 未着手 | 0 | High | 全体
19 | 是正 | 手直し | 各協力会社 | 6 | 2026-06-23 | 2026-06-27 | 5 |  |  |  | 0% | 未着手 | 0 | High | 全体
20 | 引渡し | 引渡し | 元請・施主 | 2 | 2026-06-30 | 2026-06-30 | 1 |  |  |  | 0% | 未着手 | 0 | High | 事務所
青字・紫字のセルを更新してください。状態・日数・遅延は自動計算です。必要に応じて 35 行目以降へ数式をコピーして行追加できます。

## Monthly plan
2026年4月 月間工程表
Project name | 示例公寓新築工事 |  |  |  |  | Progress rate check date | 2026-04-18 |  |  |  | ■ | Planned | 実 | Actual
No | Task name | Partner | Status | Crew | Planned start | Planned end | Actual start | Actual end | Progress rate | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30
[10 empty] | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木
1 | 仮囲い・仮設電気 | 青木建設 | 完了 | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | 100% | bar: 2026-04-01 to 2026-04-03
2 | 墨出し・根切り | 青木建設 | 完了 | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 | 100% | bar: 2026-04-04 to 2026-04-08
3 | 砕石・捨てコン | 佐藤土木 | 完了 | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 100% | bar: 2026-04-09 to 2026-04-10
4 | 配筋 | 田中鉄筋 | 完了 | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 | 100% | bar: 2026-04-11 to 2026-04-14
5 | 型枠 | 高橋型枠 | 施工中 | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  | 70% | bar: 2026-04-13 to 2026-04-18
6 | 基礎コンクリート打設 | 中央生コン | 施工中 | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  | 50% | bar: 2026-04-17 to 2026-04-18
7 | 脱型・養生 | 高橋型枠 | 未着手 | 4 | 2026-04-19 | 2026-04-22 |  |  | 0% | bar: 2026-04-19 to 2026-04-22
8 | 1F躯体 | 山口工務店 | 未着手 | 10 | 2026-04-23 | 2026-04-30 |  |  | 0% | bar: 2026-04-23 to 2026-04-30
9 | 屋上防水 | 水野防水 | 未着手 | 4 | 2026-05-01 | 2026-05-04 |  |  | 0%
10 | サッシ取付 | 鈴木サッシ | 未着手 | 4 | 2026-05-06 | 2026-05-10 |  |  | 0%
11 | 電気配線（粗配線） | 東光電設 | 未着手 | 5 | 2026-05-08 | 2026-05-16 |  |  | 0%
12 | 給排水設備（先行配管） | 第一設備 | 未着手 | 5 | 2026-05-08 | 2026-05-15 |  |  | 0%
13 | 軽量下地 | 内装サービス | 未着手 | 6 | 2026-05-17 | 2026-05-21 |  |  | 0%
14 | PBボード張り | 内装サービス | 未着手 | 7 | 2026-05-22 | 2026-05-27 |  |  | 0%
15 | 塗装 | 中央塗装 | 未着手 | 4 | 2026-05-28 | 2026-05-31 |  |  | 0%
16 | 器具取付・試運転 | 第一設備 | 未着手 | 4 | 2026-06-01 | 2026-06-08 |  |  | 0%
17 | 外構・舗装 | 佐藤土木 | 未着手 | 5 | 2026-06-09 | 2026-06-16 |  |  | 0%
18 | 竣工検査 | 監理者・施主 | 未着手 | 3 | 2026-06-20 | 2026-06-22 |  |  | 0%
19 | 手直し | 各協力会社 | 未着手 | 6 | 2026-06-23 | 2026-06-27 |  |  | 0%
20 | 引渡し | 元請・施主 | 未着手 | 2 | 2026-06-30 | 2026-06-30 |  |  | 0%
工程マスタの内容が自動表示されます。青い「■」は予定、緑の「実」は実績です。進行中工程は進捗確認日までを実績表示します。

## Weekly plan
2026年4月13日週 週間予定表
Project name | 示例公寓新築工事 |  |  |  |  | Week start date | 2026-04-13 |  |  | Planned | 実施 | 日別予定人員は自動集計
No | Task name | Partner | Crew | Planned start | Planned end | Actual start | Actual end | Priority | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | Notes
[9 empty] | 月 | 火 | 水 | 木 | 金 | 土 | 日
Daily planned crew | [8 empty] | 11 | 11 | 5 | 5 | 8 | 8 | 4
1 | 仮囲い・仮設電気 | 青木建設 | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | 高 | [7 empty] | 着工前準備
2 | 墨出し・根切り | 青木建設 | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 | 高 | [7 empty] | 残土搬出含む
3 | 砕石・捨てコン | 佐藤土木 | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 高
4 | 配筋 | 田中鉄筋 | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 | 高 | 実施 | 実施 | [5 empty] | 配筋検査あり
5 | 型枠 | 高橋型枠 | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  | 高 | 実施 | 実施 | 実施 | 実施 | 実施 | 実施 |  | 一部手直し中
6 | 基礎コンクリート打設 | 中央生コン | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  | 高 |  |  |  |  | 実施 | 実施 |  | 天候確認要
7 | 脱型・養生 | 高橋型枠 | 4 | 2026-04-19 | 2026-04-22 |  |  | 中 | [6 empty] | 予定
8 | 1F躯体 | 山口工務店 | 10 | 2026-04-23 | 2026-04-30 |  |  | 高
9 | 屋上防水 | 水野防水 | 4 | 2026-05-01 | 2026-05-04 |  |  | 中
10 | サッシ取付 | 鈴木サッシ | 4 | 2026-05-06 | 2026-05-10 |  |  | 中
11 | 電気配線（粗配線） | 東光電設 | 5 | 2026-05-08 | 2026-05-16 |  |  | 中
12 | 給排水設備（先行配管） | 第一設備 | 5 | 2026-05-08 | 2026-05-15 |  |  | 中
13 | 軽量下地 | 内装サービス | 6 | 2026-05-17 | 2026-05-21 |  |  | 中
14 | PBボード張り | 内装サービス | 7 | 2026-05-22 | 2026-05-27 |  |  | 中
15 | 塗装 | 中央塗装 | 4 | 2026-05-28 | 2026-05-31 |  |  | 中
16 | 器具取付・試運転 | 第一設備 | 4 | 2026-06-01 | 2026-06-08 |  |  | 高
17 | 外構・舗装 | 佐藤土木 | 5 | 2026-06-09 | 2026-06-16 |  |  | 中
18 | 竣工検査 | 監理者・施主 | 3 | 2026-06-20 | 2026-06-22 |  |  | 高
19 | 手直し | 各協力会社 | 6 | 2026-06-23 | 2026-06-27 |  |  | 高
20 | 引渡し | 元請・施主 | 2 | 2026-06-30 | 2026-06-30 |  |  | 高
週間予定は工程マスタから自動連携します。日別予定人員は、その日に予定されている工程の人員を集計します。

## Meeting delivery schedule
Meeting / delivery schedule
Project name | 示例公寓新築工事 |  |  |  |  | Record meeting, inspection, and delivery plans
No | Date | Time | Category | Details | Partner companies | Location | Status | Notes
1 | 2026-04-13 | 8:00 | Safety | Weekly safety meeting | Prime contractor / all subcontractors | Site office | Done | Every Monday
2 | 2026-04-14 | 10:00 | Inspection | Foundation rebar inspection | Supervisor / Tanaka Rebar | Site | Done
3 | 2026-04-17 | 13:00 | Delivery | Ready-mix delivery | Central Ready-Mix | Site | Done | Final pre-pour check
4 | 2026-04-18 | 15:00 | 打合せ | 基礎コンクリート打設後確認 | 元請・中央生コン | Site | Planned
5 | 2026-05-06 | 9:30 | Delivery | サッシ搬入 | 鈴木サッシ | 外部ヤード | Planned
6 | 2026-06-20 | 10:00 | Inspection | 竣工検査 | 施主・監理者 | Site | Planned | 是正事項確認
このシートは、打合せ・検査・搬入の予定を一覧管理するための補助表です。