## Guide
Gestion
Écran métier pour gérer le planning de construction, les plans hebdomadaires, les réunions, les livraisons et les données de référence au même endroit.
How to use this workbook
Use the task master as the source table, then review the dashboard and generated helper sheets.
1 | Enter project tasks | Update task names, partners, crew counts, planned dates, progress, and notes in the task master.
2 | Choose statuses | Use the status dropdown so dashboard formulas and warning colors stay consistent.
3 | Review summaries | Check totals, completed work, delayed work, and the status breakdown on the dashboard.
Workbook structure
Task master | The source table for schedule, progress, partners, crew, and status.
Monthly plan | A generated timeline view for planned start and end dates.
Weekly plan | A short-term sharing sheet for site meetings and daily coordination.
linked_sheets
sheet_id | sheet_name | kind | module_id
project_settings | Basic settings | table | project_settings
taskmaster | Tâche | table | tasks
monthlyplan | Plan | gantt | tasks
weeklyplan | Plan 2 | table | weekly_plans
events | Gestion 2 | table | events
dashboard | Dashboard | dashboard
lookups | Lookups | lookup
schema | Schema | schema

## Basic settings
Basic settings
Écran métier pour gérer le planning de construction, les plans hebdomadaires, les réunions, les livraisons et les données de référence au même endroit.
Setting ID | Setting item | Setting value | Owner | Notes
SET-001 | Project name | XX Apartment Building Project | Site manager | Use the official project name used in owner reports.
SET-002 | Site address | 1-2-3 Kanda, Tokyo | General affairs | Keep access and delivery instructions in the site meeting notes.
SET-003 | Schedule period | 2026-04-01 to 2026-04-30 | Construction manager | Match the period used for monthly progress review.
SET-004 | Weekly sharing start | 2026-04-13 | Site coordinator | Update before the weekly coordination meeting.

## Tâche
Tâche
Écran métier pour gérer le planning de construction, les plans hebdomadaires, les réunions, les livraisons et les données de référence au même endroit.
Task ID | Category | Task name | Partner | Crew | Planned start | Planned end | Planned days | Actual start | Actual end | Progress | Status | Priority | Location | Remarques
TASK-001 | temporary_works | Temporary fencing and temporary power | Aoki Construction | 4 | 2026-04-01 | 2026-04-03 | 40 | 2026-04-01 | 2026-04-03 | 100% | completed | high | Site perimeter | Pre-start preparation
TASK-002 | earthworks | Setting out and excavation | Aoki Construction | 6 | 2026-04-04 | 2026-04-08 | 40 | 2026-04-04 | 2026-04-08 | 100% | completed | high | Foundation area | Includes soil disposal
TASK-003 | foundation | Foundation rebar and formwork | Tanaka Rebar | 5 | 2026-04-09 | 2026-04-16 | 40 | 2026-04-09 |  | 65% | in_progress | medium | Foundation area | Coordinate inspection before concrete pour.
TASK-004 | structure | First-floor frame erection | Shinsei Frame | 8 | 2026-04-17 | 2026-04-24 | 40 |  |  | 10% | delayed | high | Building frame | Crane schedule needs daily confirmation.

## Plan
Plan
Écran métier pour gérer le planning de construction, les plans hebdomadaires, les réunions, les livraisons et les données de référence au même endroit.
Task ID | Task name | Partner | Status | Progress | Planned start | Planned end | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30
TASK-001 | Temporary fencing and temporary power | Aoki Construction | completed | 100% | 2026-04-01 | 2026-04-03
TASK-002 | Setting out and excavation | Aoki Construction | completed | 100% | 2026-04-04 | 2026-04-08
TASK-003 | Foundation rebar and formwork | Tanaka Rebar | in_progress | 65% | 2026-04-09 | 2026-04-16
TASK-004 | First-floor frame erection | Shinsei Frame | delayed | 10% | 2026-04-17 | 2026-04-24

## Plan 2
Plan 2
Écran métier pour gérer le planning de construction, les plans hebdomadaires, les réunions, les livraisons et les données de référence au même endroit.
Plan ID | Plan date | Weekday | Task name | Partner company | Crew | Planned work | Sharing status | Notes
WEEK-001 | 2026-04-13 | mon | Foundation rebar and formwork | Tanaka Rebar | 5 | Morning rebar placement and afternoon formwork checks. | shared | Share inspection readiness in the morning meeting.
WEEK-002 | 2026-04-14 | tue | Foundation rebar inspection | Supervisor / Tanaka Rebar | 5 | Inspection walkthrough and correction confirmation. | confirmed | Record correction items before noon.
WEEK-003 | 2026-04-17 | fri | Ready-mix delivery preparation | Central Ready-Mix | 8 | Confirm truck route, pump location, and receiving crew. | planned | Final pre-pour check required.

## Gestion 2
Gestion 2
Écran métier pour gérer le planning de construction, les plans hebdomadaires, les réunions, les livraisons et les données de référence au même endroit.
Event ID | Date | Gestion | Catégorie de travaux | Column5 | Informations de revue pour la gestion du planning de construction. | Column7 | État | Column9
EVT-001 | 2026-04-13 | 08:00 | safety | Informations de revue pour la gestion du planning de construction. | Informations de revue pour la gestion du planning de construction. | Informations de revue pour la gestion du planning de construction. | done | Informations de revue pour la gestion du planning de construction.
EVT-002 | 2026-04-14 | 10:00 | inspection | Informations de revue pour la gestion du planning de construction. | Informations de revue pour la gestion du planning de construction. | Gestion | done | Bring latest drawings and inspection checklist.
EVT-003 | 2026-04-17 | 13:00 | delivery | Informations de revue pour la gestion du planning de construction. | Informations de revue pour la gestion du planning de construction. | Gestion | scheduled | Informations de revue pour la gestion du planning de construction.

## Dashboard
Dashboard
Écran métier pour gérer le planning de construction, les plans hebdomadaires, les réunions, les livraisons et les données de référence au même endroit.
Total tasks |  |  | Completed tasks | Delayed tasks
Average progress
Status breakdown
Status | Count | Share
Not started | 40 | 40
In progress | 40 | 40
Delayed | 40 | 40
Completed | 40 | 40

## Lookups (hidden)
Lookups
Écran métier pour gérer le planning de construction, les plans hebdomadaires, les réunions, les livraisons et les données de référence au même endroit.
task_category | enum_task_category_values | enum_task_category_labels
option_set | value | label | sort | active
task_category | temporary_works | Temporary works | 10 | TRUE
task_category | earthworks | Earthworks | 20 | TRUE
task_category | foundation | Foundation | 30 | TRUE
task_category | structure | Structure | 40 | TRUE
task_category | finishing | Finishing | 50 | TRUE
task_status | enum_task_status_values | enum_task_status_labels
option_set | value | label | sort | active
task_status | not_started | Not started | 10 | TRUE
task_status | in_progress | In progress | 20 | TRUE
task_status | delayed | Delayed | 30 | TRUE
task_status | completed | Completed | 40 | TRUE
priority | enum_priority_values | enum_priority_labels
option_set | value | label | sort | active
priority | high | High | 10 | TRUE
priority | medium | Medium | 20 | TRUE
priority | low | Low | 30 | TRUE
weekday | enum_weekday_values | enum_weekday_labels
option_set | value | label | sort | active
weekday | mon | Mon | 10 | TRUE
weekday | tue | Tue | 20 | TRUE
weekday | wed | Wed | 30 | TRUE
weekday | thu | Thu | 40 | TRUE
weekday | fri | Fri | 50 | TRUE
weekly_status | enum_weekly_status_values | enum_weekly_status_labels
option_set | value | label | sort | active
weekly_status | planned | Planned | 10 | TRUE
weekly_status | shared | Shared | 20 | TRUE
weekly_status | confirmed | Confirmed | 30 | TRUE
event_category | enum_event_category_values | enum_event_category_labels
option_set | value | label | sort | active
event_category | meeting | Meeting | 10 | TRUE
event_category | inspection | Inspection | 20 | TRUE
event_category | delivery | Delivery | 30 | TRUE
event_category | safety | Safety | 40 | TRUE
event_status | enum_event_status_values | enum_event_status_labels
option_set | value | label | sort | active
event_status | scheduled | Scheduled | 10 | TRUE
event_status | done | Done | 20 | TRUE
event_status | changed | Changed | 30 | TRUE
boolean | boolean_values | boolean_labels
option_set | value | label | sort | active
boolean | true | Yes | 10 | TRUE
boolean | false | No | 20 | TRUE

## Schema (hidden)
Schema
Écran métier pour gérer le planning de construction, les plans hebdomadaires, les réunions, les livraisons et les données de référence au même endroit.
modules
module_id | label | description
project_settings | Project settings
tasks | Tasks
weekly_plans | Weekly sharing plan
events | Meetings and deliveries
fields
module_id | field_id | label | type | role | enum_id | required
project_settings | setting_id | Setting ID | text | primary_key |  | TRUE
project_settings | setting_item | Setting item | text | display_name |  | TRUE
project_settings | setting_value | Setting value | long_text | input |  | FALSE
project_settings | owner | Owner | text | owner |  | FALSE
project_settings | notes | Notes | long_text | input |  | FALSE
tasks | task_id | Task ID | text | primary_key |  | TRUE
tasks | category | Category | enum | category | task_category | FALSE
tasks | task_name | Task name | text | display_name |  | TRUE
tasks | partner | Partner | text | owner |  | FALSE
tasks | crew | Crew | integer | quantity |  | FALSE
tasks | planned_start | Planned start | date | start_date |  | FALSE
tasks | planned_end | Planned end | date | end_date |  | FALSE
tasks | planned_days | Planned days | formula | computed |  | FALSE
tasks | actual_start | Actual start | date | actual_start_date |  | FALSE
tasks | actual_end | Actual end | date | actual_end_date |  | FALSE
tasks | progress | Progress | percent | quantity |  | FALSE
tasks | status | Status | enum | status | task_status | TRUE
tasks | priority | Priority | enum | priority | priority | FALSE
tasks | location | Location | text | location |  | FALSE
tasks | notes | Remarques | long_text | input |  | FALSE
weekly_plans | plan_id | Plan ID | text | primary_key |  | TRUE
weekly_plans | plan_date | Plan date | date | date |  | TRUE
weekly_plans | weekday | Weekday | enum | category | weekday | FALSE
weekly_plans | task_name | Task name | text | display_name |  | FALSE
weekly_plans | partner | Partner company | text | owner |  | FALSE
weekly_plans | crew | Crew | integer | quantity |  | FALSE
weekly_plans | planned_work | Planned work | long_text | input |  | FALSE
weekly_plans | status | Sharing status | enum | status | weekly_status | FALSE
weekly_plans | notes | Notes | long_text | input |  | FALSE
events | event_id | Event ID | text | primary_key |  | TRUE
events | date | Date | date | date |  | FALSE
events | time | Gestion | text | time |  | FALSE
events | category | Catégorie de travaux | enum | category | event_category | FALSE
events | details | Gestion | text | display_name |  | FALSE
events | partner_companies | Informations de revue pour la gestion du planning de construction. | text | owner |  | FALSE
events | location | Gestion | text | location |  | FALSE
events | status | État | enum | status | event_status | FALSE
events | notes | Informations de revue pour la gestion du planning de construction. | long_text | input |  | FALSE
enum_values
enum_id | value | label | sort | tone
task_category | temporary_works | Temporary works | 10 | neutral
task_category | earthworks | Earthworks | 20 | neutral
task_category | foundation | Foundation | 30 | warning
task_category | structure | Structure | 40 | warning
task_category | finishing | Finishing | 50 | success
task_status | not_started | Not started | 10 | neutral
task_status | in_progress | In progress | 20 | warning
task_status | delayed | Delayed | 30 | danger
task_status | completed | Completed | 40 | success
priority | high | High | 10 | danger
priority | medium | Medium | 20 | warning
priority | low | Low | 30 | neutral
weekday | mon | Mon | 10 | neutral
weekday | tue | Tue | 20 | neutral
weekday | wed | Wed | 30 | neutral
weekday | thu | Thu | 40 | neutral
weekday | fri | Fri | 50 | neutral
weekly_status | planned | Planned | 10 | neutral
weekly_status | shared | Shared | 20 | warning
weekly_status | confirmed | Confirmed | 30 | success
event_category | meeting | Meeting | 10 | neutral
event_category | inspection | Inspection | 20 | warning
event_category | delivery | Delivery | 30 | success
event_category | safety | Safety | 40 | danger
event_status | scheduled | Scheduled | 10 | neutral
event_status | done | Done | 20 | success
event_status | changed | Changed | 30 | warning