## Panduan
Manajemen
Layar bisnis untuk mengelola jadwal konstruksi, rencana mingguan, rapat, pengiriman, dan data master dalam satu tempat.
How to use this workbook
Use the task master as the source table, then review the dashboard and generated helper sheets.
1 | Enter project tasks | Update task names, partners, crew counts, planned dates, progress, and notes in the task master.
2 | Choose statuses | Use the status dropdown so dashboard formulas and warning colors stay consistent.
3 | Review summaries | Check totals, completed work, delayed work, and the status breakdown on the dashboard.
Workbook structure
Task master | The source table for schedule, progress, partners, crew, and status.
Monthly plan | A generated timeline view for planned start and end dates.
Weekly plan | A short-term sharing sheet for site meetings and daily coordination.
linked_sheets
sheet_id | sheet_name | kind | module_id
project_settings | Basic settings | table | project_settings
taskmaster | Tugas | table | tasks
monthlyplan | Rencana bulanan | gantt | tasks
weeklyplan | Rencana mingguan | table | weekly_plans
events | Meeting delivery schedule | table | events
dashboard | Dasbor | dashboard
lookups | Lookups | lookup
schema | Schema | schema

## Basic settings
Basic settings
Layar bisnis untuk mengelola jadwal konstruksi, rencana mingguan, rapat, pengiriman, dan data master dalam satu tempat.
Setting ID | Setting item | Setting value | Owner | Notes
SET-001 | Project name | XX Apartment Building Project | Site manager | Use the official project name used in owner reports.
SET-002 | Site address | 1-2-3 Kanda, Tokyo | General affairs | Keep access and delivery instructions in the site meeting notes.
SET-003 | Schedule period | 2026-04-01 to 2026-04-30 | Construction manager | Match the period used for monthly progress review.
SET-004 | Weekly sharing start | 2026-04-13 | Site coordinator | Update before the weekly coordination meeting.

## Tugas
Tugas
Layar bisnis untuk mengelola jadwal konstruksi, rencana mingguan, rapat, pengiriman, dan data master dalam satu tempat.
Tingkat Keparahan | Kategori | Tugas | Rencana | Column5 | Mulai terencana | Rencana selesai | Column8 | Actual start | Actual end | Progres | Respons atau Catatan | Priority | Lokasi | Catatan
TASK-001 | temporary_works | Informasi tinjauan untuk manajemen jadwal konstruksi. | Manajemen | 4 | 2026-04-01 | 2026-04-03 | 40 | 2026-04-01 | 2026-04-03 | 100% | completed | high | Tugas | Informasi tinjauan untuk manajemen jadwal konstruksi.
TASK-002 | earthworks | Informasi tinjauan untuk manajemen jadwal konstruksi. | Manajemen | 6 | 2026-04-04 | 2026-04-08 | 40 | 2026-04-04 | 2026-04-08 | 100% | completed | high | Tugas | Informasi tinjauan untuk manajemen jadwal konstruksi.
TASK-003 | foundation | Foundation rebar and formwork | Tanaka Rebar | 5 | 2026-04-09 | 2026-04-16 | 40 | 2026-04-09 |  | 65% | in_progress | medium | Foundation area | Coordinate inspection before concrete pour.
TASK-004 | structure | First-floor frame erection | Shinsei Frame | 8 | 2026-04-17 | 2026-04-24 | 40 |  |  | 10% | delayed | high | Building frame | Crane schedule needs daily confirmation.

## Rencana bulanan
Rencana bulanan
Layar bisnis untuk mengelola jadwal konstruksi, rencana mingguan, rapat, pengiriman, dan data master dalam satu tempat.
Tingkat Keparahan | Tugas | Rencana | Respons atau Catatan | Progres | Mulai terencana | Rencana selesai | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30
TASK-001 | Informasi tinjauan untuk manajemen jadwal konstruksi. | Manajemen | completed | 100% | 2026-04-01 | 2026-04-03
TASK-002 | Informasi tinjauan untuk manajemen jadwal konstruksi. | Manajemen | completed | 100% | 2026-04-04 | 2026-04-08
TASK-003 | Foundation rebar and formwork | Tanaka Rebar | in_progress | 65% | 2026-04-09 | 2026-04-16
TASK-004 | First-floor frame erection | Shinsei Frame | delayed | 10% | 2026-04-17 | 2026-04-24

## Rencana mingguan
Rencana mingguan
Layar bisnis untuk mengelola jadwal konstruksi, rencana mingguan, rapat, pengiriman, dan data master dalam satu tempat.
Plan ID | Plan date | Weekday | Task name | Partner company | Crew | Planned work | Sharing status | Notes
WEEK-001 | 2026-04-13 | mon | Foundation rebar and formwork | Tanaka Rebar | 5 | Morning rebar placement and afternoon formwork checks. | shared | Share inspection readiness in the morning meeting.
WEEK-002 | 2026-04-14 | tue | Foundation rebar inspection | Supervisor / Tanaka Rebar | 5 | Inspection walkthrough and correction confirmation. | confirmed | Record correction items before noon.
WEEK-003 | 2026-04-17 | fri | Ready-mix delivery preparation | Central Ready-Mix | 8 | Confirm truck route, pump location, and receiving crew. | planned | Final pre-pour check required.

## Meeting delivery schedule
Meeting delivery schedule
Layar bisnis untuk mengelola jadwal konstruksi, rencana mingguan, rapat, pengiriman, dan data master dalam satu tempat.
Event ID | Tanggal | Waktu | Kategori | Manajemen | Column6 | Lokasi | Respons atau Catatan | Catatan
EVT-001 | 2026-04-13 | 08:00 | safety | Rencana | Informasi tinjauan untuk manajemen jadwal konstruksi. | Tugas | done | Informasi tinjauan untuk manajemen jadwal konstruksi.
EVT-002 | 2026-04-14 | 10:00 | inspection | Rencana | Informasi tinjauan untuk manajemen jadwal konstruksi. | Lokasi | done | Bring latest drawings and inspection checklist.
EVT-003 | 2026-04-17 | 13:00 | delivery | Rencana | Manajemen | Lokasi | scheduled | Informasi tinjauan untuk manajemen jadwal konstruksi.

## Dasbor
Dasbor
Layar bisnis untuk mengelola jadwal konstruksi, rencana mingguan, rapat, pengiriman, dan data master dalam satu tempat.
Tugas |  |  | Completed tasks | Tugas terlambat
Kemajuan rata-rata
Status breakdown
Respons atau Catatan | Jumlah | Porsi
Belum mulai | 40 | 40
Berjalan | 40 | 40
Terlambat | 40 | 40
Proyek konstruksi pusat | 40 | 40

## Lookups (hidden)
Lookups
Layar bisnis untuk mengelola jadwal konstruksi, rencana mingguan, rapat, pengiriman, dan data master dalam satu tempat.
task_category | enum_task_category_values | enum_task_category_labels
option_set | value | label | sort | active
task_category | temporary_works | Temporary works | 10 | TRUE
task_category | earthworks | Earthworks | 20 | TRUE
task_category | foundation | Foundation | 30 | TRUE
task_category | structure | Structure | 40 | TRUE
task_category | finishing | Finishing | 50 | TRUE
task_status | enum_task_status_values | enum_task_status_labels
option_set | value | label | sort | active
task_status | not_started | Belum mulai | 10 | TRUE
task_status | in_progress | Berjalan | 20 | TRUE
task_status | delayed | Terlambat | 30 | TRUE
task_status | completed | Proyek konstruksi pusat | 40 | TRUE
priority | enum_priority_values | enum_priority_labels
option_set | value | label | sort | active
priority | high | High | 10 | TRUE
priority | medium | Medium | 20 | TRUE
priority | low | Low | 30 | TRUE
weekday | enum_weekday_values | enum_weekday_labels
option_set | value | label | sort | active
weekday | mon | Mon | 10 | TRUE
weekday | tue | Tue | 20 | TRUE
weekday | wed | Wed | 30 | TRUE
weekday | thu | Thu | 40 | TRUE
weekday | fri | Fri | 50 | TRUE
weekly_status | enum_weekly_status_values | enum_weekly_status_labels
option_set | value | label | sort | active
weekly_status | planned | Planned | 10 | TRUE
weekly_status | shared | Shared | 20 | TRUE
weekly_status | confirmed | Confirmed | 30 | TRUE
event_category | enum_event_category_values | enum_event_category_labels
option_set | value | label | sort | active
event_category | meeting | Meeting | 10 | TRUE
event_category | inspection | Inspection | 20 | TRUE
event_category | delivery | Delivery | 30 | TRUE
event_category | safety | Safety | 40 | TRUE
event_status | enum_event_status_values | enum_event_status_labels
option_set | value | label | sort | active
event_status | scheduled | Scheduled | 10 | TRUE
event_status | done | Done | 20 | TRUE
event_status | changed | Changed | 30 | TRUE
boolean | boolean_values | boolean_labels
option_set | value | label | sort | active
boolean | true | Ya | 10 | TRUE
boolean | false | Tidak | 20 | TRUE

## Schema (hidden)
Schema
Layar bisnis untuk mengelola jadwal konstruksi, rencana mingguan, rapat, pengiriman, dan data master dalam satu tempat.
modules
module_id | label | description
project_settings | Project settings
tasks | Kemajuan
weekly_plans | Weekly sharing plan
events | Meetings and deliveries
fields
module_id | field_id | label | type | role | enum_id | required
project_settings | setting_id | Setting ID | text | primary_key |  | TRUE
project_settings | setting_item | Setting item | text | display_name |  | TRUE
project_settings | setting_value | Setting value | long_text | input |  | FALSE
project_settings | owner | Owner | text | owner |  | FALSE
project_settings | notes | Notes | long_text | input |  | FALSE
tasks | task_id | Tingkat Keparahan | text | primary_key |  | TRUE
tasks | category | Kategori | enum | category | task_category | FALSE
tasks | task_name | Tugas | text | display_name |  | TRUE
tasks | partner | Rencana | text | owner |  | FALSE
tasks | crew | Tugas | integer | quantity |  | FALSE
tasks | planned_start | Mulai terencana | date | start_date |  | FALSE
tasks | planned_end | Rencana selesai | date | end_date |  | FALSE
tasks | planned_days | Tugas | formula | computed |  | FALSE
tasks | actual_start | Actual start | date | actual_start_date |  | FALSE
tasks | actual_end | Actual end | date | actual_end_date |  | FALSE
tasks | progress | Progres | percent | quantity |  | FALSE
tasks | status | Respons atau Catatan | enum | status | task_status | TRUE
tasks | priority | Priority | enum | priority | priority | FALSE
tasks | location | Lokasi | text | location |  | FALSE
tasks | notes | Catatan | long_text | input |  | FALSE
weekly_plans | plan_id | Plan ID | text | primary_key |  | TRUE
weekly_plans | plan_date | Plan date | date | date |  | TRUE
weekly_plans | weekday | Weekday | enum | category | weekday | FALSE
weekly_plans | task_name | Task name | text | display_name |  | FALSE
weekly_plans | partner | Partner company | text | owner |  | FALSE
weekly_plans | crew | Crew | integer | quantity |  | FALSE
weekly_plans | planned_work | Planned work | long_text | input |  | FALSE
weekly_plans | status | Sharing status | enum | status | weekly_status | FALSE
weekly_plans | notes | Notes | long_text | input |  | FALSE
events | event_id | Event ID | text | primary_key |  | TRUE
events | date | Tanggal | date | date |  | FALSE
events | time | Waktu | text | time |  | FALSE
events | category | Kategori | enum | category | event_category | FALSE
events | details | Manajemen | text | display_name |  | FALSE
events | partner_companies | Manajemen | text | owner |  | FALSE
events | location | Lokasi | text | location |  | FALSE
events | status | Respons atau Catatan | enum | status | event_status | FALSE
events | notes | Catatan | long_text | input |  | FALSE
enum_values
enum_id | value | label | sort | tone
task_category | temporary_works | Temporary works | 10 | neutral
task_category | earthworks | Earthworks | 20 | neutral
task_category | foundation | Foundation | 30 | warning
task_category | structure | Structure | 40 | warning
task_category | finishing | Finishing | 50 | success
task_status | not_started | Belum mulai | 10 | neutral
task_status | in_progress | Berjalan | 20 | warning
task_status | delayed | Terlambat | 30 | danger
task_status | completed | Proyek konstruksi pusat | 40 | success
priority | high | High | 10 | danger
priority | medium | Medium | 20 | warning
priority | low | Low | 30 | neutral
weekday | mon | Mon | 10 | neutral
weekday | tue | Tue | 20 | neutral
weekday | wed | Wed | 30 | neutral
weekday | thu | Thu | 40 | neutral
weekday | fri | Fri | 50 | neutral
weekly_status | planned | Planned | 10 | neutral
weekly_status | shared | Shared | 20 | warning
weekly_status | confirmed | Confirmed | 30 | success
event_category | meeting | Meeting | 10 | neutral
event_category | inspection | Inspection | 20 | warning
event_category | delivery | Delivery | 30 | success
event_category | safety | Safety | 40 | danger
event_status | scheduled | Scheduled | 10 | neutral
event_status | done | Done | 20 | success
event_status | changed | Changed | 30 | warning