## Overview
Construction Subcontractor Lifecycle Assessment System ¦ Overview Dashboard
Core dashboard
[7 empty] | System logic | Runs a closed loop from qualification, tendering, contract and site entry, delivery, payment, post-completion evaluation, and reuse or exit; combines a 100-point model, red-line veto rules, monthly process tracking, and annual or project post-evaluation.
Subcontractors under review or approved | Average total score | Excellent or preferred count | Warning or banned count | Red-line triggers | High-risk monthly items |  |  | Scores directly drive bid invitations, limited-use controls, corrective re-evaluation, negative lists, and capability improvement plans.
4 | 76.245 | 0 | 2 | 2 | 1
Subcontractor overall ranking
Subcontractor | Category | Total score | Grade | Control status | Red-line count | Reuse recommendation
East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | 88.275 | B Qualified preferred | Normal use | 0 | Continue using
Excellence MEP Installation Co., Ltd. | Trade subcontractor | 78.255 | C Qualified watch | Limited use / close tracking | 0 | Limit high-risk packages and review monthly
Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | 62.205 | Red line | Negative list / banned | 2 | Do not include in bid lists for three years
GreenBuild Decoration Engineering Co., Ltd. | Trade subcontractor | 0 | E Exit | Negative list / banned | 0 | Do not include in bid lists for three years
Stage weights |  |  |  | Red-line quick check
Stage | Weight | Notes |  | Major safety or quality incident or concealment |  |  |  |  | Forged qualifications or certificates, borrowed qualifications, or affiliation
Qualification, credentials, and credit | 15 | Certificates, credit, QHSE, and capability |  | Illegal subcontracting, transfer, or work beyond qualification scope |  |  |  |  | Malicious wage arrears or collective labor incident
Tendering and contract fit | 10 | Technical scope, pricing, and contract boundaries |  | Commercial bribery, bid rigging, collusive bidding, or major dishonesty |  |  |  |  | Major environmental incident or refusal to correct
Start-up planning and site-entry preparation | 10 | Method statements, training, risk, and real-name management |  | Unauthorized replacement of key personnel or materials without approval |  |  |  |  | Refusal to accept general-contractor management or continued work despite suspended correction
Process delivery performance | 45 | Quality, safety, schedule, and coordination
Commercial payment and labor wages | 10 | Measurement, changes, and wage payment
Completion settlement and post-evaluation | 10 | Handover, warranty, review, and reuse

## Evaluation Model
Construction subcontractor lifecycle assessment model (100 points)
Stage | Stage weights | Indicator code | Assessment indicator | Indicator weight | Scoring points | Evidence source | Frequency | Responsible department | Red-line related
Qualification, credentials, and credit | 15 | A1 | Valid corporate qualification, business license, and safety production permit | 3 | Licenses are authentic and valid, and trade category and grade match the intended scope; certificates nearing expiry are already under alert. | Business license, qualification certificates, safety production permit, certificate register | Approved-list entry / annual review | Procurement / legal / safety | Yes
Qualification, credentials, and credit | 15 | A2 | Scope fits and there is no illegal subcontracting, transfer, or borrowed-qualification risk | 3 | Qualification borrowing, affiliation, transfer, or outsourcing of primary responsibility is prohibited; subcontract boundaries are clear. | Contract review, credit search, legal-person and ownership look-through, site check | Approved-list entry / before bidding | Legal / procurement / project | Yes
Qualification, credentials, and credit | 15 | A3 | Similar project experience and owner feedback in the past three years | 2 | Comparable project scale, method, and regional experience are sufficient, with strong owner feedback. | Performance contracts, completion certificates, owner feedback, past project scores | Approved-list entry / annual review | Procurement / engineering | No
Qualification, credentials, and credit | 15 | A4 | Financial stability, insurance, bonds, or guarantee capability | 2 | Financial position can support project cash flow; insurance, bonds, and guarantees meet contract requirements. | Financial statements, bank credit, insurance policies, bonds, tax records | Approved-list entry / before bidding | Finance / contract | No
Qualification, credentials, and credit | 15 | A5 | QHSE system, occupational health, and environmental management capability | 2 | Operable quality, safety, occupational health, and environmental systems or certifications are in place and match project risk. | QHSE procedures, certificates, incident records, system audit reports | Approved-list entry / annual review | Quality / safety | Yes
Qualification, credentials, and credit | 15 | A6 | Credit, litigation, administrative penalties, and integrity compliance records | 2 | No major dishonesty, major penalties, bid rigging, commercial bribery, or other high-risk records. | Credit platforms, court documents, administrative penalties, integrity commitments | Approved-list entry / before bidding | Legal / discipline inspection / procurement | Yes
Qualification, credentials, and credit | 15 | A7 | Core management, crew, and equipment capability | 1 | Project manager, technical lead, full-time safety officer, key crews, and equipment can meet peak project demand. | Staff resumes, certificates, equipment lists, crew rosters | Approved-list entry / before bidding | Engineering / safety | No
Tendering and contract fit | 10 | B1 | Technical response and construction method are complete and executable | 2 | Construction methods, work steps, quality control points, and risk measures match the tender documents. | Technical bid, construction organization design, special method statements | Bid review | Engineering / technical | No
Tendering and contract fit | 10 | B2 | Bill pricing completeness and price reasonableness | 2 | No major omissions, abnormally low prices, or unbalanced pricing; price level aligns with market and historical data. | Quoted bill, pricing analysis, inquiry and comparison records | Bid review | Cost / procurement | No
Tendering and contract fit | 10 | B3 | Schedule, resource, material, and equipment commitments are credible | 2 | Labor, material, and equipment input plans are verifiable, and key milestones align with the master schedule. | Resource plan, supply plan, schedule commitment letter | Bid review | Engineering / planning | No
Tendering and contract fit | 10 | B4 | Contract scope, SOV, drawings, and specifications are clearly aligned | 2 | Scope of work, quantities, valuation milestones, acceptance criteria, and drawing/spec references are consistent. | Contract scope, SOV, interface matrix, drawing and specification list | Before contract signing | Contract / engineering | No
Tendering and contract fit | 10 | B5 | Response to change, claim, dispute, and payment terms | 1 | Change orders, dispute resolution, payment milestones, retention, and default liability are clear and enforceable. | Contract clauses, negotiation minutes, risk list | Before contract signing | Contract / legal / finance | No
Tendering and contract fit | 10 | B6 | Integrity, confidentiality, and data compliance commitments | 1 | Integrity, confidentiality, information security, and data compliance commitments are signed and understood by key personnel. | Commitment letters, training sign-ins, contract attachments | Before contract signing | Discipline inspection / legal / procurement | Yes
Start-up planning and site-entry preparation | 10 | C1 | Construction organization design and special method approval | 2 | Plans are prepared, reviewed, approved, and expert-reviewed as required; site versions are controlled. | Construction organization design, special method statements, expert review, approval records | Before start / major change | Engineering / technical / safety | Yes
Start-up planning and site-entry preparation | 10 | C2 | Site-entry certificates, special-operation permits, and training | 2 | Real-name registration is complete, certificates are valid, and tiered safety education, special briefings, and entry exams are complete. | Real-name register, certificates, training records, exam records | Site entry / monthly | Safety / labor | Yes
Start-up planning and site-entry preparation | 10 | C3 | Risk assessment, work permits, and emergency plan | 2 | High-risk work has JSA/risk matrix, permits, emergency resources, and drills in place. | Risk assessment forms, work permits, emergency plans, drill records | Before start / before work | Safety / project | Yes
Start-up planning and site-entry preparation | 10 | C4 | Material and equipment submittals, mockups, and first-article preparation | 1.5 | Materials, equipment, tools, mockups, first-article acceptance, and test plans are fully prepared. | Submittals, certificates of conformity, test plans, mockup acceptance records | Before start / before site entry | Quality / engineering | No
Start-up planning and site-entry preparation | 10 | C5 | Labor contracts, real-name system, and payroll agency documents | 1.5 | Labor contracts, real-name registration, payroll cards, wage sheet process, and entrusted payroll documents are complete. | Labor contracts, real-name platform, payroll cards, entrusted payroll agreement | Site entry / monthly | Labor / finance | Yes
Start-up planning and site-entry preparation | 10 | C6 | Interface handover, site conditions, and start order | 1 | Work fronts, temporary power and water, survey control points, and interface conditions are handed over and ready for start. | Interface handover forms, start order, site photos | Before start | Project / engineering | No
Process delivery performance | 45 | D1 | First-pass acceptance rate and inspection lot quality | 4 | Inspection lots, sub-items, and concealed works meet first-pass targets with no systemic quality defects. | Quality acceptance records, inspection lot data, third-party tests | Monthly / milestone | Quality / project | No
Process delivery performance | 45 | D2 | Rework rate, NCR count, and timely closure rate | 3 | Rework, repair, and nonconformities are controlled, and NCRs close on time. | NCR register, corrective closure records, rework records | Monthly / milestone | Quality / project | No
Process delivery performance | 45 | D3 | Material and equipment quality, submittal, and testing compliance | 3 | Materials and equipment comply with contract and specifications; substitutions require approval; tests are timely and valid. | Material submittals, certificates, test reports, substitution approvals | Monthly / batch | Quality / materials | No
Process delivery performance | 45 | D4 | Technical briefing, mockup-led execution, and process compliance | 2 | Critical processes follow briefings and mockups, and process records are traceable. | Technical briefings, mockup acceptance, process witness records | Monthly / milestone | Engineering / quality | No
Process delivery performance | 45 | D5 | Finished-work protection and cross-trade quality | 2 | Finished-work protection is implemented, and quality damage from cross-trade work is controlled. | Finished-work protection records, patrol records, issue closure | Monthly / milestone | Engineering / quality | No
Process delivery performance | 45 | D6 | Quality issue prevention and continuous improvement | 1 | Quality trend analysis, reviews, and preventive actions are carried out proactively. | Quality meeting minutes, improvement actions, review reports | Monthly | Quality / project | No
Process delivery performance | 45 | D7 | Safety incidents, near misses, and violations | 4 | No major incidents or serious violations; near misses are reported and corrected promptly. | Incident/near-miss records, penalty notices, videos/photos | Routine / monthly | Safety / project | Yes
Process delivery performance | 45 | D8 | Safety inspection corrective closure rate | 3 | Safety hazards are corrected within required deadlines with complete closure evidence. | Safety checklists, correction notices, closure photos | Weekly / monthly | Safety / project | Yes
Process delivery performance | 45 | D9 | Toolbox meetings, safety training, and permit execution | 2 | Toolbox meetings, special training, and hot-work/lifting/temporary-power permits are properly executed. | Toolbox records, training sign-ins, work permits | Routine / monthly | Safety / crews | Yes
Process delivery performance | 45 | D10 | Major-risk works and high-risk work control | 2 | Major-risk works follow approved plans, with witness, monitoring, and acceptance for critical processes. | Major-risk work register, witness records, monitoring records | Milestone / before work | Safety / engineering | Yes
Process delivery performance | 45 | D11 | Civilized construction, environmental, dust, noise, and waste control | 1 | Site appearance, material stacking, dust, noise, wastewater, and solid waste meet project requirements. | Civilized construction checks, environmental monitoring, penalty records | Weekly / monthly | Safety / environment | Yes
Process delivery performance | 45 | D12 | Schedule milestone completion rate | 3 | Monthly/weekly plans and key milestones meet targets without material impact on the master schedule. | Master schedule, weekly plan, monthly progress report | Weekly / monthly | Planning / engineering | No
Process delivery performance | 45 | D13 | Labor, material, and equipment availability rate | 2 | Labor, major materials, and equipment arrive as committed and meet peak construction needs. | Attendance, equipment arrival, material delivery records | Weekly / monthly | Engineering / materials | No
Process delivery performance | 45 | D14 | Delay warning and acceleration correction effectiveness | 2 | Delays are warned early, acceleration and correction measures are effective, and responsibilities are clear. | Warning notices, acceleration plan, meeting minutes, updated schedule | Weekly / monthly | Planning / project | No
Process delivery performance | 45 | D15 | Coordination with other trades | 2 | Interface handover, interleaved work, design changes, and site coordination run smoothly. | Interface list, meeting minutes, handover forms | Weekly / monthly | Engineering / project | No
Process delivery performance | 45 | D16 | Timeliness of RFI, meeting, and project instruction responses | 2 | Technical clarifications, RFIs, meeting minutes, and project instructions are answered promptly with clear closure. | RFI register, meeting minutes, instruction notices | Weekly / monthly | Engineering / commercial | No
Process delivery performance | 45 | D17 | Construction documents, concealed-work acceptance, and test report submission | 2 | Documents progress with construction, and concealed-work acceptance and test reports are filed on time. | Document register, concealed-work acceptance, test reports | Monthly / milestone | Documentation / quality | No
Process delivery performance | 45 | D18 | Change order documents are timely and accurate | 2 | Change, order, and site confirmation documents are timely, accurate, and traceable. | Change forms, order forms, site photos, measurement records | Monthly / event | Commercial / engineering | No
Process delivery performance | 45 | D19 | Site sign-off, measurement data, and cost loss control | 2 | Measurement data is accurate, and material loss, equipment shifts, and rework costs are controlled. | Measurement register, material issue records, cost analysis | Monthly | Commercial / cost | No
Process delivery performance | 45 | D20 | Digital platform, daily report, and weekly report execution | 1 | Daily reports, weekly reports, images, and collaboration platforms are used as required, with complete and truthful data. | Daily/weekly reports, platform logs, image records | Routine / monthly | Project / information | No
Commercial payment and labor wages | 10 | E1 | Monthly progress claim is accurate and complete | 2 | Measurement period, quantities, visual progress, and attachment evidence are complete and accurate. | Payment claim, measurement records, acceptance records | Monthly | Commercial / engineering | No
Commercial payment and labor wages | 10 | E2 | Invoices, tax, and payment documents are timely and compliant | 1 | Invoices, tax documents, payment applications, and contract attachments are complete and without exceptions. | Invoices, payment applications, tax documents | Monthly / before payment | Finance / commercial | No
Commercial payment and labor wages | 10 | E3 | Change claim and counterclaim evidence closure | 2 | Change claims follow contract procedures with sufficient evidence; counterclaims are handled promptly. | Change claim register, evidence chain, dispute handling records | Monthly / event | Commercial / legal | No
Commercial payment and labor wages | 10 | E4 | Payroll, attendance, real-name records, and general-contractor payroll support | 3 | Payroll sheets, attendance, and real-name data are submitted monthly to support general-contractor supervision and payment. | Real-name register, attendance, payroll sheets, agency payment records | Monthly | Labor / finance | Yes
Commercial payment and labor wages | 10 | E5 | No arrears, complaints, or collective incidents | 2 | No wage arrears, malicious wage demands, labor disputes, or collective incidents. | Complaint records, wage payment evidence, stability records | Monthly / event | Labor / legal | Yes
Completion settlement and post-evaluation | 10 | F1 | Completion documents, handover documents, and maintenance manuals are complete | 2 | As-built drawings, quality warranty documents, test reports, and maintenance instructions are complete and handed over on time. | Completion document list, handover sign-off, maintenance manual | Completion / handover | Documentation / quality | No
Completion settlement and post-evaluation | 10 | F2 | Defect correction and warranty response | 2 | Defect lists close on time, warranty responses are timely, and recurrence is low. | Defect list, warranty orders, closure records | Completion / warranty | Quality / project | No
Completion settlement and post-evaluation | 10 | F3 | Final account support and dispute resolution | 2 | Final account documents are submitted on time, and disputed matters have sufficient evidence and efficient handling. | Final account statement, reconciliation statement, dispute closure records | Completion / final account | Commercial / legal | No
Completion settlement and post-evaluation | 10 | F4 | Performance review, lessons learned, and two-way evaluation | 2 | Project review is completed, with issues, corrective actions, and two-way improvement suggestions retained. | Post-evaluation form, review report, meeting minutes | After completion | Project / procurement | No
Completion settlement and post-evaluation | 10 | F5 | Future reuse recommendation and capability improvement plan | 2 | Reuse, limited-use, correction, exit recommendations, and capability improvement plans are formed. | Post-evaluation conclusion, correction plan, approved-list status adjustment | After completion / annual | Procurement / project | No

## Score Entry
Score Entry ¦ Record evidence by project, subcontractor, and indicator
Date | Item | Contract No. | Subcontractor | Subcontract category | Stage | Indicator code | Indicator | Weight | Score (0-100) | Red-line triggered | Deduction / correction notes | Evidence link / No. | Reviewer | Weighted score | Score status
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A1 | Valid corporate qualification, business license, and safety production permit | 3 | 87 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 2.61 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A2 | Scope fits and there is no illegal subcontracting, transfer, or borrowed-qualification risk | 3 | 91 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 2.73 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A3 | Similar project experience and owner feedback in the past three years | 2 | 87 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.74 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A4 | Financial stability, insurance, bonds, or guarantee capability | 2 | 86 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.72 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A5 | QHSE system, occupational health, and environmental management capability | 2 | 83 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.66 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A6 | Credit, litigation, administrative penalties, and integrity compliance records | 2 | 87 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.74 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A7 | Core management, crew, and equipment capability | 1 | 94 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 0.94 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Tendering and contract fit | B1 | Technical response and construction method are complete and executable | 2 | 90 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.8 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Tendering and contract fit | B2 | Bill pricing completeness and price reasonableness | 2 | 93 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.86 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Tendering and contract fit | B3 | Schedule, resource, material, and equipment commitments are credible | 2 | 89 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.78 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Tendering and contract fit | B4 | Contract scope, SOV, drawings, and specifications are clearly aligned | 2 | 90 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.8 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Tendering and contract fit | B5 | Response to change, claim, dispute, and payment terms | 1 | 89 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 0.89 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Tendering and contract fit | B6 | Integrity, confidentiality, and data compliance commitments | 1 | 80 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 0.8 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C1 | Construction organization design and special method approval | 2 | 92 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.84 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C2 | Site-entry certificates, special-operation permits, and training | 2 | 91 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.82 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C3 | Risk assessment, work permits, and emergency plan | 2 | 90 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.8 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C4 | Material and equipment submittals, mockups, and first-article preparation | 1.5 | 80 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.2 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C5 | Labor contracts, real-name system, and payroll agency documents | 1.5 | 79 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.185 | Observe
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C6 | Interface handover, site conditions, and start order | 1 | 84 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 0.84 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D1 | First-pass acceptance rate and inspection lot quality | 4 | 92 | No | Performance is above target and evidence is complete. | Project documents / platform records | Commercial manager | 3.68 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D2 | Rework rate, NCR count, and timely closure rate | 3 | 90 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 2.7 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D3 | Material and equipment quality, submittal, and testing compliance | 3 | 88 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 2.64 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D4 | Technical briefing, mockup-led execution, and process compliance | 2 | 91 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.82 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D5 | Finished-work protection and cross-trade quality | 2 | 85 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.7 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D6 | Quality issue prevention and continuous improvement | 1 | 90 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 0.9 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D7 | Safety incidents, near misses, and violations | 4 | 90 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 3.6 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D8 | Safety inspection corrective closure rate | 3 | 92 | No | Performance is above target and evidence is complete. | Project documents / platform records | Safety lead | 2.76 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D9 | Toolbox meetings, safety training, and permit execution | 2 | 97 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.94 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D10 | Major-risk works and high-risk work control | 2 | 91 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.82 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D11 | Civilized construction, environmental, dust, noise, and waste control | 1 | 94 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 0.94 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D12 | Schedule milestone completion rate | 3 | 85 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 2.55 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D13 | Labor, material, and equipment availability rate | 2 | 84 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.68 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D14 | Delay warning and acceleration correction effectiveness | 2 | 86 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.72 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D15 | Coordination with other trades | 2 | 87 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.74 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D16 | Timeliness of RFI, meeting, and project instruction responses | 2 | 91 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.82 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D17 | Construction documents, concealed-work acceptance, and test report submission | 2 | 89 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.78 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D18 | Change order documents are timely and accurate | 2 | 86 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.72 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D19 | Site sign-off, measurement data, and cost loss control | 2 | 83 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.66 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Process delivery performance | D20 | Digital platform, daily report, and weekly report execution | 1 | 85 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 0.85 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Commercial payment and labor wages | E1 | Monthly progress claim is accurate and complete | 2 | 94 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.88 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Commercial payment and labor wages | E2 | Invoices, tax, and payment documents are timely and compliant | 1 | 84 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 0.84 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Commercial payment and labor wages | E3 | Change claim and counterclaim evidence closure | 2 | 89 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.78 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Commercial payment and labor wages | E4 | Payroll, attendance, real-name records, and general-contractor payroll support | 3 | 92 | No | Performance is above target and evidence is complete. | Project documents / platform records | Safety lead | 2.76 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Commercial payment and labor wages | E5 | No arrears, complaints, or collective incidents | 2 | 81 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.62 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Completion settlement and post-evaluation | F1 | Completion documents, handover documents, and maintenance manuals are complete | 2 | 88 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.76 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Completion settlement and post-evaluation | F2 | Defect correction and warranty response | 2 | 92 | No | Performance is above target and evidence is complete. | Project documents / platform records | Quality lead | 1.84 | Excellent
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Completion settlement and post-evaluation | F3 | Final account support and dispute resolution | 2 | 78 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.56 | Observe
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Completion settlement and post-evaluation | F4 | Performance review, lessons learned, and two-way evaluation | 2 | 86 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.72 | Qualified
2025-05-31 | Rivergate Complex Project | RG-GC-2025-001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Completion settlement and post-evaluation | F5 | Future reuse recommendation and capability improvement plan | 2 | 87 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.74 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A1 | Valid corporate qualification, business license, and safety production permit | 3 | 75 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 2.25 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A2 | Scope fits and there is no illegal subcontracting, transfer, or borrowed-qualification risk | 3 | 81 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 2.43 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A3 | Similar project experience and owner feedback in the past three years | 2 | 79 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.58 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A4 | Financial stability, insurance, bonds, or guarantee capability | 2 | 72 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.44 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A5 | QHSE system, occupational health, and environmental management capability | 2 | 83 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.66 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A6 | Credit, litigation, administrative penalties, and integrity compliance records | 2 | 82 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.64 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Qualification, credentials, and credit | A7 | Core management, crew, and equipment capability | 1 | 84 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 0.84 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Tendering and contract fit | B1 | Technical response and construction method are complete and executable | 2 | 86 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.72 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Tendering and contract fit | B2 | Bill pricing completeness and price reasonableness | 2 | 81 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.62 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Tendering and contract fit | B3 | Schedule, resource, material, and equipment commitments are credible | 2 | 80 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.6 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Tendering and contract fit | B4 | Contract scope, SOV, drawings, and specifications are clearly aligned | 2 | 73 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.46 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Tendering and contract fit | B5 | Response to change, claim, dispute, and payment terms | 1 | 82 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 0.82 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Tendering and contract fit | B6 | Integrity, confidentiality, and data compliance commitments | 1 | 76 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 0.76 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C1 | Construction organization design and special method approval | 2 | 77 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.54 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C2 | Site-entry certificates, special-operation permits, and training | 2 | 73 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.46 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C3 | Risk assessment, work permits, and emergency plan | 2 | 74 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.48 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C4 | Material and equipment submittals, mockups, and first-article preparation | 1.5 | 76 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.14 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C5 | Labor contracts, real-name system, and payroll agency documents | 1.5 | 85 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.275 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Start-up planning and site-entry preparation | C6 | Interface handover, site conditions, and start order | 1 | 69 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 0.69 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D1 | First-pass acceptance rate and inspection lot quality | 4 | 72 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 2.88 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D2 | Rework rate, NCR count, and timely closure rate | 3 | 80 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 2.4 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D3 | Material and equipment quality, submittal, and testing compliance | 3 | 86 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 2.58 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D4 | Technical briefing, mockup-led execution, and process compliance | 2 | 82 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.64 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D5 | Finished-work protection and cross-trade quality | 2 | 70 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.4 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D6 | Quality issue prevention and continuous improvement | 1 | 66 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 0.66 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D7 | Safety incidents, near misses, and violations | 4 | 81 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 3.24 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D8 | Safety inspection corrective closure rate | 3 | 75 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 2.25 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D9 | Toolbox meetings, safety training, and permit execution | 2 | 73 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.46 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D10 | Major-risk works and high-risk work control | 2 | 84 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.68 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D11 | Civilized construction, environmental, dust, noise, and waste control | 1 | 85 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 0.85 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D12 | Schedule milestone completion rate | 3 | 72 | No | Lag exists and has been included in corrective tracking. | Project documents / platform records | Safety lead | 2.16 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D13 | Labor, material, and equipment availability rate | 2 | 80 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.6 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D14 | Delay warning and acceleration correction effectiveness | 2 | 81 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.62 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D15 | Coordination with other trades | 2 | 87 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.74 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D16 | Timeliness of RFI, meeting, and project instruction responses | 2 | 82 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.64 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D17 | Construction documents, concealed-work acceptance, and test report submission | 2 | 72 | No | Lag exists and has been included in corrective tracking. | Project documents / platform records | Commercial manager | 1.44 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D18 | Change order documents are timely and accurate | 2 | 82 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.64 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D19 | Site sign-off, measurement data, and cost loss control | 2 | 71 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.42 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Process delivery performance | D20 | Digital platform, daily report, and weekly report execution | 1 | 85 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 0.85 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Commercial payment and labor wages | E1 | Monthly progress claim is accurate and complete | 2 | 84 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.68 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Commercial payment and labor wages | E2 | Invoices, tax, and payment documents are timely and compliant | 1 | 82 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 0.82 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Commercial payment and labor wages | E3 | Change claim and counterclaim evidence closure | 2 | 72 | No | Lag exists and has been included in corrective tracking. | Project documents / platform records | Quality lead | 1.44 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Commercial payment and labor wages | E4 | Payroll, attendance, real-name records, and general-contractor payroll support | 3 | 76 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 2.28 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Commercial payment and labor wages | E5 | No arrears, complaints, or collective incidents | 2 | 83 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.66 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Completion settlement and post-evaluation | F1 | Completion documents, handover documents, and maintenance manuals are complete | 2 | 70 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.4 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Completion settlement and post-evaluation | F2 | Defect correction and warranty response | 2 | 78 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.56 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Completion settlement and post-evaluation | F3 | Final account support and dispute resolution | 2 | 84 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.68 | Qualified
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Completion settlement and post-evaluation | F4 | Performance review, lessons learned, and two-way evaluation | 2 | 72 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.44 | Observe
2025-05-31 | Rivergate Complex Project | RG-ME-2025-002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | Completion settlement and post-evaluation | F5 | Future reuse recommendation and capability improvement plan | 2 | 87 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.74 | Qualified
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Qualification, credentials, and credit | A1 | Valid corporate qualification, business license, and safety production permit | 3 | 69 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 2.07 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Qualification, credentials, and credit | A2 | Scope fits and there is no illegal subcontracting, transfer, or borrowed-qualification risk | 3 | 65 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.95 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Qualification, credentials, and credit | A3 | Similar project experience and owner feedback in the past three years | 2 | 68 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.36 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Qualification, credentials, and credit | A4 | Financial stability, insurance, bonds, or guarantee capability | 2 | 69 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.38 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Qualification, credentials, and credit | A5 | QHSE system, occupational health, and environmental management capability | 2 | 67 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.34 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Qualification, credentials, and credit | A6 | Credit, litigation, administrative penalties, and integrity compliance records | 2 | 72 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.44 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Qualification, credentials, and credit | A7 | Core management, crew, and equipment capability | 1 | 63 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 0.63 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Tendering and contract fit | B1 | Technical response and construction method are complete and executable | 2 | 64 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.28 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Tendering and contract fit | B2 | Bill pricing completeness and price reasonableness | 2 | 71 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.42 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Tendering and contract fit | B3 | Schedule, resource, material, and equipment commitments are credible | 2 | 66 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.32 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Tendering and contract fit | B4 | Contract scope, SOV, drawings, and specifications are clearly aligned | 2 | 62 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.24 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Tendering and contract fit | B5 | Response to change, claim, dispute, and payment terms | 1 | 71 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 0.71 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Tendering and contract fit | B6 | Integrity, confidentiality, and data compliance commitments | 1 | 73 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 0.73 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Start-up planning and site-entry preparation | C1 | Construction organization design and special method approval | 2 | 64 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.28 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Start-up planning and site-entry preparation | C2 | Site-entry certificates, special-operation permits, and training | 2 | 59 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.18 | Not qualified
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Start-up planning and site-entry preparation | C3 | Risk assessment, work permits, and emergency plan | 2 | 65 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.3 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Start-up planning and site-entry preparation | C4 | Material and equipment submittals, mockups, and first-article preparation | 1.5 | 65 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 0.975 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Start-up planning and site-entry preparation | C5 | Labor contracts, real-name system, and payroll agency documents | 1.5 | 58 | No | Real-name and payroll documents are incomplete and require special correction. | Project documents / platform records | Quality lead | 0.87 | Not qualified
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Start-up planning and site-entry preparation | C6 | Interface handover, site conditions, and start order | 1 | 73 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 0.73 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D1 | First-pass acceptance rate and inspection lot quality | 4 | 61 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 2.44 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D2 | Rework rate, NCR count, and timely closure rate | 3 | 72 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 2.16 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D3 | Material and equipment quality, submittal, and testing compliance | 3 | 60 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.8 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D4 | Technical briefing, mockup-led execution, and process compliance | 2 | 62 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.24 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D5 | Finished-work protection and cross-trade quality | 2 | 69 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.38 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D6 | Quality issue prevention and continuous improvement | 1 | 72 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 0.72 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D7 | Safety incidents, near misses, and violations | 4 | 45 | Yes | A red-line risk item occurred and must be corrected and re-evaluated immediately. | Project documents / platform records | Quality lead | 0 | Red-line triggered
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D8 | Safety inspection corrective closure rate | 3 | 68 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 2.04 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D9 | Toolbox meetings, safety training, and permit execution | 2 | 67 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.34 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D10 | Major-risk works and high-risk work control | 2 | 67 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.34 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D11 | Civilized construction, environmental, dust, noise, and waste control | 1 | 69 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 0.69 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D12 | Schedule milestone completion rate | 3 | 65 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.95 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D13 | Labor, material, and equipment availability rate | 2 | 67 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.34 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D14 | Delay warning and acceleration correction effectiveness | 2 | 69 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.38 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D15 | Coordination with other trades | 2 | 66 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.32 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D16 | Timeliness of RFI, meeting, and project instruction responses | 2 | 70 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.4 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D17 | Construction documents, concealed-work acceptance, and test report submission | 2 | 69 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.38 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D18 | Change order documents are timely and accurate | 2 | 76 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.52 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D19 | Site sign-off, measurement data, and cost loss control | 2 | 68 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.36 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Process delivery performance | D20 | Digital platform, daily report, and weekly report execution | 1 | 64 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 0.64 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Commercial payment and labor wages | E1 | Monthly progress claim is accurate and complete | 2 | 64 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.28 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Commercial payment and labor wages | E2 | Invoices, tax, and payment documents are timely and compliant | 1 | 66 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 0.66 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Commercial payment and labor wages | E3 | Change claim and counterclaim evidence closure | 2 | 71 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.42 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Commercial payment and labor wages | E4 | Payroll, attendance, real-name records, and general-contractor payroll support | 3 | 58 | No | Real-name and payroll documents are incomplete and require special correction. | Project documents / platform records | Safety lead | 1.74 | Not qualified
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Commercial payment and labor wages | E5 | No arrears, complaints, or collective incidents | 2 | 45 | Yes | A red-line risk item occurred and must be corrected and re-evaluated immediately. | Project documents / platform records | Commercial manager | 0 | Red-line triggered
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Completion settlement and post-evaluation | F1 | Completion documents, handover documents, and maintenance manuals are complete | 2 | 75 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.5 | Observe
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Completion settlement and post-evaluation | F2 | Defect correction and warranty response | 2 | 53 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Quality lead | 1.06 | Not qualified
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Completion settlement and post-evaluation | F3 | Final account support and dispute resolution | 2 | 60 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Safety lead | 1.2 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Completion settlement and post-evaluation | F4 | Performance review, lessons learned, and two-way evaluation | 2 | 67 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Commercial manager | 1.34 | Corrective action
2025-05-31 | Rivergate Complex Project | RG-LB-2025-003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Completion settlement and post-evaluation | F5 | Future reuse recommendation and capability improvement plan | 2 | 68 | No | Recorded according to policy, with no major exceptions noted. | Project documents / platform records | Project manager | 1.36 | Corrective action

## Subcontractor Register
Subcontractor Register ¦ Qualification status, overall assessment, and reuse strategy
Subcontractor ID | Subcontractor name | Subcontract category | Main trade | Qualification status | Approved date | Qualification/certificate expiry | Insurance expiry | Projects in last 12 months | Latest total score | Grade | Control status | Red-line count | Correction deadline | Reuse recommendation | Remarks
SUB001 | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | Steel structure | Approved | 2024-03-15 | 2027-06-30 | 2026-12-31 | 3 | 88.275 | B Qualified preferred | Normal use | 0 |  | Continue using
SUB002 | Excellence MEP Installation Co., Ltd. | Trade subcontractor | MEP installation | Approved | 2023-08-05 | 2026-09-30 | 2026-09-30 | 2 | 78.255 | C Qualified watch | Limited use / close tracking | 0 | 2026-11-10 | Limit high-risk packages and review monthly
SUB003 | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | Structural labor | Warning | 2022-11-20 | 2025-10-31 | 2025-11-30 | 1 | 62.205 | Red line | Negative list / banned | 2 |  | Do not include in bid lists for three years
SUB004 | GreenBuild Decoration Engineering Co., Ltd. | Trade subcontractor | Fit-out | Pending review | 2024-09-01 | 2026-03-31 | 2026-05-31 | 0 | 0 | E Exit | Negative list / banned | 0 |  | Do not include in bid lists for three years
Formulas:
Correction deadline = IF([Subcontractor name]="","",IF(OR([Control status]="Warning correction",[Control status]="Limited use / close tracking"),TODAY()+180,""))

## Monthly Process Tracking
Monthly Process Tracking ¦ Schedule, quality, safety, labor, and commercial risk
Month | Item | Subcontractor | Subcontract category | Planned completion rate | Actual completion rate | Schedule variance | First-pass acceptance rate | Open NCR count | Major safety incident count | General violation count | Site workers | Real-name registration rate | Wages paid on time | Unconfirmed change amount | Overdue document items | Monthly risk level | Corrective measures | Owner
2025-05-01 | Rivergate Complex Project | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | 62% | 64% | 2% | 96% | 1 | 0 | 2 | 86 | 99% | Yes | 120000 | 1 | Low | Keep rolling weekly plan corrections | Project manager
2025-05-01 | Rivergate Complex Project | Excellence MEP Installation Co., Ltd. | Trade subcontractor | 48% | 43% | -5% | 90% | 4 | 0 | 8 | 54 | 97% | Yes | 380000 | 4 | Low | Increase labor and submit acceleration plan | MEP engineer
2025-05-01 | Rivergate Complex Project | Anhe Labor Subcontracting Co., Ltd. | Labor subcontractor | 55% | 46% | -9% | 84% | 8 | 1 | 18 | 120 | 88% | No | 250000 | 9 | High | Pause new work fronts and start special rectification | Safety lead
2025-04-01 | Rivergate Complex Project | East China Steel Structure Engineering Co., Ltd. | Trade subcontractor | 50% | 51% | 1% | 95% | 1 | 0 | 3 | 78 | 100% | Yes | 80000 | 0 | Low | None | Project manager
2025-04-01 | Rivergate Complex Project | Excellence MEP Installation Co., Ltd. | Trade subcontractor | 38% | 36% | -2% | 92% | 3 | 0 | 5 | 49 | 98% | Yes | 210000 | 2 | Low | Track material deliveries | MEP engineer

## Rules and Sources
Construction Subcontractor Lifecycle Assessment System ¦ Rules and Sources
Scope of application | Applies to EPC or general construction contractors managing qualification, tendering, contracts, site entry, delivery, payment, completion, and reuse for trade, labor, equipment installation, and fit-out subcontractors.
Scoring basis | Total score is 100 points. Indicator weights are score weights; item weighted score = indicator weight x score / 100. If only part of the indicators are assessed, the total score is normalized by assessed indicator weight.
Scoring cycle | Qualification / annual review; before bidding; before start; monthly or at key milestones; before payment; after completion; annual overall assessment.
Red-line principle | Major safety or quality incidents, illegal subcontracting/transfer/affiliation, forged certificates, malicious wage arrears, commercial bribery, refusal to correct, or major environmental incidents may lead directly to warning or negative-list status.
Total score | Grade | Management action | Reuse strategy
≥90 | A Excellent | Invite first and treat as benchmark subcontractor | Framework cooperation / priority allocation of high-value packages
80-89 | B Qualified preferred | Normal use, monitor ordinary gaps | Continue using
70-79 | C Qualified watch | Limited use, monthly tracking by project team | Restrict high-risk packages
60-69 | D Warning correction | Pause new assignments and require timed correction and re-evaluation | Restore after correction passes
<60 | E Exit | Remove from approved pool or add to negative list | Do not invite in principle
Red-line triggered | Red line | Investigate immediately; stop work, suspend payment, or remove as appropriate | Add to negative list or ban for three years
Source category | Relevant excerpt | URL
Local page | User-provided local template page; the current session cannot access it directly | http://localhost:2020/zh/excel-templates/construction/subcontractor-lifecycle-scorecard/
Contractor lifecycle | Campbell Institute: the contractor lifecycle includes prequalification, pre-job risk assessment, training and onboarding, process monitoring, post-completion evaluation, and other stages | https://www.thecampbellinstitute.org/wp-content/uploads/2020/02/374956_CI_Contractor-Management_WP_FNL_Digital.pdf
Subcontract lifecycle process | CMiC: subcontract processes manage qualification, bidding, work start, contracts, payments, changes, and other steps | https://docs.cmicglobal.com/portal/Content/E_Reference_Material/SC_-_Subcontract_Management/Reference/Overview/SC_Lifecycle.htm
Prequalification indicators | Procore: subcontractor prequalification usually collects financial, safety record, project experience, and similar information to reduce delay, cost overrun, and safety risk | https://www.procore.com/library/subcontractor-prequalification
Process monitoring indicators | AppIt/FlowSense: process monitoring can cover schedule, quality, safety, resources, communication responsiveness, and similar indicators | https://www.appitsoftware.com/blog/subcontractor-management-best-practices-construction-2025
Migrant worker wage payment | Regulations on Ensuring Wage Payment to Migrant Workers: general construction contractors supervise labor use and wage payment by subcontractors | https://www.moj.gov.cn/pub/sfbgw/jgsz/jgszzsdw/zsdwflyzzx/flyzzxzcxx/zcxxzcfg/zcfgxzfg/202001/t20200117_188766.html
Construction project safety | Regulations on Construction Project Safety Production Management: construction-related entities must comply with safety production laws and regulations and ensure safe production | https://www.moj.gov.cn/pub/sfbgw/flfggz/flfggzxzfg/200405/t20040524_350438.html
Dynamic assessment and negative list | China Aluminum International social responsibility report discloses strict admission, preferential use, standardized vendor selection, dynamic management, and excellent/qualified/warning/negative-list classifications | https://www.hkexnews.hk/listedco/listconews/sehk/2020/0330/2020033003052_c.pdf