## मार्गदर्शक
Facility Management Equipment Repair Replace Lcc Template
Excel template for facility management equipment repair replace lcc template.
Type | Color | Meaning | Main Usage
Input | #F4F6F6 | Cells where the user enters amounts, dates, notes, etc. directly. | Equipment Register, Repair Records, Approval Tracking
Select | #EBF5FA | Cells selected from dropdown menus | Equipment ID, Risk Category, Application Status
Auto Calculation | #EBF2F0 | Cells automatically calculated by formulas. | Dashboard, LCC Calculation, Decision Matrix

## डॅशबोर्ड
डॅशबोर्ड
Excel template for facility management equipment repair replace lcc template.
Equipment ID | Equipment Name | Years Elapsed | Repair Ratio (%) | Assessment Result (Replace/Monitor/Optimal) | सुचवलेली कृती

## उपकरण नोंदणी
उपकरण नोंदणी
Excel template for facility management equipment repair replace lcc template.
Equipment ID | Equipment Name | Category | Location | Service Start Date | Acquisition Cost | Expected Lifespan (Years) | Current Replacement Estimate | Risk Category (High/Medium/Low)
EQ-001 | HVAC Chiller No. 1 | HVAC | Mechanical Room A | 2014-04-01 | ¥12,000,000 | 15 | ¥15,800,000 | उच्च
EQ-002 | Power Substation | Electrical | Electrical Room | 2011-09-15 | ¥28,000,000 | 20 | ¥35,000,000 | उच्च
EQ-003 | Water Supply Pump | Plumbing | Pump Room | 2018-02-01 | ¥4,200,000 | 12 | ¥5,500,000 | मध्यम

## Repair Records
Repair Records
Excel template for facility management equipment repair replace lcc template.
Repair ID | Repair Date | Equipment ID | Equipment Name | Repair Description | Repair Cost | Downtime Hours | Downtime Loss | Recurrence Flag (Yes/No) | Contractor
R-0001 | 2023-04-12 | EQ-001 |  | Refrigerant leak repair & pressure adjustment | ¥850,000 | 6.0 | ¥420,000 | Yes | Yamada Equipment
R-0002 | 2023-06-07 | EQ-008 |  | Agitator motor replacement | ¥1,250,000 | 10.0 | ¥900,000 | Yes | Environmental Facility
R-0003 | 2023-09-18 | EQ-003 |  | Mechanical seal replacement | ¥310,000 | 2.5 | ¥120,000 | No | Suiken Service

## LCC Calculation
LCC Calculation
Excel template for facility management equipment repair replace lcc template.
Item | Repair Option: Nominal Amount | Repair Option: Present Value (PV) | Replacement Option: Nominal Amount | Replacement Option: Present Value (PV) | टीप | Dropdown Options | LCC Present Value
Initial Investment (Replacement Cost) | ¥0 |  |  |  | Replacement option counts current replacement estimate as initial investment | Repair Option
Annual Maintenance & Repair Cost |  |  |  |  | Estimated based on annual average of past repair costs | Replacement Option
Annual Energy Cost | ¥1,200,000 |  | ¥900,000 |  | Replacement option assumes lower running costs due to energy savings

## Decision Matrix
Decision Matrix
Excel template for facility management equipment repair replace lcc template.
Equipment ID | Equipment Name | Lifespan Elapsed Rate | Repair Ratio | Risk Score | Assessment Indicators | Recommendation Status | Manager Recommendation Note

## प्रसंग विश्लेषण
प्रसंग विश्लेषण
Excel template for facility management equipment repair replace lcc template.
परिस्थिती | Discount Rate | Inflation Rate | Energy Price Growth Rate | Repair Option PV | Replacement Option PV | सुचवलेली कृती
Base Case
Low Interest Rate | 1.5%
High Interest Rate | 6.0%

## Approval Tracking
Approval Tracking
Excel template for facility management equipment repair replace lcc template.
Equipment ID | Approval Status (Not Requested/Pending/Approved) | Approval Date | Order Amount | Scheduled Work Date | Completion Verifier
EQ-001 | Pending |  | ¥15,800,000 | 2026-08-20
EQ-008 | Not Requested |  | ¥22,000,000
EQ-002 | कार्य माहिती | 2026-05-30 | ¥35,000,000 | 2026-09-15 | Sato

## Data Dictionary & Formulas
Data Dictionary & Formulas
Excel template for facility management equipment repair replace lcc template.
Term / Item | Definition / Meaning | Key Formulas | Sheets Used | Input / Calculated
LCC | Life Cycle Cost. The total cost including initial investment, maintenance, energy, downtime loss, and residual/dismantling value. | Total LCC = Initial Investment PV + Annual Cost PV + Residual Value/Dismantling Cost PV | LCC Calculation | Calculated
PV（Present Value） | The value of future costs converted to present value using the discount rate. | '=Future_Cost/(1+Discount Rate)^Years | LCC Calculation | Calculated
NPV | Net Present Value. The sum of the present values of future cash flows. The Excel function discounts end-of-period amounts. | '=NPV(Discount Rate, Year1_Cost:YearN_Cost)+Initial_Investment | LCC Calculation | Calculated