## Vue d ensemble du plan de maint
Modele de journal de plan de maintenance
Suivez ensemble les plans de maintenance, les reparations et les enregistrements de travail.
Total | Remarques | Business Scenario | En attente | Key Fields | Suggested Maintenance Type | Ouvert | Column8
Termine | Maintain company or project, location, owner, status, and scenario dropdowns in Settings. | Office Buildings / Facilities | Termine | Location, asset category, owner, and status | Recurring service, inspection, and safety check | En cours | Suitable for multi-floor or multi-building management
2. Build the asset register | Register asset number, location, category, criticality, default cycle, and owner in Asset Register. | Industrial Plant | Production lines, pumps, compressors, and distribution cabinets | Asset number, maintenance cycle, downtime requirement, and parts | Preventive maintenance, lubrication, and annual overhaul | En attente | Can be filtered by line or shift team
Visibilite operationnelle | Record plans by asset, location, cycle, owner, planned date, completion status, and delay reason in Maintenance Plan. | Retail / Stores | Refrigerators, POS equipment, lighting, and access control | Company or Project、Location、Priority、Related Work Order | Inspection, breakdown repair, and corrective recheck | Note | Suitable for copying by area

## Journal
Journal
Suivez ensemble les plans de maintenance, les reparations et les enregistrements de travail.
Metric | 2026-01-08 | Test de fonctionnement du generateur | Responsable 4 | 2026-01-10 | Ligne d exemple. Remplacez cette ligne par des donnees reelles et verifiez chaque matin le responsable, l echeance et le statut. Test de fonctionnement du generateur/Termine/#4 | Open Count | Maintenance Cycle | Plan Count
Total Plans | 24 | Maintenance de l ascenseur | Responsable 1 | 24 | Ligne d exemple. Remplacez cette ligne par des donnees reelles et verifiez chaque matin le responsable, l echeance et le statut. Maintenance de l ascenseur/Ouvert/#5 |  | Daily
Completed | 18 | Controle du tableau electrique | Responsable 2 | 18 | Ligne d exemple. Remplacez cette ligne par des donnees reelles et verifiez chaque matin le responsable, l echeance et le statut. Controle du tableau electrique/En cours/#6 |  | Weekly
Overdue | 3 | Controle periodique CVC | Responsable 3 | 3 | Ligne d exemple. Remplacez cette ligne par des donnees reelles et verifiez chaque matin le responsable, l echeance et le statut. Controle periodique CVC/En attente/#7 |  | Monthly

## Referentiel
Referentiel
Suivez ensemble les plans de maintenance, les reparations et les enregistrements de travail.
MA-03 | Inspection de la pompe | Visite | Inspection de la pompe - fr 3 | Asset or Facility Name | Asset Category | Maintenance Type | Maintenance Cycle | Planned Date | Due Date | Owner | Priority | Estimated Hours | Estimated Cost | Required Materials or Parts | Safety or Downtime Requirement | Status | Completion Date | Delay Days | Progress Judgment | Delay or Open Reason | Next Planned Date | Related Work Order or Record | Business Scenario | Remarques
MP-0001 | Test de fonctionnement du generateur | Reunion | Test de fonctionnement du generateur - fr 4 | HVAC Unit | HVAC | Recurring Service | Monthly | 2026-05-05 | 2026-05-06 | Alex Carter | High | 2.0 | 300.00 | Filters and cleaner | Requires 30 minutes of downtime | Pending | [5 empty] | WO-2026-001 | Office Building | Example: monthly HVAC service
MP-0002 | Maintenance de l ascenseur | Telephone | Maintenance de l ascenseur - fr 5 | Exhaust Fan Service | HVAC | Preventive Maintenance | Monthly | 2026-05-05 | 2026-05-05 | Morgan Lee | Medium | 1.5 | 120.00 | Belt and lubricant | Work at height requires approval | Planned | [5 empty] | WO-2026-002 | Retail | Expanded from page input example
MP-0003 | Controle du tableau electrique | E-mail | Controle du tableau electrique - fr 6 | Low-voltage Distribution Cabinet | Electrical / Distribution | Safety Check | Quarterly | 2026-04-28 | 2026-04-30 | Jordan Patel | Urgent | 3.0 | 0.00 | Infrared thermometer | Requires lockout tagout | Delayed |  |  |  | Waiting for power shutdown window |  | WO-2026-003 | Industrial Plant | Example: overdue or delay review

## Flux
Flux
Suivez ensemble les plans de maintenance, les reparations et les enregistrements de travail.
3 | Responsable | Element prioritaire | Decider la prochaine action | Within 30 min | Asset or Facility Name | Maintenance Result | Actual Work Performed | Replaced Parts or Materials | Actual Hours | Actual Cost | Downtime Hours | Recheck Needed | Recheck Date | Findings | Follow-up Action | Attachment or Photo Link | Remarques
EXE-0001 | MP-0004 | Work result | Update the log | Within 5 min | Fire Pump | Normal | Completed fire pump start test, pressure check, and control cabinet indicator inspection. | None | 1.0 | 0.00 | 0.0 | No |  | No finding | Continue weekly inspection |  | Example
EXE-0002 | MP-0001 | 2026-05-07 | Verifier le lendemain | HVAC-001
EXE-0003 | MP-0002 | 2026-05-08 | Examiner les ameliorations | FAN-ROOF-02

## Guide
Guide
Suivez ensemble les plans de maintenance, les reparations et les enregistrements de travail.
Watch out | Ne terminez pas avec des champs vides. | Cela rend le suivi ulterieur difficile. | Remplissez toujours le statut. | Asset Category | Brand or Model | Serial No. | Start Date | Warranty Expiry | Warranty Days Remaining | Criticality | Asset Status | Default Maintenance Type | Default Maintenance Cycle | Default Owner | Risk or Compliance Notes | Remarques
Cadence de revue | La revue quotidienne ou hebdomadaire est la valeur par defaut. | Cela evite les informations obsoletes. | Fixez l heure du controle. | HVAC | Carrier 30RB | SN-HVAC-001 | 2021-06-01 | 2027-05-31 |  | High | In Service | Recurring Service | Monthly | Alex Carter | Filters, condensate, and belts need regular checks | Example
Sharing | Alignez le dernier etat avant la passation de poste. | Cela evite les malentendus. | Update status before sharing. | Electrical / Distribution | Schneider | SN-EL-002 | 2020-09-15 | 2026-09-14 |  | Urgent | In Service | Safety Check | Quarterly | Jordan Patel | Requires power shutdown and lockout tagout | Example
Impression | Il peut aussi etre utilise en deplacement. | Moins de colonnes visibles ameliorent la lisibilite. | Masquez les colonnes inutiles. | Fire Safety | Grundfos | SN-FP-001 | 2019-03-20 | 2025-03-19 |  | Urgent | In Service | Inspection | Weekly | Facilities Supervisor | Fire linkage must be fully recorded | Example

## Revue des retards
Revue des retards
Suivez ensemble les plans de maintenance, les reparations et les enregistrements de travail.
N° de revue | N° de plan | Actif / installation | Motif du retard | Cause racine | Impact | Responsable | Action de reprise | Date cible | Statut | Notes
DR-0001 | MP-0003 | Low-voltage Distribution Cabinet | Waiting for power shutdown window | Production shutdown window moved | Quarterly electrical safety check delayed by two days | Jordan Patel | Confirm the shutdown slot and prepare the lockout checklist | 2026-05-02 | Open | Review in the daily maintenance meeting
DR-0002 | MP-0002 | Roof Exhaust Fan | Parts delivery rescheduled | Supplier shipping delay | Preventive maintenance remains planned but the spare belt is not on site | Morgan Lee | Reserve an alternate belt and update the vendor ETA | 2026-05-06 | Monitoring | Keep the maintenance window visible to operations
DR-0003 | MP-0001 | Air Handling Unit | Access permit pending | Tenant access approval has not returned | Filter check may move outside the weekly cycle | Alex Carter | Call the tenant contact and prepare the mobile kit | 2026-05-04 | Recovered | Recovered before the next weekly plan lock

## Paramètres
Paramètres
Suivez ensemble les plans de maintenance, les reparations et les enregistrements de travail.
Groupe | Paramètre | Valeur affichée | Code | Ordre | Actif | Notes
Status | Maintenance plan status | Planned | planned | 1 | Yes | Default status for new maintenance plans
Priority | Maintenance priority | Urgent | urgent | 1 | Yes | Use for safety or service-impacting maintenance
Maintenance Cycle | Recurring cycle | Monthly | monthly | 3 | Yes | Common cycle for mechanical assets