## Guide
Predložak dnevnika plana održavanja
Track maintenance plans, repairs, work records together.
Steps | Bilješke | Business Scenario | Applicable Assets | Key Fields | Suggested Maintenance Type | Risk Note | Remarks
1. Configure settings | Održavajte padajuće izbornike tvrtke ili projekta, lokacije, vlasnika, statusa i scenarija u Postavkama. | Office Buildings / Facilities | HVAC, dizala, vodovod, protupožarna zaštita i sigurnost | Lokacija, kategorija imovine, vlasnik i status | Periodični servis, inspekcija i sigurnosna provjera | Zakašnjele stavke utječu na sigurnost i iskustvo korisnika | Suitable for multi-floor or multi-building management
2. Izradite registar imovine | Registrirajte broj imovine, lokaciju, kategoriju, kritičnost, zadani ciklus i vlasnika u Registru imovine. | Industrial Plant | Proizvodne linije, pumpe, kompresori i razvodni ormari | Broj imovine, ciklus održavanja, zahtjev za zastojem i dijelovi | Preventivno održavanje, podmazivanje i godišnji remont | Zahtijeva koordinaciju razdoblja zastoja i zaliha dijelova | Can be filtered by line or shift team
3. Enter maintenance plans | Zabilježite planove prema imovini, lokaciji, ciklusu, izvršitelju, planiranom datumu, statusu dovršenosti i razlogu kašnjenja u Planu održavanja. | Retail / Stores | Hladnjaci, POS oprema, rasvjeta i kontrola pristupa | Tvrtka ili projekt, lokacija, prioritet, povezani radni nalog | Inspekcija, popravak kvara i korektivna ponovna provjera | Dijeljenje između trgovina i obavijesti su važniji | Suitable for copying by area

## Nadzorna ploča
Nadzorna ploča
Track maintenance plans, repairs, work records together.
Metric | Value | Bilješke | Status | Broj | Prioritet | Open Count | Maintenance Cycle | Plan Count
Total Plans | 24 | Zapisi s generiranim brojevima planova | Planirano | 24 | Hitno |  | Dnevno
Completed | 18 | Status is completed | Pending | 18 | Visok |  | Tjedno
Kašnjenje | 3 | Open items whose due date is before today | U tijeku | 3 | Srednji |  | Mjesečno

## Plan održavanja
Plan održavanja
Track maintenance plans, repairs, work records together.
Plan No. | Company or Project | Location or Area | Asset No. | Asset or Facility Name | Asset Category | Vrsta održavanja | Maintenance Cycle | Planirani datum | Rok | Izvršitelj | Prioritet | Estimated Hours | Procijenjeni trošak | Required Materials or Parts | Safety or Downtime Requirement | Status | Datum završetka | Delay Days | Progress Judgment | Delay or Open Reason | Next Planned Date | Related Work Order or Record | Business Scenario | Remarks
MP-0001 | Headquarters Campus | HVAC Plant Room | HVAC-001 | HVAC Unit | HVAC | Recurring Service | Mjesečno | 2026-05-05 | 2026-05-06 | Alex Carter | Visok | 2.0 | 300.00 | Filtri i sredstvo za čišćenje | Requires 30 minutes of downtime | Pending | [5 empty] | WO-2026-001 | Office Building | Example: monthly HVAC service
MP-0002 | Commercial Complex | Roof | FAN-ROOF-02 | Exhaust Fan Service | HVAC | Preventive Maintenance | Mjesečno | 2026-05-05 | 2026-05-05 | Morgan Lee | Srednji | 1.5 | 120.00 | Remen i mazivo | Work at height requires approval | Planirano | [5 empty] | WO-2026-002 | Retail | Prošireno iz primjera unosa na stranici
MP-0003 | East China Plant | Electrical Room | ELEC-DB-02 | Low-voltage Distribution Cabinet | Electrical / Distribution | Safety Check | Tromjesečno | 2026-04-28 | 2026-04-30 | Jordan Patel | Hitno | 3.0 | 0.00 | Infrared thermometer | Requires lockout tagout | Delayed |  |  |  | Waiting for power shutdown window |  | WO-2026-003 | Industrial Plant | Example: overdue or delay review

## Execution Log
Execution Log
Track maintenance plans, repairs, work records together.
Record No. | Plan No. | Execution Date | Performer | Asset No. | Asset or Facility Name | Maintenance Result | Actual Work Performed | Replaced Parts or Materials | Actual Hours | Stvarni trošak | Downtime Hours | Recheck Needed | Recheck Date | Nalazi | Follow-up Action | Attachment or Photo Link | Remarks
EXE-0001 | MP-0004 | 2026-05-02 | Facilities Supervisor | FIRE-PUMP-01 | Fire Pump | Normalno | Dovršen test pokretanja protupožarne pumpe, provjera tlaka i inspekcija indikatora upravljačkog ormara. | None | 1.0 | 0.00 | 0.0 | Ne |  | No finding | Continue weekly inspection |  | Example
EXE-0002 | MP-0001 | 2026-05-07 | Performer | HVAC-001
EXE-0003 | MP-0002 | 2026-05-08 | Performer | FAN-ROOF-02

## Asset Register
Asset Register
Track maintenance plans, repairs, work records together.
Asset No. | Company or Project | Location or Area | Asset or Facility Name | Asset Category | Brand or Model | Serial No. | Start Date | Warranty Expiry | Warranty Days Remaining | Criticality | Asset Status | Default Maintenance Type | Default Maintenance Cycle | Default Owner | Risk or Compliance Notes | Remarks
HVAC-001 | Headquarters Campus | HVAC Plant Room | HVAC Unit | HVAC | Carrier 30RB | SN-HVAC-001 | 2021-06-01 | 2027-05-31 |  | Visok | In Service | Recurring Service | Mjesečno | Alex Carter | Filtri, kondenzat i remeni trebaju redovite provjere | Example
ELEC-DB-02 | East China Plant | Electrical Room | Low-voltage Distribution Cabinet | Electrical / Distribution | Schneider | SN-EL-002 | 2020-09-15 | 2026-09-14 |  | Hitno | In Service | Safety Check | Tromjesečno | Jordan Patel | Zahtijeva isključivanje napajanja i zaključavanje/označavanje (LOTO) | Example
FIRE-PUMP-01 | Commercial Complex | Fire Pump Room | Fire Pump | Fire Protection | Grundfos | SN-FP-001 | 2019-03-20 | 2025-03-19 |  | Hitno | In Service | Inspection | Tjedno | Facilities Supervisor | Fire linkage must be fully recorded | Example

## Delay Review
Delay Review
Track maintenance plans, repairs, work records together.
Review No. | Plan No. | Asset / Facility Name | Delay Reason | Root Cause | Impact | Owner | Recovery Action | Target Date | Status | Notes
DR-0001 | MP-0003 | Low-voltage Distribution Cabinet | Waiting for power shutdown window | Production shutdown window moved | Quarterly electrical safety check delayed by two days | Jordan Patel | Confirm the shutdown slot and prepare the lockout checklist | 2026-05-02 | Open | Review in the daily maintenance meeting
DR-0002 | MP-0002 | Roof Exhaust Fan | Parts delivery rescheduled | Supplier shipping delay | Preventive maintenance remains planned but the spare belt is not on site | Morgan Lee | Reserve an alternate belt and update the vendor ETA | 2026-05-06 | Monitoring | Keep the maintenance window visible to operations
DR-0003 | MP-0001 | Air Handling Unit | Access permit pending | Tenant access approval has not returned | Filter check may move outside the weekly cycle | Alex Carter | Call the tenant contact and prepare the mobile kit | 2026-05-04 | Recovered | Recovered before the next weekly plan lock

## Settings
Settings
Track maintenance plans, repairs, work records together.
Setting Group | Setting Key | Display Value | Code | Sort Order | Active | Notes
Status | Maintenance plan status | Planned | planned | 1 | Yes | Default status for new maintenance plans
Priority | Maintenance priority | Urgent | urgent | 1 | Yes | Use for safety or service-impacting maintenance
Maintenance Cycle | Recurring cycle | Monthly | monthly | 3 | Yes | Common cycle for mechanical assets