## Guide
Maintenance Plan Log Template (General Version)
Track maintenance plans, repair history, work records, and parts replacement in one workbook.
Steps | Notes | Business Scenario | Applicable Assets | Key Fields | Suggested Maintenance Type | Risk Note | Remarks
1. Configure settings | Maintain company or project, location, owner, status, and scenario dropdowns in Settings. | Office Buildings / Facilities | HVAC, elevators, plumbing, fire protection, and security | Location, asset category, owner, and status | Recurring service, inspection, and safety check | Overdue items affect safety and customer experience | Suitable for multi-floor or multi-building management
2. Build the asset register | Register asset number, location, category, criticality, default cycle, and owner in Asset Register. | Industrial Plant | Production lines, pumps, compressors, and distribution cabinets | Asset number, maintenance cycle, downtime requirement, and parts | Preventive maintenance, lubrication, and annual overhaul | Requires coordination of downtime windows and parts inventory | Can be filtered by line or shift team
3. Enter maintenance plans | Record plans by asset, location, cycle, owner, planned date, completion status, and delay reason in Maintenance Plan. | Retail / Stores | Refrigerators, POS equipment, lighting, and access control | Company or project, location, priority, and related work order | Inspection, breakdown repair, and corrective recheck | Cross-store sharing and notifications are more important | Suitable for copying by area

## Dashboard
Dashboard
Track maintenance plans, repair history, work records, and parts replacement in one workbook.
Metric | Value | Notes | Status | Count | Priority | Open Count | Maintenance Cycle | Plan Count
Total Plans | 24 | Records with generated plan numbers | Planned | 24 | Urgent |  | Daily
Completed | 18 | Status is completed | Pending | 18 | High |  | Weekly
Overdue | 3 | Open items whose due date is before today | In Progress | 3 | Medium |  | Monthly

## Maintenance Plan
Maintenance Plan
Track maintenance plans, repair history, work records, and parts replacement in one workbook.
Plan No. | Company or Project | Location or Area | Asset No. | Asset or Facility Name | Asset Category | Maintenance Type | Maintenance Cycle | Planned Date | Due Date | Owner | Priority | Estimated Hours | Estimated Cost | Required Materials or Parts | Safety or Downtime Requirement | Status | Completion Date | Delay Days | Progress Judgment | Delay or Open Reason | Next Planned Date | Related Work Order or Record | Business Scenario | Remarks
MP-0001 | Headquarters Campus | HVAC Plant Room | HVAC-001 | HVAC Unit | HVAC | Recurring Service | Monthly | 2026-05-05 | 2026-05-06 | Alex Carter | High | 2.0 | 300.00 | Filters and cleaner | Requires 30 minutes of downtime | Pending | [5 empty] | WO-2026-001 | Office Building | Example: monthly HVAC service
MP-0002 | Commercial Complex | Roof | FAN-ROOF-02 | Exhaust Fan Service | HVAC | Preventive Maintenance | Monthly | 2026-05-05 | 2026-05-05 | Morgan Lee | Medium | 1.5 | 120.00 | Belt and lubricant | Work at height requires approval | Planned | [5 empty] | WO-2026-002 | Retail | Expanded from page input example
MP-0003 | East China Plant | Electrical Room | ELEC-DB-02 | Low-voltage Distribution Cabinet | Electrical / Distribution | Safety Check | Quarterly | 2026-04-28 | 2026-04-30 | Jordan Patel | Urgent | 3.0 | 0.00 | Infrared thermometer | Requires lockout tagout | Delayed |  |  |  | Waiting for power shutdown window |  | WO-2026-003 | Industrial Plant | Example: overdue or delay review

## Execution Log
Execution Log
Track maintenance plans, repair history, work records, and parts replacement in one workbook.
Record No. | Plan No. | Execution Date | Performer | Asset No. | Asset or Facility Name | Maintenance Result | Actual Work Performed | Replaced Parts or Materials | Actual Hours | Actual Cost | Downtime Hours | Recheck Needed | Recheck Date | Findings | Follow-up Action | Attachment or Photo Link | Remarks
EXE-0001 | MP-0004 | 2026-05-02 | Facilities Supervisor | FIRE-PUMP-01 | Fire Pump | Normal | Completed fire pump start test, pressure check, and control cabinet indicator inspection. | None | 1.0 | 0.00 | 0.0 | No |  | No finding | Continue weekly inspection |  | Example
EXE-0002 | MP-0001 | 2026-05-07 | HVAC Technician | HVAC-001
EXE-0003 | MP-0002 | 2026-05-08 | Maintenance Vendor | FAN-ROOF-02

## Asset Register
Asset Register
Track maintenance plans, repair history, work records, and parts replacement in one workbook.
Asset No. | Company or Project | Location or Area | Asset or Facility Name | Asset Category | Brand or Model | Serial No. | Start Date | Warranty Expiry | Warranty Days Remaining | Criticality | Asset Status | Default Maintenance Type | Default Maintenance Cycle | Default Owner | Risk or Compliance Notes | Remarks
HVAC-001 | Headquarters Campus | HVAC Plant Room | HVAC Unit | HVAC | Carrier 30RB | SN-HVAC-001 | 2021-06-01 | 2027-05-31 |  | High | In Service | Recurring Service | Monthly | Alex Carter | Filters, condensate, and belts need regular checks | Example
ELEC-DB-02 | East China Plant | Electrical Room | Low-voltage Distribution Cabinet | Electrical / Distribution | Schneider | SN-EL-002 | 2020-09-15 | 2026-09-14 |  | Urgent | In Service | Safety Check | Quarterly | Jordan Patel | Requires power shutdown and lockout tagout | Example
FIRE-PUMP-01 | Commercial Complex | Fire Pump Room | Fire Pump | Fire Protection | Grundfos | SN-FP-001 | 2019-03-20 | 2025-03-19 |  | Urgent | In Service | Inspection | Weekly | Facilities Supervisor | Fire linkage must be fully recorded | Example

## Delay Review
Delay Review
Track maintenance plans, repair history, work records, and parts replacement in one workbook.
Review No. | Plan No. | Asset / Facility Name | Delay Reason | Root Cause | Impact | Owner | Recovery Action | Target Date | Status | Notes
DR-0001 | MP-0003 | Low-voltage Distribution Cabinet | Waiting for power shutdown window | Production shutdown window moved | Quarterly electrical safety check delayed by two days | Jordan Patel | Confirm the shutdown slot and prepare the lockout checklist | 2026-05-02 | Open | Review in the daily maintenance meeting
DR-0002 | MP-0002 | Roof Exhaust Fan | Parts delivery rescheduled | Supplier shipping delay | Preventive maintenance remains planned but the spare belt is not on site | Morgan Lee | Reserve an alternate belt and update the vendor ETA | 2026-05-06 | Monitoring | Keep the maintenance window visible to operations
DR-0003 | MP-0001 | Air Handling Unit | Access permit pending | Tenant access approval has not returned | Filter check may move outside the weekly cycle | Alex Carter | Call the tenant contact and prepare the mobile kit | 2026-05-04 | Recovered | Recovered before the next weekly plan lock

## Settings
Settings
Track maintenance plans, repair history, work records, and parts replacement in one workbook.
Setting Group | Setting Key | Display Value | Code | Sort Order | Active | Notes
Status | Maintenance plan status | Planned | planned | 1 | Yes | Default status for new maintenance plans
Priority | Maintenance priority | Urgent | urgent | 1 | Yes | Use for safety or service-impacting maintenance
Maintenance Cycle | Recurring cycle | Monthly | monthly | 3 | Yes | Common cycle for mechanical assets