## Инструкции (instructions)
Forestry Forest Road Inspection Log Template
Excel template for forestry forest road inspection log template.
Стъпка | Управление | Target Sheet | Input & Review Details | Бележка
Стъпка 1 | Maintain Road Register | Road Register | Регистрирайте имената на управляваните пътища, участъците (начална/крайна точка), дължината (km) и отговорното лице. | Road ID служи като ключ за търсене в дневника за инспекция.
Стъпка 2 | Enter Inspection Results | Inspection & Repair Log | Въведете аномалии по повърхността, канавките, откосите и др., както и тежестта (Няма, Незначителна, Умерена, Критична). | Keep Emergency Flag unified as Yes/No.
Стъпка 3 | Dashboard Monitoring | Дашборд | Проверете броя на чакащите ремонти, особено зоните, маркирани за авариен отговор. | Identify priority routes using bar charts.

## Табло за управление (dashboard)
Табло за управление (dashboard)
Excel template for forestry forest road inspection log template.
Road ID | Road Name | Inspection Count | Pending Issues | Emergency Actions | Condition Assessment

## Road Register (roads)
Road Register (roads)
Excel template for forestry forest road inspection log template.
Road ID | Road Name | Start Point | End Point | Total Length (km) | Road Class | Department / Person in Charge
RD-01 | Ohira Daiichi Road | 0.0km (National Highway Junction) | 5.2km (National Forest Boundary) | 5.2 | Forest Road (Class 1) | Forest Conservation Division
RD-02 | Kuromori Work Road | 0.0km (Ohira Road Junction) | 1.8km (Plantation Area A) | 1.8 | Work Path (Single Lane) | Extraction Crew
RD-03 | Tanigawa Route | 0.0km (Road Start Marker) | 3.4km (Log Landing B) | 3.4 | Forest Road (Class 2) | Forestry Management Crew

## Inspection & Repair Log (inspec
Inspection & Repair Log (inspec
Excel template for forestry forest road inspection log template.
Поредност | Дата на проверка | Road ID | Road Name | Station/Location (km) | Inspection Category | Damage Level | Anomaly Details / Status | Recommended Repair Method | Emergency Flag | Repair Status | Repair Execution Date | Управление | Final Verifier
1 | 2026-06-01 | RD-01 |  | 0.8 | Road Surface | Незначително | Rutting observed. Puddles form after rain. | Gravel grading & compaction | Не | Продължаване на наблюдението |  | Check progress during next patrol | Yamamoto
2 | 2026-06-02 | RD-01 |  | 2.4 | Drainage Facility (Ditch/Culvert) | Средна | Sediment accumulation in ditch. Signs of overflow onto road. | Ditch dredging & culvert inlet cleaning | Не | В процес | 2026-06-08 | Partially dredged; continuing remaining section | Sato
3 | 2026-06-03 | RD-02 |  | 1.1 | Slope / Cut Slope | Тежка | Minor collapse on cut slope. Soil spill onto road shoulder. | Soil removal, slope curing, traffic restriction | Да | Не е започнато |  | Arrange repairs immediately | Tanaka

## Настройки
Настройки
Excel template for forestry forest road inspection log template.
Damage Level | Inspection Category | Repair Status | Emergency Flag
Няма | Road Surface | Не е започнато | Да
Незначително | Drainage Facility (Ditch/Culvert) | В процес | Не
Средна | Slope / Cut Slope | Приключено