## Instrucțiuni (instructions)
Forestry Forest Road Inspection Log Template
Excel template for forestry forest road inspection log template.
Pas | Controale | Target Sheet | Input & Review Details | Notă
Pasul 1 | Maintain Road Register | Road Register | Register managed road names, sections (start/end points), length (km), and person in charge. | Road ID acts as the lookup key for the inspection log.
Pasul 2 | Enter Inspection Results | Inspection & Repair Log | Enter anomalies on surfaces, ditches, slopes, etc., and severity (None, Minor, Moderate, Critical). | Keep Emergency Flag unified as Yes/No.
Pasul 3 | Dashboard Monitoring | Tablou de bord | Check the number of pending repairs, especially areas flagged for emergency response. | Identify priority routes using bar charts.

## Tablou de bord (dashboard)
Tablou de bord (dashboard)
Excel template for forestry forest road inspection log template.
Road ID | Road Name | Inspection Count | Pending Issues | Emergency Actions | Condition Assessment

## Road Register (roads)
Road Register (roads)
Excel template for forestry forest road inspection log template.
Road ID | Road Name | Start Point | End Point | Total Length (km) | Road Class | Department / Person in Charge
RD-01 | Ohira Daiichi Road | 0.0km (National Highway Junction) | 5.2km (National Forest Boundary) | 5.2 | Forest Road (Class 1) | Forest Conservation Division
RD-02 | Kuromori Work Road | 0.0km (Ohira Road Junction) | 1.8km (Plantation Area A) | 1.8 | Work Path (Single Lane) | Extraction Crew
RD-03 | Tanigawa Route | 0.0km (Road Start Marker) | 3.4km (Log Landing B) | 3.4 | Forest Road (Class 2) | Forestry Management Crew

## Inspection & Repair Log (inspec
Inspection & Repair Log (inspec
Excel template for forestry forest road inspection log template.
Element | Data verificării | Road ID | Road Name | Station/Location (km) | Inspection Category | Damage Level | Anomaly Details / Status | Recommended Repair Method | Emergency Flag | Repair Status | Repair Execution Date | Detalii | Final Verifier
1 | 2026-06-01 | RD-01 |  | 0.8 | Road Surface | Minoră | Rutting observed. Puddles form after rain. | Gravel grading & compaction | Nu | Monitorizare continuă |  | Check progress during next patrol | Inregistrare MOV-2026-0005 Element
2 | 2026-06-02 | RD-01 |  | 2.4 | Drainage Facility (Ditch/Culvert) | Mid-size | Sediment accumulation in ditch. Signs of overflow onto road. | Ditch dredging & culvert inlet cleaning | Nu | Se proceseaza | 2026-06-08 | Partially dredged; continuing remaining section | Alex Chen
3 | 2026-06-03 | RD-02 |  | 1.1 | Slope / Cut Slope | Severe | Minor collapse on cut slope. Soil spill onto road shoulder. | Soil removal, slope curing, traffic restriction | Da | În așteptare |  | Arrange repairs immediately | Chris Zhao

## Setări
Setări
Excel template for forestry forest road inspection log template.
Damage Level | Inspection Category | Repair Status | Emergency Flag
Niciunul | Road Surface | În așteptare | Da
Minoră | Drainage Facility (Ditch/Culvert) | Se proceseaza | Nu
Mid-size | Slope / Cut Slope | Finalizat