## 使用說明 (instructions)
Forestry Forest Road Inspection Log Template
Excel template for forestry forest road inspection log template.
環節 | 控制 | 目標工作表 | 输入/确认内容 | 注意
步驟1 | Maintain Road Register | Road Register | Register managed road names, sections (start/end points), length (km), and person in charge. | Road ID acts as the lookup key for the inspection log.
步驟 2 | Enter Inspection Results | Inspection & Repair Log | Enter anomalies on surfaces, ditches, slopes, etc., and severity (None, Minor, Moderate, Critical). | Keep Emergency Flag unified as Yes/No.
步驟 3 | 看板可視化監控 | 狀況看板 | Check the number of pending repairs, especially areas flagged for emergency response. | Identify priority routes using bar charts.

## 儀表板 (dashboard)
儀表板 (dashboard)
Excel template for forestry forest road inspection log template.
Road ID | Road Name | 點檢次數 | 未處理糾正件數 | Emergency Actions | 狀態評估

## Road Register (roads)
Road Register (roads)
Excel template for forestry forest road inspection log template.
Road ID | Road Name | Start Point | End Point | Total Length (km) | Road Class | Department / Person in Charge
RD-01 | Ohira Daiichi Road | 0.0km (National Highway Junction) | 5.2km (National Forest Boundary) | 5.2 | Forest Road (Class 1) | Forest Conservation Division
RD-02 | Kuromori Work Road | 0.0km (Ohira Road Junction) | 1.8km (Plantation Area A) | 1.8 | Work Path (Single Lane) | Extraction Crew
RD-03 | Tanigawa Route | 0.0km (Road Start Marker) | 3.4km (Log Landing B) | 3.4 | Forest Road (Class 2) | Forestry Management Crew

## Inspection & Repair Log (inspec
Inspection & Repair Log (inspec
Excel template for forestry forest road inspection log template.
序號 | 檢查日期 | Road ID | Road Name | Station/Location (km) | 點檢類別 | Damage Level | Anomaly Details / Status | Recommended Repair Method | Emergency Flag | 處理狀況 | Repair Execution Date | 詳情 | Final Verifier
1 | 2026-06-01 | RD-01 |  | 0.8 | Road Surface | Minor/輕微 | Rutting observed. Puddles form after rain. | Gravel grading & compaction | 否 | 観察継続 |  | Check progress during next patrol | 王五
2 | 2026-06-02 | RD-01 |  | 2.4 | Drainage Facility (Ditch/Culvert) | 中型 | Sediment accumulation in ditch. Signs of overflow onto road. | Ditch dredging & culvert inlet cleaning | 否 | 處理中 | 2026-06-08 | Partially dredged; continuing remaining section | 張三
3 | 2026-06-03 | RD-02 |  | 1.1 | Slope / Cut Slope | 嚴重 | Minor collapse on cut slope. Soil spill onto road shoulder. | Soil removal, slope curing, traffic restriction | 是 | 待處理 |  | Arrange repairs immediately | 趙六

## Settings & Master (settings)
Settings & Master (settings)
Excel template for forestry forest road inspection log template.
Damage Level | 點檢類別 | 處理狀況 | Emergency Flag
無 | Road Surface | 待處理 | 是
Minor/輕微 | Drainage Facility (Ditch/Culvert) | 處理中 | 否
中型 | Slope / Cut Slope | 已完成