## Instrukcje
Rejestr wyciągniętych wniosków
Szablon Excel do zarządzania wyciągniętymi wnioskami (lessons learned), analizą przyczyn źródłowych i działaniami zapobiegawczymi.
Input Cells | Manual input fields. Record lesson details, countermeasures, remarks, etc.
Formula Cells (Auto-calculation) | Automatically calculated fields such as KPIs, aggregates, or VLOOKUP formulas.
Dropdown (Selection) Cells | Dropdown lists to select category, impact level, status, owner, etc.
Operational Guidelines: Do not let lessons learned end as "individual reflection." Record the cause, countermeasures, and deployment status, and reflect them in future project plans, review checklists, and standard operating procedures (SOPs).

## Dashboard
Dashboard
Szablon Excel do zarządzania wyciągniętymi wnioskami (lessons learned), analizą przyczyn źródłowych i działaniami zapobiegawczymi.
Category | Not Addressed | In Progress | Completed | SOP/Standardization in Progress | Archived | Total
Technology & Infrastructure
Business Process
Communication

## Rejestr wniosków
Rejestr wniosków
Szablon Excel do zarządzania wyciągniętymi wnioskami (lessons learned), analizą przyczyn źródłowych i działaniami zapobiegawczymi.
Lesson ID | Title | Project Name | Category | Impact Level | Status | Submitter | Occurrence Date | Lesson Details | Preventative Action Summary | Remarks
LES-001 | Rework due to design review omissions | System Migration Project | Business Process | High | SOP/Standardization in Progress | Member 1 | 2026-04-05 | Failed to confirm external integration conditions during design review, resulting in design changes in later phases. | Add confirmation items for external integration and scope of migration to the design review checklist, requiring PM approval. | Verify at the next gate review
LES-002 | Insufficient pre-validation of production data migration procedures | System Migration Project | Technology & Infrastructure | High | In Progress | Member 2 | 2026-04-12 | Due to a limited dry run volume, processing delays caused by exceptional data were not detected beforehand. | Standardize dry run criteria using production-equivalent data and validation procedures for exceptional data. | To be reflected in the migration plan
LES-003 | Mismatch in customer approval criteria expectations | New Service Implementation | Communication | Medium | Completed | Project Manager | 2026-05-08 | Ambiguous phrasing of approval conditions led to different interpretations of completion criteria between the client and our team. | Create a checklist for approval criteria and state agreed terms clearly in the minutes. | Reflected in the standard template

## Środki zaradcze
Środki zaradcze
Szablon Excel do zarządzania wyciągniętymi wnioskami (lessons learned), analizą przyczyn źródłowych i działaniami zapobiegawczymi.
Action ID | Lesson ID | Lesson Title | Root Cause Analysis | Temporary Countermeasure | Permanent Countermeasure | Owner | Deadline | Progress
ACT-001 | LES-001 |  | The design review checklist was personalized, and the responsibility and evidence for confirming external integration conditions were unclear. | Hold a review meeting for integration scopes and identify all unconfirmed items immediately. | Revise the design review checklist to make external integration, scope of migration, and approver fields mandatory. | Member 1 | 2026-05-20 | In Progress
ACT-002 | LES-002 |  | There were no standards for the scope of the dry run, resulting in insufficient performance and anomaly testing with exceptional data. | Conduct a dry run with exceptional data and record processing times and failure counts. | Make production-equivalent data volume, exceptional data ratio, and rollback procedures mandatory in the migration plan template. | Member 2 | 2026-06-10 | Not Started
ACT-003 | LES-003 |  | Approval criteria were not written as concrete acceptance criteria in the minutes, leading to differing interpretations among stakeholders. | Reconfirm approval criteria for the current phase and align expectations with the customer. | Standardize the approval checklist template and enforce a rule to confirm agreements within 24 hours of meetings. | Project Manager | 2026-05-25 | Completed

## Ustawienia główne
Ustawienia główne
Szablon Excel do zarządzania wyciągniętymi wnioskami (lessons learned), analizą przyczyn źródłowych i działaniami zapobiegawczymi.
Lesson Categories | Member List | Impact Levels | Status List | Action Progress List
Technology & Infrastructure | Member 1 | High | Not Addressed | Not Started
Business Process | Member 2 | Medium | In Progress | In Progress
Communication | Member 3 | Low | Completed | Completed