## Leiðbeiningar
Sniðmát fyrir frávik í afhendingu
Track delivery delays, damage, misdelivery, redelivery, customer confirmation, and carrier claims in one response workbook.
Vinnuflæði viðbragða við frávikum í afhendingu
Byrjaðu á frávikaskránni, úthlutaðu viðbragðsverkefnum, skipuleggðu endurafhendingu, staðfestu árangur hjá viðskiptavini og lokaðu kröfum á flutningsaðila með sönnunargögnum.
1 | Log the exception | Record the shipment, customer, site, carrier, type, severity, owner, target resolution, delay hours, and cost impact as soon as the issue is reported.
2 | Úthluta viðbragðsverkefnum | Create tasks for customer contact, carrier checks, document correction, redelivery booking, or claim preparation, and keep due times visible.
3 | Plan recovery | Use the redelivery plan and customer confirmation sheets to align the new route, time window, contact status, proof, and delivery result.
4 | Close and learn | Leystu frávikið aðeins eftir að athugasemdir, sannanir, kröfur og staðfesting viðskiptavinar eru fullnægjandi fyrir mánaðarlega yfirferð.
Field legend
Input | Reitir sem rekstrarteymið uppfærir.
Required | Gildi sem þarf til að vinnubókin sé nothæf fyrir flokkun, síur og mælaborð.
Fellilisti | Choose from the option sheet to keep statuses consistent.
Reiknað | Formúlur eða gildi á mælaborði sem vinnubókin reiknar.
linked_sheets
sheet_id | sheet_name | kind | module_id
dashboard | Mælaborð | worksheet | exception_log
exception_log | Exception log | worksheet | exception_log
response_tasks | Response tasks | worksheet | response_tasks
redelivery_plan | Endurafhendingaráætlun | worksheet | redelivery_plan
customer_confirmation | Customer confirmations | worksheet | customer_confirmation
carrier_claims | Kröfur á flutningsaðila | worksheet | carrier_claims
lookup_options | Uppflettigildi | worksheet
machine_schema | Machine schema | worksheet

## Mælaborð
Mælaborð
Track delivery delays, damage, misdelivery, redelivery, customer confirmation, and carrier claims in one response workbook.
Samtals frávik |  |  | Í rannsókn | Recovery planned
Leyst |  |  | Delay hours | Kröfufjárhæð
Exception status
Staða | Fjöldi | Share
New | 42 | 42
Í rannsókn | 42 | 42
Recovery planned | 42 | 42
Bíður viðskiptavinar | 42 | 42
Leyst | 42 | 42
Sent áfram | 42 | 42
Severity mix
Alvarleiki | Fjöldi | Share
Low | 42 | 42
Medium | 42 | 42
High | 42 | 42
Critical | 42 | 42
Response task status
Staða verkefnis | Fjöldi | Share
Not started | 42 | 42
In progress | 42 | 42
Waiting external | 42 | 42
Done | 42 | 42
Stöðvað | 42 | 42

## Exception log
Exception log
Track delivery delays, damage, misdelivery, redelivery, customer confirmation, and carrier claims in one response workbook.
Exception ID | Tilkynnt þann | Shipment ID | Customer | Sendistaður | Viðtökustaður | Flutningsaðili | Exception type | Alvarleiki | Staða | Owner | Target resolution | Delay hours | Cost impact | Notes
EX-20260424-001 | 2026-04-24 08:40 | SHP-20260424-018 | North Region Store A | Central Hub Warehouse | Harbor District Store | Blueway Express | delay | medium | recovery_planned | Riley Morgan | 2026-04-24 18:00 | 6.5 | 420 | Dock congestion delayed departure; redelivery slot is agreed with the customer service desk.
EX-20260424-002 | 2026-04-24 10:15 | SHP-20260424-024 | Lakeside Medical Supplies | Central Hub Warehouse | Lakeside Clinic Receiving | Northline Freight | damage | high | investigating | Avery Stone | 2026-04-25 12:00 | 18 | 1280 | Outer cartons arrived crushed. Hold the shipment until photo proof and replacement timing are confirmed.
EX-20260425-001 | 2026-04-25 09:05 | SHP-20260425-011 | Metro Parts Outlet | West Crossdock | Metro East Service Counter | Blueway Express | address_issue | low | waiting_customer | Jordan Blake | 2026-04-25 15:00 | 3 | 95 | Address contact name differs from the order record. Customer confirmation is required before dispatch.

## Response tasks
Response tasks
Track delivery delays, damage, misdelivery, redelivery, customer confirmation, and carrier claims in one response workbook.
Task ID | Exception ID | Task type | Staða verkefnis | Frestur til | Owner | Tengiliður | Næsta skref | Athugasemdir
TASK-001 | EX-20260424-001 | redelivery_booking | in_progress | 2026-04-24 13:00 | Casey Reed | North Region Store A | Confirm the 16:00-18:00 redelivery window and update the customer confirmation sheet after the call. | Keep customer service and dispatch on the same status before route release.
TASK-002 | EX-20260424-002 | carrier_check | waiting_external | 2026-04-24 17:00 | Jamie Carter | Northline Freight claims desk | Request dock photos and driver statement, then decide whether a carrier claim is required. | Do not close before photo proof is attached to the case file.
TASK-003 | EX-20260425-001 | customer_contact | not_started | 2026-04-25 11:30 | Taylor Quinn | Metro Parts Outlet | Confirm the receiving contact and release the route only after the corrected address is validated. | Address correction must match the order management record.

## Endurafhendingaráætlun
Endurafhendingaráætlun
Track delivery delays, damage, misdelivery, redelivery, customer confirmation, and carrier claims in one response workbook.
Redelivery ID | Auðkenni fráviks | Áætluð dagsetning | Time window | Carrier | Route no. | Delivery status | Haft samband við viðskiptavin | Notes
RD-20260424-01 | EX-20260424-001 | 2026-04-24 | 16:00-18:00 | Blueway Express | R-18B | planned | Yes | Use a priority route and call the store 30 minutes before arrival.
RD-20260425-01 | EX-20260424-002 | 2026-04-25 | 09:00-12:00 | Northline Freight | R-22A | out_for_delivery | Yes | Replacement cartons are staged at Central Hub Warehouse pending damage approval.

## Customer confirmations
Customer confirmations
Track delivery delays, damage, misdelivery, redelivery, customer confirmation, and carrier claims in one response workbook.
Confirmation ID | Exception ID | Confirmation date | Confirmed by | Confirmation channel | Confirmation status | Krafist sönnunar | Notes
CF-001 | EX-20260424-001 | 2026-04-24 | Riley Morgan | phone | confirmed | No | Customer accepted the new delivery window and waived extra proof.
CF-002 | EX-20260424-002 | 2026-04-24 | Avery Stone | email | pending | Yes | Customer is waiting for photo evidence before accepting the replacement timing.

## Kröfur á flutningsaðila
Kröfur á flutningsaðila
Track delivery delays, damage, misdelivery, redelivery, customer confirmation, and carrier claims in one response workbook.
Auðkenni kröfu | Exception ID | Flutningsaðili | Kröfufjárhæð | Staða kröfu | Innsendunardagur | Gjalddagi uppgjörs | Owner | Notes
CL-001 | EX-20260424-002 | Northline Freight | 1280 | preparing | 2026-04-24 | 2026-05-02 | Jamie Carter | Prepare claim package with photos, delivery note, and replacement cost estimate.
CL-002 | EX-20260424-001 | Blueway Express | 420 | not_required | 2026-04-24 | 2026-04-30 | Casey Reed | Delay is operationally recovered; no formal claim expected if redelivery succeeds.

## Uppflettigildi (hidden)
Uppflettigildi
Track delivery delays, damage, misdelivery, redelivery, customer confirmation, and carrier claims in one response workbook.
exception_type | enum_exception_type_values | enum_exception_type_labels
option_set | value | label | sort | active
exception_type | delay | Delay | 10 | TRUE
exception_type | damage | Damage | 20 | TRUE
exception_type | misdelivery | Ranga afhending | 30 | TRUE
exception_type | address_issue | Address issue | 40 | TRUE
exception_type | missing_document | Vantar skjal | 50 | TRUE
exception_type | temperature_excursion | Frávik í hitastigi | 60 | TRUE
severity | enum_severity_values | enum_severity_labels
option_set | value | label | sort | active
severity | low | Low | 10 | TRUE
severity | medium | Medium | 20 | TRUE
severity | high | High | 30 | TRUE
severity | critical | Critical | 40 | TRUE
exception_status | enum_exception_status_values | enum_exception_status_labels
option_set | value | label | sort | active
exception_status | new | New | 10 | TRUE
exception_status | investigating | Í rannsókn | 20 | TRUE
exception_status | recovery_planned | Recovery planned | 30 | TRUE
exception_status | waiting_customer | Bíður viðskiptavinar | 40 | TRUE
exception_status | resolved | Leyst | 50 | TRUE
exception_status | escalated | Sent áfram | 60 | TRUE
task_type | enum_task_type_values | enum_task_type_labels
option_set | value | label | sort | active
task_type | customer_contact | Haft samband við viðskiptavin | 10 | TRUE
task_type | carrier_check | Athugun hjá flutningsaðila | 20 | TRUE
task_type | document_fix | Document fix | 30 | TRUE
task_type | redelivery_booking | Redelivery booking | 40 | TRUE
task_type | claim_preparation | Claim preparation | 50 | TRUE
task_status | enum_task_status_values | enum_task_status_labels
option_set | value | label | sort | active
task_status | not_started | Not started | 10 | TRUE
task_status | in_progress | In progress | 20 | TRUE
task_status | waiting_external | Waiting external | 30 | TRUE
task_status | done | Done | 40 | TRUE
task_status | blocked | Stöðvað | 50 | TRUE
delivery_status | enum_delivery_status_values | enum_delivery_status_labels
option_set | value | label | sort | active
delivery_status | planned | Áætlað | 10 | TRUE
delivery_status | out_for_delivery | Out for delivery | 20 | TRUE
delivery_status | delivered | Delivered | 30 | TRUE
delivery_status | failed | Mistókst | 40 | TRUE
delivery_status | cancelled | Cancelled | 50 | TRUE
confirmation_channel | enum_confirmation_channel_values | enum_confirmation_channel_labels
option_set | value | label | sort | active
confirmation_channel | phone | Sími | 10 | TRUE
confirmation_channel | email | Email | 20 | TRUE
confirmation_channel | portal | Portal | 30 | TRUE
confirmation_channel | sms | SMS | 40 | TRUE
confirmation_status | enum_confirmation_status_values | enum_confirmation_status_labels
option_set | value | label | sort | active
confirmation_status | pending | Pending | 10 | TRUE
confirmation_status | confirmed | Staðfest | 20 | TRUE
confirmation_status | disputed | Umdeilt | 30 | TRUE
confirmation_status | not_reached | Not reached | 40 | TRUE
claim_status | enum_claim_status_values | enum_claim_status_labels
option_set | value | label | sort | active
claim_status | not_required | Ekki krafist | 10 | TRUE
claim_status | preparing | Í undirbúningi | 20 | TRUE
claim_status | submitted | Submitted | 30 | TRUE
claim_status | accepted | Samþykkt | 40 | TRUE
claim_status | rejected | Rejected | 50 | TRUE
boolean | boolean_values | boolean_labels
option_set | value | label | sort | active
boolean | true | Yes | 10 | TRUE
boolean | false | No | 20 | TRUE

## Machine schema (hidden)
Machine schema
Track delivery delays, damage, misdelivery, redelivery, customer confirmation, and carrier claims in one response workbook.
modules
module_id | label | description
exception_log | Skráning frávika
response_tasks | Viðbragðsverkefni
redelivery_plan | Endurafhendingaráætlun
customer_confirmation | Customer confirmations
carrier_claims | Carrier claims
fields
module_id | field_id | label | type | role | enum_id | required
exception_log | exception_id | Exception ID | text | primary_key |  | TRUE
exception_log | reported_at | Tilkynnt þann | datetime | created_at |  | TRUE
exception_log | shipment_id | Shipment ID | text | foreign_key |  | TRUE
exception_log | customer | Customer | text | display_name |  | TRUE
exception_log | origin_site | Sendistaður | text | input |  | FALSE
exception_log | destination | Viðtökustaður | text | input |  | FALSE
exception_log | carrier | Flutningsaðili | text | input |  | FALSE
exception_log | exception_type | Exception type | enum | input | exception_type | TRUE
exception_log | severity | Alvarleiki | enum | input | severity | TRUE
exception_log | status | Staða | enum | status | exception_status | TRUE
exception_log | owner | Owner | text | owner |  | FALSE
exception_log | target_resolution | Target resolution | datetime | end_date |  | FALSE
exception_log | delay_hours | Delay hours | decimal | quantity |  | FALSE
exception_log | cost_impact | Cost impact | currency | amount |  | FALSE
exception_log | notes | Notes | long_text | input |  | FALSE
response_tasks | task_id | Task ID | text | primary_key |  | TRUE
response_tasks | exception_id | Exception ID | text | foreign_key |  | TRUE
response_tasks | task_type | Task type | enum | input | task_type | TRUE
response_tasks | task_status | Staða verkefnis | enum | status | task_status | TRUE
response_tasks | due_at | Frestur til | datetime | end_date |  | FALSE
response_tasks | owner | Owner | text | owner |  | FALSE
response_tasks | contact_party | Tengiliður | text | input |  | FALSE
response_tasks | next_action | Næsta skref | long_text | input |  | FALSE
response_tasks | notes | Athugasemdir | long_text | input |  | FALSE
redelivery_plan | redelivery_id | Redelivery ID | text | primary_key |  | TRUE
redelivery_plan | exception_id | Auðkenni fráviks | text | foreign_key |  | TRUE
redelivery_plan | planned_date | Áætluð dagsetning | date | start_date |  | FALSE
redelivery_plan | time_window | Time window | text | input |  | FALSE
redelivery_plan | carrier | Carrier | text | input |  | FALSE
redelivery_plan | route_no | Route no. | text | input |  | FALSE
redelivery_plan | delivery_status | Delivery status | enum | status | delivery_status | TRUE
redelivery_plan | customer_contacted | Haft samband við viðskiptavin | boolean | input |  | FALSE
redelivery_plan | notes | Notes | long_text | input |  | FALSE
customer_confirmation | confirmation_id | Confirmation ID | text | primary_key |  | TRUE
customer_confirmation | exception_id | Exception ID | text | foreign_key |  | TRUE
customer_confirmation | confirmation_date | Confirmation date | date | updated_at |  | FALSE
customer_confirmation | confirmed_by | Confirmed by | text | owner |  | FALSE
customer_confirmation | confirmation_channel | Confirmation channel | enum | input | confirmation_channel | FALSE
customer_confirmation | confirmation_status | Confirmation status | enum | status | confirmation_status | TRUE
customer_confirmation | proof_required | Krafist sönnunar | boolean | input |  | FALSE
customer_confirmation | notes | Notes | long_text | input |  | FALSE
carrier_claims | claim_id | Auðkenni kröfu | text | primary_key |  | TRUE
carrier_claims | exception_id | Exception ID | text | foreign_key |  | TRUE
carrier_claims | carrier | Flutningsaðili | text | display_name |  | FALSE
carrier_claims | claim_amount | Kröfufjárhæð | currency | amount |  | FALSE
carrier_claims | claim_status | Staða kröfu | enum | status | claim_status | TRUE
carrier_claims | submitted_date | Innsendunardagur | date | created_at |  | FALSE
carrier_claims | settlement_due | Gjalddagi uppgjörs | date | end_date |  | FALSE
carrier_claims | owner | Owner | text | owner |  | FALSE
carrier_claims | notes | Notes | long_text | input |  | FALSE
enum_values
enum_id | value | label | sort | tone
exception_type | delay | Delay | 10 | warning
exception_type | damage | Damage | 20 | danger
exception_type | misdelivery | Ranga afhending | 30 | danger
exception_type | address_issue | Address issue | 40 | warning
exception_type | missing_document | Vantar skjal | 50 | neutral
exception_type | temperature_excursion | Frávik í hitastigi | 60 | danger
severity | low | Low | 10 | neutral
severity | medium | Medium | 20 | warning
severity | high | High | 30 | danger
severity | critical | Critical | 40 | danger
exception_status | new | New | 10 | neutral
exception_status | investigating | Í rannsókn | 20 | warning
exception_status | recovery_planned | Recovery planned | 30 | warning
exception_status | waiting_customer | Bíður viðskiptavinar | 40 | warning
exception_status | resolved | Leyst | 50 | success
exception_status | escalated | Sent áfram | 60 | danger
task_type | customer_contact | Haft samband við viðskiptavin | 10 | neutral
task_type | carrier_check | Athugun hjá flutningsaðila | 20 | neutral
task_type | document_fix | Document fix | 30 | warning
task_type | redelivery_booking | Redelivery booking | 40 | warning
task_type | claim_preparation | Claim preparation | 50 | danger
task_status | not_started | Not started | 10 | neutral
task_status | in_progress | In progress | 20 | warning
task_status | waiting_external | Waiting external | 30 | warning
task_status | done | Done | 40 | success
task_status | blocked | Stöðvað | 50 | danger
delivery_status | planned | Áætlað | 10 | neutral
delivery_status | out_for_delivery | Out for delivery | 20 | warning
delivery_status | delivered | Delivered | 30 | success
delivery_status | failed | Mistókst | 40 | danger
delivery_status | cancelled | Cancelled | 50 | neutral
confirmation_channel | phone | Sími | 10 | neutral
confirmation_channel | email | Email | 20 | neutral
confirmation_channel | portal | Portal | 30 | neutral
confirmation_channel | sms | SMS | 40 | neutral
confirmation_status | pending | Pending | 10 | warning
confirmation_status | confirmed | Staðfest | 20 | success
confirmation_status | disputed | Umdeilt | 30 | danger
confirmation_status | not_reached | Not reached | 40 | warning
claim_status | not_required | Ekki krafist | 10 | neutral
claim_status | preparing | Í undirbúningi | 20 | warning
claim_status | submitted | Submitted | 30 | warning
claim_status | accepted | Samþykkt | 40 | success
claim_status | rejected | Rejected | 50 | danger
relations
relation_id | from_module_id | from_field_id | to_module_id | to_field_id | cardinality