## Instructions
Logistics Delivery Tracking Template
Usage tip: the light-blue columns are for input, and the light-gray columns are auto-calculated. Rows 14-22 are sample data and can be overwritten or deleted. Charts and KPIs update automatically with the master ledger.
Topic | Detail
Template purpose | Organize shipment numbers, tracking numbers, carriers, ETAs, transit updates, and delivery confirmations in one workbook.
Scope | Best for low-volume delivery operations, daily manual updates, and customer support inquiries.
Steps | 1. Register each shipment. 2. Add carrier tracking updates. 3. Record delivery confirmation. 4. Escalate delays or address issues in the exception log.

## Dashboard
Dashboard
Usage tip: the light-blue columns are for input, and the light-gray columns are auto-calculated. Rows 14-22 are sample data and can be overwritten or deleted. Charts and KPIs update automatically with the master ledger.
Metric | Value | Notes | Review rule
Active shipments | 9 | Registered, in transit, delayed, and exception shipments. | Check incomplete deliveries.
In transit | 4 | Shipments with a current transit status. | Filter by transit status.
Overdue undelivered | 1 | Shipments past ETA without delivery confirmation. | Review ETA and carrier update.

## Shipment Ledger
Shipment Ledger
Usage tip: the light-blue columns are for input, and the light-gray columns are auto-calculated. Rows 14-22 are sample data and can be overwritten or deleted. Charts and KPIs update automatically with the master ledger.
Record ID | Shipment ID | Tracking no. | Carrier | Sender | Receiver | Route | Status | ETA | Promised date | Current location | Owner | Priority | Notes
SHIP-001 | SHP-2026-001 | TRK-8401 | Northline Express | Main Distribution Center | Retail Store A | Main DC to Store A | In transit | 2026-04-14 | 2026-04-15 | Transfer hub | Olivia Morgan | Normal | Passed through transfer hub.
SHIP-002 | SHP-2026-002 | TRK-8402 | Metro Freight | Spare Parts Warehouse | Service Center B | Warehouse to service center | Delayed | 2026-04-13 | 2026-04-13 | Regional depot | Noah Carter | High | Weather delay, customer notified.
SHIP-003 | SHP-2026-003 | TRK-8403 | Parcel Link | Returns Desk | Inspection Area | Return desk to inspection | Exception | 2026-04-16 | 2026-04-16 | Address review | Emma Lee | Urgent | Address needs confirmation.

## Tracking Updates
Tracking Updates
Usage tip: the light-blue columns are for input, and the light-gray columns are auto-calculated. Rows 14-22 are sample data and can be overwritten or deleted. Charts and KPIs update automatically with the master ledger.
Update ID | Shipment ID | Update time | Status | Location | Carrier event | Next action | Owner | Visibility | Delay reason | Notes
UPD-001 | SHP-2026-001 | 2026-04-12 09:30 | Departed hub | Transfer hub | Linehaul departed | Monitor next scan. | Olivia Morgan | Internal and support | N/A | On schedule.
UPD-002 | SHP-2026-002 | 2026-04-12 14:10 | Delayed | Regional depot | Weather hold | Ask carrier for recovery ETA. | Noah Carter | Support only | Bad weather | Customer notified.
UPD-003 | SHP-2026-003 | 2026-04-12 16:20 | Address issue | Address review | Delivery blocked | Confirm address with requester. | Emma Lee | Internal | Address mismatch | Awaiting correction.

## Delivery Confirmations
Delivery Confirmations
Usage tip: the light-blue columns are for input, and the light-gray columns are auto-calculated. Rows 14-22 are sample data and can be overwritten or deleted. Charts and KPIs update automatically with the master ledger.
Receipt ID | Shipment ID | Delivery date | Receiver | Received status | Timing result | Proof type | Confirmer | Exception flag | Follow-up owner | Notes
RCV-001 | SHP-2026-001 | 2026-04-14 | Retail Store A | Pending | On time | Signature | Store manager | No | Olivia Morgan | Awaiting POD upload.
RCV-002 | SHP-2026-002 | 2026-04-14 | Service Center B | Not received | Late | None | Support desk | Yes | Noah Carter | Carrier recovery ETA requested.
RCV-003 | SHP-2026-003 | 2026-04-16 | Inspection Area | Blocked | At risk | None | Inspection lead | Yes | Emma Lee | Address issue must close first.

## Delivery Exceptions
Delivery Exceptions
Usage tip: the light-blue columns are for input, and the light-gray columns are auto-calculated. Rows 14-22 are sample data and can be overwritten or deleted. Charts and KPIs update automatically with the master ledger.
Exception ID | Shipment ID | Exception time | Exception type | Priority | Exception status | Root cause | Owner | Response note | Corrective action | Due date | Closure status
EXC-001 | SHP-2026-002 | 2026-04-12 14:10 | Delay | High | Open | Weather disruption | Noah Carter | Customer notified and carrier recovery ETA requested. | Review alternate carrier for urgent shipments. | 2026-04-13 | In progress
EXC-002 | SHP-2026-003 | 2026-04-12 16:20 | Address issue | Urgent | Open | Address mismatch | Emma Lee | Requester asked to confirm delivery address. | Require address validation before dispatch. | 2026-04-13 | Waiting
EXC-003 | SHP-2026-001 | 2026-04-12 17:00 | Document pending | Normal | Monitoring | POD not uploaded yet | Olivia Morgan | Store asked to upload signed POD. | Remind receiver before ETA. | 2026-04-14 | Monitoring

## Lookup Options
Lookup Options
Usage tip: the light-blue columns are for input, and the light-gray columns are auto-calculated. Rows 14-22 are sample data and can be overwritten or deleted. Charts and KPIs update automatically with the master ledger.
Option group | Option key | Label | Applies to | Sort order | Active | Status tone | Notes
shipment_status | in_transit | In transit | Shipment status | 10 | TRUE | info | Shipment has left origin and has not been delivered.
shipment_status | delayed | Delayed | Shipment status | 20 | TRUE | warning | ETA or promised date is at risk.
exception_type | address_issue | Address issue | Exception type | 30 | TRUE | danger | Address must be corrected before delivery.

## Machine Schema
Machine Schema
Usage tip: the light-blue columns are for input, and the light-gray columns are auto-calculated. Rows 14-22 are sample data and can be overwritten or deleted. Charts and KPIs update automatically with the master ledger.
Worksheet name | Table name | Store name | Module key | Field name | Field label | Field type | Field role | Required | Unique | Default value | Validation rule | Option set key | Show in table | Show in mobile table | Show in form | Export in CSV | Notes
Shipment Ledger | shipments | shipments | logistics_delivery_tracking | record_id | Record ID | text | primary_key | TRUE | TRUE | N/A | Internal ID for each shipment row. | N/A | TRUE | TRUE | TRUE | TRUE | Stable row identifier.
Shipment Ledger | shipments | shipments | logistics_delivery_tracking | shipment_number | Shipment ID | text | business_key | TRUE | TRUE | N/A | Operational shipment reference number. | N/A | TRUE | TRUE | TRUE | TRUE | Visible business key.
Tracking Updates | transit_updates | transit_updates | logistics_delivery_tracking | status | Status | text | status | TRUE | FALSE | N/A | Use lookup options when possible. | shipment_status | TRUE | TRUE | TRUE | TRUE | Supports dashboard filtering.