## Loading Checklist Overview
Logistics Loading Checklist Template
Logistics loading checklist template
| Loading site A | Not Started
Loading coordinator | Taro Yamada | In Progress
| 2026-04-01 | Completed
2026-06-30
2026-04-18
Monthly loading summary | 2026-04-01 | 1. Loading overview date 2. Sheet 2 3. Weekly loading sheet
Weekly loading checklist Week start day | 2026-04-13
Input Cell | Fields entered directly by the user
Control Cell | Settings for the base date and base month
Link/Auto-reflect | Sheet 2
Notes/Delay | Items that require delay handling or review
Sheet 2 + Monthly loading sheet + Weekly loading checklist + Sheet 5 1
Note on B8: MediumActual
Note on B9: 1 Monthly loading sheet
Note on B10: Date Weekly packing sheet

## Shipping Master
Loading Master
Not Started
In Progress
No | Category | Task Name |  | Staff | Planned Start | Planned End | Actual Start | Actual End | Actual | Progress Rate | Status | Priority | Location
| Loading order | Loading order check | Aoki Logistics | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 |  | 100% |  | High | Perimeter | Pre-loading preparation
| Vehicle check | Vehicle inspection | Aoki Logistics | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 |  | 100% |  | High | Around the foundation | Including soil disposal
| Load confirmation | Cargo condition check | Sato Logistics | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 |  | 100% |  | High | Overall foundation
| Load confirmation | Departure readiness | Tanaka Logistics | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 |  | 100% |  | High | Overall foundation | Departure readiness inspection required
| Load confirmation |  | Takahashi Logistics | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  |  | 70% |  | High | Overall foundation | Partially reworked
| Load confirmation | Load confirmation | Chuo Ready-Mix | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  |  | 50% |  | High | Overall foundation | Weather check required
| Load confirmation | Departure log removal and curing | Takahashi Logistics | 4 | 2026-04-19 | 2026-04-22 |  |  |  | 0% |  | Medium | Overall foundation
| Structure works | 1F | Yamaguchi Logistics | 10 | 2026-04-23 | 2026-04-30 |  |  |  | 0% |  | High | 1F
| Waterproofing works | Roof waterproofing | Mizuno Waterproofing | 4 | 2026-05-01 | 2026-05-04 |  |  |  | 0% |  | Medium | Rooftop
| Joinery works |  | Suzuki Sash | 4 | 2026-05-06 | 2026-05-10 |  |  |  | 0% |  | Medium | Perimeter area
| Electrical | Electrical wiring (rough-in) | Toko Electrical | 5 | 2026-05-08 | 2026-05-16 |  |  |  | 0% |  | Medium | Each floor
| Plumbing | Plumbing (pre-piping) | Daiichi Equipment | 5 | 2026-05-08 | 2026-05-15 |  |  |  | 0% |  | Medium | Each floor
| Interior works | Light-gauge framing | Interior Service | 6 | 2026-05-17 | 2026-05-21 |  |  |  | 0% |  | Medium | Each floor
| Interior works | PB board installation | Interior Service | 7 | 2026-05-22 | 2026-05-27 |  |  |  | 0% |  | Medium | Each floor
| Interior works | Painting | Chuo Painting | 4 | 2026-05-28 | 2026-05-31 |  |  |  | 0% |  | Medium | Each floor
| MEP finishing | Fixture installation and commissioning | Daiichi Equipment | 4 | 2026-06-01 | 2026-06-08 |  |  |  | 0% |  | High | Each floor
| Exterior works | Exterior and paving | Sato Logistics | 5 | 2026-06-09 | 2026-06-16 |  |  |  | 0% |  | Medium | Exterior
| Check | Check | Supervisor/client | 3 | 2026-06-20 | 2026-06-22 |  |  |  | 0% |  | High
|  | Rework |  | 6 | 2026-06-23 | 2026-06-27 |  |  |  | 0% |  | High
|  |  | Main contractor/client | 2 | 2026-06-30 | 2026-06-30 |  |  |  | 0% |  | High | Office
Update the blue and purple cells. Status, days, and delays are calculated automatically. Copy formulas below row 35 if you need more rows.

## Monthly Shipping Sheet
Monthly Loading
[9 empty] | ■ | Actual | Actual
No | Task Name | Status | Staff | Planned Start | Planned End | Actual Start | Actual End | Progress Rate
Sheet 2Content ■ Actual Actual MediumActual

## Weekly Packing Sheet
Loading Loading
[5 empty] | Week start day |  |  | Implementation | Daily planned vehicles is aggregated automatically
No | Task Name | Staff | Planned Start | Planned End | Actual Start | Actual End | Priority
Daily planned vehicles
LoadingSheet 2 Daily planned vehicles Staff

## Shipping and Delivery Log
Loading and Departure Record
Check
No | Date | Time | Category | Content | Related Company | Location | Status
| 2026-04-13 | 8:00 |  | Loading |  | Warehouse | Completed | Every Monday
| 2026-04-14 | 10:00 | Check | Load inspection | Supervisor/Tanaka Logistics | Site | Completed
| 2026-04-17 | 13:00 |  |  | Chuo Ready-Mix | Site | Completed | Final pre-pour check
| 2026-04-18 | 15:00 |  | Pre-departure check | Main contractor/Chuo Ready-Mix | Site
| 2026-05-06 | 9:30 |  |  | Suzuki Sash | External yard
| 2026-06-20 | 10:00 | Check | Check | Operations team | Site |  | Corrective action check
Check