## Receiving Overview
Logistics Receiving Inspection Template
Logistics receiving inspection template
| Receiving site A | Not Started
Receiving supervisor | Taro Yamada | In Progress
| 2026-04-01 | Completed
2026-06-30
2026-04-18
Monthly receiving summary | 2026-04-01 | 1. Receiving overview date 2. Sheet 2 3. Receiving loading sheet
Weekly receiving checklist Week start day | 2026-04-13
Input Cell | Fields entered directly by the user
Control Cell | Settings for the base date and base month
Link/Auto-reflect | Sheet 2
Notes/Delay | Items that require delay handling or review
Sheet 2 + Monthly loading sheet + Weekly receiving checklist + Sheet 5 1
Note on B8: MediumActual
Note on B9: 1 Monthly loading sheet
Note on B10: Date Weekly packing sheet

## Shipping Master
Receiving Master
Not Started
In Progress
No | Category | Task Name |  | Staff | Planned Start | Planned End | Actual Start | Actual End | Actual | Progress Rate | Status | Priority | Location
| Receiving | Inbound receiving check | Aoki Logistics | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 |  | 100% |  | High | Perimeter | Pre-receiving preparation
| Check | Visual inspection | Aoki Logistics | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 |  | 100% |  | High | Around the foundation | Including soil disposal
| Putaway plan | Putaway prep | Sato Logistics | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 |  | 100% |  | High | Overall foundation
| Putaway plan | Discrepancy log | Tanaka Discrepancy log | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 |  | 100% |  | High | Overall foundation | Discrepancy log inspection required
| Putaway plan |  | Takahashi Receiving confirmation | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  |  | 70% |  | High | Overall foundation | Partially reworked
| Putaway plan | Putaway complete | Chuo Ready-Mix | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  |  | 50% |  | High | Overall foundation | Weather check required
| Putaway plan | Receiving confirmation removal and curing | Takahashi Receiving confirmation | 4 | 2026-04-19 | 2026-04-22 |  |  |  | 0% |  | Medium | Overall foundation
| Structure works | 1F | Yamaguchi Logistics | 10 | 2026-04-23 | 2026-04-30 |  |  |  | 0% |  | High | 1F
| Waterproofing works | Roof waterproofing | Mizuno Waterproofing | 4 | 2026-05-01 | 2026-05-04 |  |  |  | 0% |  | Medium | Rooftop
| Joinery works |  | Suzuki Sash | 4 | 2026-05-06 | 2026-05-10 |  |  |  | 0% |  | Medium | Perimeter area
| Electrical | Electrical wiring (rough-in) | Toko Electrical | 5 | 2026-05-08 | 2026-05-16 |  |  |  | 0% |  | Medium | Each floor
| Plumbing | Plumbing (pre-piping) | Daiichi Equipment | 5 | 2026-05-08 | 2026-05-15 |  |  |  | 0% |  | Medium | Each floor
| Interior works | Light-gauge framing | Interior Service | 6 | 2026-05-17 | 2026-05-21 |  |  |  | 0% |  | Medium | Each floor
| Interior works | PB board installation | Interior Service | 7 | 2026-05-22 | 2026-05-27 |  |  |  | 0% |  | Medium | Each floor
| Interior works | Painting | Chuo Painting | 4 | 2026-05-28 | 2026-05-31 |  |  |  | 0% |  | Medium | Each floor
| MEP finishing | Fixture installation and commissioning | Daiichi Equipment | 4 | 2026-06-01 | 2026-06-08 |  |  |  | 0% |  | High | Each floor
| Exterior works | Exterior and paving | Sato Logistics | 5 | 2026-06-09 | 2026-06-16 |  |  |  | 0% |  | Medium | Exterior
| Check | Check | Supervisor/client | 3 | 2026-06-20 | 2026-06-22 |  |  |  | 0% |  | High
|  | Rework |  | 6 | 2026-06-23 | 2026-06-27 |  |  |  | 0% |  | High
|  |  | Main contractor/client | 2 | 2026-06-30 | 2026-06-30 |  |  |  | 0% |  | High | Office
Update the blue and purple cells. Status, days, and delays are calculated automatically. Copy formulas below row 35 if you need more rows.

## Monthly Shipping Sheet
Monthly Receiving
[9 empty] | ■ | Actual | Actual
No | Task Name | Status | Staff | Planned Start | Planned End | Actual Start | Actual End | Progress Rate
Sheet 2Content ■ Actual Actual MediumActual

## Weekly Packing Sheet
Weekly receiving
[5 empty] | Week start day |  |  | Implementation | Daily planned putaway is aggregated automatically
No | Task Name | Staff | Planned Start | Planned End | Actual Start | Actual End | Priority
Daily planned putaway
ReceivingSheet 2 Daily planned putaway Staff

## Shipping and Delivery Log
Receiving and Check Record
Check
No | Date | Time | Category | Content | Related Company | Location | Status
| 2026-04-13 | 8:00 |  | Receiving |  | Warehouse | Completed | Every Monday
| 2026-04-14 | 10:00 | Check | Receiving inspection | Supervisor/Tanaka Discrepancy log | Site | Completed
| 2026-04-17 | 13:00 |  |  | Chuo Ready-Mix | Site | Completed | Final pre-pour check
| 2026-04-18 | 15:00 |  | Discrepancy review | Main contractor/Chuo Ready-Mix | Site
| 2026-05-06 | 9:30 |  |  | Suzuki Sash | External yard
| 2026-06-20 | 10:00 | Check | Check | Warehouse team | Site |  | Corrective action check
Check