## Production Overview
Product name | Sample manufacturing case |  | 20
| Tokyo Sample Ward 1-2-3 | Not Started | 14
Site manager | Taro Yamada | In Progress | 2
| 2026-04-01 | Completed | 4
| 2026-06-30 |  | 26%
2026-04-18
Monthly Production Sheet 1 | 2026-04-01 | How to use 1. Enter the date and product name in Production Overview 2. Update the blue cells in Production Master 3. Monthly and weekly sheets update automatically
Weekly Process SheetWeek start day | 2026-04-13
Input Cell | Fields entered directly by the user
Control Cell | Settings for the base date and base month
Link/Auto-reflect | Production Master
Notes/Delay | Items that require delay handling or review
This workbook keeps work orders, process steps, quality checks, and shipping timing in one place. You can overwrite the sample rows and add more rows as needed, then copy formulas downward.
Note on B8: Medium Quality and Performance Log
Note on B9: 1 Monthly Production Sheet
Note on B10: Date Weekly Process Sheet

## Production Master
Production Master
Product name | Sample manufacturing case | [8 empty] | 20
[9 empty] | Not Started | 14
[9 empty] | In Progress | 2
No | Category | Task Name |  | Staff | Planned Start | Planned End |  | Quality and Performance Log Start | Quality and Performance Log End | Quality and Performance Log | Progress Rate | Status |  | Priority | Location
1 | Line setup | Initial setup | Production Team | 4 | 2026-04-01 | 2026-04-03 | 3 | 2026-04-01 | 2026-04-03 | 3 | 100% | Completed | 0 | High | Plant perimeter | Pre-production preparation
2 | Material preparation | Planning review | Production Team | 6 | 2026-04-04 | 2026-04-08 | 5 | 2026-04-04 | 2026-04-08 | 5 | 100% | Completed | 0 | High | Around the line | Including scrap removal
3 | Equipment setup | Equipment base preparation | Partner E | 5 | 2026-04-09 | 2026-04-10 | 2 | 2026-04-09 | 2026-04-10 | 2 | 100% | Completed | 0 | High | Overall setup
4 | Equipment setup | Parts preparation | Tanaka Parts | 6 | 2026-04-11 | 2026-04-14 | 4 | 2026-04-11 | 2026-04-14 | 4 | 100% | Completed | 0 | High | Overall setup | Parts inspection required
5 | Equipment setup |  | Partner D | 5 | 2026-04-13 | 2026-04-16 | 4 | 2026-04-13 |  | 6 | 70% | In Progress | 2 | High | Overall setup | Partially reworked
6 | Equipment setup | Trial production | Chuo Materials | 8 | 2026-04-17 | 2026-04-18 | 2 | 2026-04-17 |  | 2 | 50% | In Progress | 0 | High | Overall setup | Weather check required
7 | Equipment setup | Verification | Partner D | 4 | 2026-04-19 | 2026-04-22 | 4 |  |  |  | 0% | Not Started | 0 | Medium | Overall setup
8 | Trial prep | Trial prep | Aoyama Manufacturing | 10 | 2026-04-23 | 2026-04-30 | 8 |  |  |  | 0% | Not Started | 0 | High | Assembly area
9 | Quality check | First-article check | Quality | 4 | 2026-05-01 | 2026-05-04 | 4 |  |  |  | 0% | Not Started | 0 | Medium | Inspection area
10 | Parts assembly | Parts assembly | Suzuki Components | 4 | 2026-05-06 | 2026-05-10 | 5 |  |  |  | 0% | Not Started | 0 | Medium | Parts area
11 | Electrical | Electrical check | Toko Controls | 5 | 2026-05-08 | 2026-05-16 | 9 |  |  |  | 0% | Not Started | 0 | Medium | Equipment area
12 | Packing | Packing prep | Packing | 5 | 2026-05-08 | 2026-05-15 | 8 |  |  |  | 0% | Not Started | 0 | Medium | Packing area
13 | Shipping | Shipping prep | Logistics | 6 | 2026-05-17 | 2026-05-21 | 5 |  |  |  | 0% | Not Started | 0 | Medium | Shipping area
14 | Equipment | Equipment check | Equipment | 7 | 2026-05-22 | 2026-05-27 | 6 |  |  |  | 0% | Not Started | 0 | Medium | Equipment area
15 | Maintenance | Preventive maintenance | Equipment | 4 | 2026-05-28 | 2026-05-31 | 4 |  |  |  | 0% | Not Started | 0 | Medium | Equipment area
16 | Rework | Defect rework | Quality | 4 | 2026-06-01 | 2026-06-08 | 8 |  |  |  | 0% | Not Started | 0 | High | Rework area
17 | Completion | Completion confirmation | Quality | 5 | 2026-06-09 | 2026-06-16 | 8 |  |  |  | 0% | Not Started | 0 | Medium | Shipment area
18 | Inspection | Inspection | Manager / HQ | 3 | 2026-06-20 | 2026-06-22 | 3 |  |  |  | 0% | Not Started | 0 | High
19 |  | Rework |  | 6 | 2026-06-23 | 2026-06-27 | 5 |  |  |  | 0% | Not Started | 0 | High
20 |  |  | Manager / HQ | 2 | 2026-06-30 | 2026-06-30 | 1 |  |  |  | 0% | Not Started | 0 | High | Office
Update the blue and purple cells. Status, days, and delays are calculated automatically. Copy formulas below row 35 if you need more rows.

## Monthly Process Sheet
20264 Monthly Production Sheet
Product name | Sample manufacturing case | [5 empty] | 2026-04-18 |  |  |  | ■ |  | Quality and Performance Log | Quality and Performance Log
No | Task Name |  | Status | Staff | Planned Start | Planned End | Quality and Performance Log Start | Quality and Performance Log End | Progress Rate | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30
1 | Initial setup | Production Team | Completed | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | 100% | 2026-04-01: Quality and Performance Log; 2026-04-02: Quality and Performance Log; 2026-04-03: Quality and Performance Log
2 | Planning review | Production Team | Completed | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 | 100% | 2026-04-04: Quality and Performance Log; 2026-04-05: Quality and Performance Log; 2026-04-06: Quality and Performance Log; 2026-04-07: Quality and Performance Log; 2026-04-08: Quality and Performance Log
3 | Equipment base preparation | Partner E | Completed | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 100% | 2026-04-09: Quality and Performance Log; 2026-04-10: Quality and Performance Log
4 | Parts preparation | Tanaka Parts | Completed | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 | 100% | 2026-04-11: Quality and Performance Log; 2026-04-12: Quality and Performance Log; 2026-04-13: Quality and Performance Log; 2026-04-14: Quality and Performance Log
5 |  | Partner D | In Progress | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  | 70% | 2026-04-13: Quality and Performance Log; 2026-04-14: Quality and Performance Log; 2026-04-15: Quality and Performance Log; 2026-04-16: Quality and Performance Log; 2026-04-17: Quality and Performance Log; 2026-04-18: Quality and Performance Log
6 | Trial production | Chuo Materials | In Progress | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  | 50% | 2026-04-17: Quality and Performance Log; 2026-04-18: Quality and Performance Log
7 | Trial prep | Aoyama Manufacturing | Not Started | 4 | 2026-04-19 | 2026-04-22 |  |  | 0% | bar: 2026-04-19 to 2026-04-22
8 | First-article check | Quality | Not Started | 10 | 2026-04-23 | 2026-04-30 |  |  | 0% | bar: 2026-04-23 to 2026-04-30
9 | Parts assembly | Suzuki Components | Not Started | 4 | 2026-05-01 | 2026-05-04 |  |  | 0%
10 | Electrical check | Toko Controls | Not Started | 4 | 2026-05-06 | 2026-05-10 |  |  | 0%
11 | Packing prep | Packing | Not Started | 5 | 2026-05-08 | 2026-05-16 |  |  | 0%
12 | Shipping prep | Logistics | Not Started | 5 | 2026-05-08 | 2026-05-15 |  |  | 0%
13 | Equipment check | Equipment | Not Started | 6 | 2026-05-17 | 2026-05-21 |  |  | 0%
14 | Preventive maintenance | Equipment | Not Started | 7 | 2026-05-22 | 2026-05-27 |  |  | 0%
15 | Defect rework | Quality | Not Started | 4 | 2026-05-28 | 2026-05-31 |  |  | 0%
16 | Completion confirmation | Quality | Not Started | 4 | 2026-06-01 | 2026-06-08 |  |  | 0%
17 | Site setup | Partner E | Not Started | 5 | 2026-06-09 | 2026-06-16 |  |  | 0%
18 | Inspection | Manager / HQ | Not Started | 3 | 2026-06-20 | 2026-06-22 |  |  | 0%
19 | Rework |  | Not Started | 6 | 2026-06-23 | 2026-06-27 |  |  | 0%
20 |  | Manager / HQ | Not Started | 2 | 2026-06-30 | 2026-06-30 |  |  | 0%
Production Master Content ■ Quality and Performance Log Quality and Performance Log Medium Quality and Performance Log

## Weekly Process Sheet
2026413 Weekly Process Sheet
Product name | Sample manufacturing case |  |  |  |  | Week start day | 2026-04-13 |  |  |  | Implementation | Daily planned staff is aggregated automatically
No | Task Name |  | Staff | Planned Start | Planned End | Quality and Performance Log Start | Quality and Performance Log End | Priority | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19
Daily planned staff | [8 empty] | 11 | 11 | 5 | 5 | 8 | 8 | 4
1 | Initial setup | Production Team | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | High | [7 empty] | Pre-production preparation
2 | Planning review | Production Team | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 | High | [7 empty] | Including scrap removal
3 | Equipment base preparation | Partner E | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | High
4 | Parts preparation | Tanaka Parts | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 | High | Implementation | Implementation | [5 empty] | Parts inspection required
5 |  | Partner D | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  | High | Implementation | Implementation | Implementation | Implementation | Implementation | Implementation |  | Partially reworked
6 | Trial prep | Aoyama Manufacturing | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  | High |  |  |  |  | Implementation | Implementation |  | Weather check required
7 | First-article check | Quality | 4 | 2026-04-19 | 2026-04-22 |  |  | Medium
8 | Parts assembly | Suzuki Components | 10 | 2026-04-23 | 2026-04-30 |  |  | High
9 | Electrical check | Toko Controls | 4 | 2026-05-01 | 2026-05-04 |  |  | Medium
10 | Packing prep | Packing | 4 | 2026-05-06 | 2026-05-10 |  |  | Medium
11 | Shipping prep | Logistics | 5 | 2026-05-08 | 2026-05-16 |  |  | Medium
12 | Equipment check | Equipment | 5 | 2026-05-08 | 2026-05-15 |  |  | Medium
13 | Preventive maintenance | Equipment | 6 | 2026-05-17 | 2026-05-21 |  |  | Medium
14 | Defect rework | Quality | 7 | 2026-05-22 | 2026-05-27 |  |  | Medium
15 | Completion confirmation | Quality | 4 | 2026-05-28 | 2026-05-31 |  |  | Medium
16 | Fixture installation and commissioning | Daiichi Machinery | 4 | 2026-06-01 | 2026-06-08 |  |  | High
17 | Site setup | Partner E | 5 | 2026-06-09 | 2026-06-16 |  |  | Medium
18 | Inspection | Manager / HQ | 3 | 2026-06-20 | 2026-06-22 |  |  | High
19 | Rework |  | 6 | 2026-06-23 | 2026-06-27 |  |  | High
20 |  | Manager / HQ | 2 | 2026-06-30 | 2026-06-30 |  |  | High
Weekly Production Master Daily planned staff Staff

## Quality and Performance Log
Quality and Performance Log
Product name | Sample manufacturing case |  |  |  |  | Production and inspection log
No | Date | Time | Category | Content | Related Company | Location | Status | Notes
1 | 2026-04-13 | 8:00 | Safety | Weekly safety check | Production | Site office | Completed | Every Monday
2 | 2026-04-14 | 10:00 | Inspection | First-article check | Supervisor/Suzuki Components | Site | Completed | Review after approval
3 | 2026-04-17 | 13:00 | Inspection | Process confirmation | Engineering | Site | Completed | Trial-run check
4 | 2026-04-18 | 15:00 | Production | Output check | Production | Site | Planned | Pending confirmation
5 | 2026-05-06 | 9:30 | Packing | Packing check | Warehouse | Warehouse | Planned | Check before shipping
6 | 2026-06-20 | 10:00 | Inspection | Final inspection | Quality | Site | Planned | Corrective action check
This sheet is a helper table for tracking non-process plans such as safety, inspections, and shipping.