## Instructions
Manufacturing Process Management General Excel Template
This workbook is organized from the web version's production plan, process progress, quality checks, completion confirmation, and issue tracking logic, and expanded for multi-line, multi-item, multi-business scenarios.
Module | Purpose | Recommended entry role | Key fields | Common business scenarios
Production Plan | Establish work orders and due-date baselines, and standardize work order status, line, owner, and material status. | Planning / production management | Work order no., product, planned quantity, planned completion, status | Order production, inventory replenishment, prototype trials, multi-line scheduling
Process Master | Maintain the standard process route for each product, which is the foundation for downstream progress, quality, and traceability. | Process / IE / production engineering | Product, route, process order, equipment, inspection point, SOP | Standard processes, NPI, outsourced steps, critical parameter management
Process Progress | Record planned vs actual, completion rate, output, and defects by step to spot bottlenecks quickly. | Team leader / on-site supervisor | Work order no., step, completion rate, status, output quantity | Daily reports, bottleneck tracking, rework tracking, outsourced progress

## Management Dashboard
Management Dashboard
This workbook is organized from the web version's production plan, process progress, quality checks, completion confirmation, and issue tracking logic, and expanded for multi-line, multi-item, multi-business scenarios.
Total work orders | In progress / awaiting first article | Delay risk | First article / quality pass rate | Average process progress | Open issues | On-time delivery rate | Due within 7 days
8 | 5 | 1 | 40% | 39% | 4 | 0% | 4
Work order status distribution | Quantity |  | Quality result | Recordscount |  | Business scenario | Work orders
Not started | 2 |  | Pass | 2 |  | Order Production/MTO | 3

## Production Plan
Production Plan
This workbook is organized from the web version's production plan, process progress, quality checks, completion confirmation, and issue tracking logic, and expanded for multi-line, multi-item, multi-business scenarios.
Work order no. | Business scenario | Customer/Project | Product/Material | Spec/Version | Lot No. / Order No. | Planned Qty | Unit | Planned Start | Planned Completion | Line/Area | Owner | Work order status | Priority | Current Step | Progress % | Days Left | Risk | Material Status | Notes
WO-260418-018 | Order Production/MTO | Customer A | A-series pump body | V2 | SO-10018 | 1,200 | pcs | 2026-04-18 | 2026-04-30 | Line 1 | Ken Sato | First article approved | High | machining | 81% | 6 | On track | complete set | First article approved; move to batch processing
WO-260419-006 | Inventory Replenishment/MTS | Finished goods warehouse | B-series valve seat | Standard | LOT-B0426 | 800 | pcs | 2026-04-19 | 2026-05-03 | Line 2 | Nana Tanaka | In progress | Medium | Heat treatment | 73% | 9 | On track | complete set | Produce according to the replenishment plan
WO-260420-011 | Prototype Trial/NPI | R&D project P7 | C-type bracket | Trial R1 | NPI-0420 | 60 | pcs | 2026-04-20 | 2026-04-28 | Trial line | Hiro Takahashi | Awaiting first article | High | Assembly | 65% | 4 | On track | alternative material | Critical dimensions need quality recheck

## Process Master
Process Master
This workbook is organized from the web version's production plan, process progress, quality checks, completion confirmation, and issue tracking logic, and expanded for multi-line, multi-item, multi-business scenarios.
Product/Material | Process Route | Process Sequence | Process name | Standard Cycle Time (hours/pc) | Standard Yield % | Equipment / station | Responsible Role | Inspection point | critical parameters/control points | SOP / file link | Outsourced | Effective date | Notes
A-series pump body | Pump body standard route | 10 | Material prep | 0.02 | 99% | Storage / material prep area | Material handler | No | Material completeness and lot check | SOP-MAT-001 | No | 2026-01-01
A-series pump body | Pump body standard route | 20 | CNC rough machining | 0.15 | 97% | CNC-01 | machining | Yes | Tool life, first-article dimension check | SOP-CNC-012 | No | 2026-01-01
A-series pump body | Pump body standard route | 30 | Cleaning | 0.03 | 99% | Cleaning line A | Production | No | Cleaning agent concentration | SOP-CLN-003 | No | 2026-01-01

## Process Progress
Process Progress
This workbook is organized from the web version's production plan, process progress, quality checks, completion confirmation, and issue tracking logic, and expanded for multi-line, multi-item, multi-business scenarios.
Work order no. | Product/Material | Process Route | Process Sequence | Process name | Planned Start | Planned Completion | Actual Start | Actual Completion | Owner | Completion rate% | Status | Output quantity | Defect Qty | Yield % | Bottleneck / delay reason | Next Action | Updated Time | Notes
WO-260418-018 | A-series pump body | Pump body standard route | 10 | Material prep | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | Ken Sato | 100% | Completed | 1,200 | 0 | 100% |  | Send to CNC | 2026-04-18
WO-260418-018 | A-series pump body | Pump body standard route | 20 | CNC rough machining | 2026-04-19 | 2026-04-24 | 2026-04-19 |  | Ken Sato | 62% | In progress | 760 | 8 | 99% | Tool-change waiting | complete remaining batches | 2026-04-24
WO-260419-006 | B-series valve seat | Valve seat standard route | 10 | Material prep | 2026-04-19 | 2026-04-19 | 2026-04-19 | 2026-04-19 | Nana Tanaka | 100% | Completed | 800 | 0 | 100% |  | Move to heat treatment | 2026-04-19

## Quality Records
Quality Records
This workbook is organized from the web version's production plan, process progress, quality checks, completion confirmation, and issue tracking logic, and expanded for multi-line, multi-item, multi-business scenarios.
Date | Work order no. | Product/Material | Lot No. / Order No. | Process name | Inspection type | Sample Count | Pass Count | Defect Count | Inspection Result | defect type | Photo / Attachment Link | Verifier | Disposition | Close status | Notes
2026-04-18 | WO-260418-018 | A-series pump body | SO-10018 | CNC rough machining | First article | 5 | 5 | 0 | Pass |  | photo://example/a001 | Rei Yamamoto | Release | Closed | First-article dimensions OK
2026-04-21 | WO-260420-011 | C-type bracket | NPI-0420 | Assembly | First article | 3 | 2 | 1 | Fail | Dimension deviation | photo://example/c001 | Rei Yamamoto | Pending decision | In progress | Critical dimensions need process confirmation
2026-04-22 | WO-260419-006 | B-series valve seat | LOT-B0426 | Heat treatment | Patrol inspection | 20 | 19 | 1 | Concession / watch | low hardness |  | Nana Tanaka | Concession accepted | Awaiting verification | Supplemental recheck

## Issue Tracking
Issue Tracking
This workbook is organized from the web version's production plan, process progress, quality checks, completion confirmation, and issue tracking logic, and expanded for multi-line, multi-item, multi-business scenarios.
Issue number | Found Date | Work order no. | Source Module | Issue type | Severity | Impact Description | Owner | Status | Temporary Action | Root Cause | Corrective and Preventive Action (CAPA) | Expected Close Date | Actual Close Date | Overdue Days | Notes
EX-260421-001 | 2026-04-21 | WO-260420-011 | Quality Records | Quality issue | High | First article critical dimension deviation affects trial release | Rei Yamamoto | In progress | Stop the batch and isolate the sample parts | Fixture positioning deviation | Calibrate the fixture and remeasure the first article | 2026-04-26 |  | 0 | NPIProjectpriorityhandling
EX-260423-002 | 2026-04-23 | WO-260423-003 | Material | Material shortage | High | Packaging material shortage stops packing | Daisuke Ito | In progress | Adjust the packing sequence and handle complete sets first | Supplier delivery delay | Expedite procurement and create safety stock | 2026-04-25 |  | 0 | Procurement notified
EX-260424-003 | 2026-04-24 | WO-260418-018 | Equipment | Equipment failure | Medium | CNC tool-change waiting is affecting daily output | Ken Sato | Awaiting verification | Use backup tooling | Insufficient tool-life monitoring | Add a tool-life warning | 2026-04-29 |  | 0

## Completion History
Completion History
This workbook is organized from the web version's production plan, process progress, quality checks, completion confirmation, and issue tracking logic, and expanded for multi-line, multi-item, multi-business scenarios.
Record no. | Work order no. | Product/Material | Lot No. / Order No. | Planned Qty | Completed Qty | Rework Qty | Scrap Qty | Completion Date | Reviewer | Delivery status | Output achievement rate | File / Attachment Link | Notes
FG-260419-001 | WO-260418-018 | A-series pump body | SO-10018 | 1,200 | 0 | 0 | 0 |  |  | Awaiting review | 0% |  | Example: fill in the actual completion quantity and date after completion
FG-260424-001 | WO-260423-003 | F-series end cover | SO-10031 | 300 | 60 | 0 | 0 | 2026-04-24 | Daisuke Ito | Ahead of schedule | 20% |  | Partially packed

## Settings
Settings
This workbook is organized from the web version's production plan, process progress, quality checks, completion confirmation, and issue tracking logic, and expanded for multi-line, multi-item, multi-business scenarios.
Field | Default value | Description | Business scenario | Work order status | Priority | Line/Area | Shift | Unit | Material Status | Whether | Inspection type | Disposition | Close status | Issue source | Issue type | Severity | Progress status | Delivery status
Company name | Sample Manufacturing Co., Ltd. | Replace with the actual company name | Order Production/MTO | Not started | Urgent | Line 1 | Day shift | pcs | complete set | Yes | First article | Release | New | Production Plan | Line stop | High | Not started | On time
Factory / location | Plant 1 | Used to distinguish multiple factories or workshops | Inventory Replenishment/MTS | In progress | High | Line 2 | Night shift | set | Partial material shortage | No | Patrol inspection | Rework | In progress | Process Progress | Material shortage | Medium | In progress | Delayed
Template version | v1.0 | Internal template version | Prototype Trial/NPI | Awaiting first article | Medium | Line 3 | Mid shift | batch | Awaiting inspection |  | Last piece | Scrap | Awaiting verification | Quality Records | Equipment failure | Low | Awaiting inspection | Ahead of schedule