## Instructions
Work Order Tracking Template
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Display name | Machine worksheet name | type | Purpose | Business data
Usage notes | Instructions | System notes | Explains template steps, field maintenance rules, status definitions, and downstream generation notes. | Tidak
Dasbor | Work Order Dashboard | System dashboard | Summarizes six metrics directly related to work order tracking for regular meeting review. | Tidak
Work Order Register | Work Order Register | Business data | Register baseline work order information and standardize order numbers, items, planned quantities, due dates, priorities, lines, and owners. | Ya

## Work Order Dashboard
Work Order Dashboard
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Metric | Current value | Deskripsi | Review rule | Data source
Open work orders |  | Counts work orders that are not completed or cancelled. | If the count keeps rising, review scheduling and bottlenecks. | Work Order Register
Overdue open orders |  | Counts work orders past due that are not completed or cancelled. | Any value above 0 should be reviewed in the regular meeting. | Work Order Register
Material shortage items |  | Counts material issue records with a shortage quantity or shortage status. | If above 0, confirm material issue status and alternatives first. | Material Issue

## Work Order Register
Work Order Register
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Record ID | Work order no. | Item | Planned quantity | Due date | Priority | Line | Responsible department | Work order status | Penanggung Jawab | Created date | Updated date | Catatan
WO-0001 | WO-260418-024 | A-Series Pump Body | 1,200 | 2026-05-16 | Tinggi | Line A | Production | Sedang Berlangsung | John Smith | 2026-05-01 | 2026-05-18 | Customer order prioritized for scheduling; monitor material arrival.
WO-0002 | WO-260505-011 | B-Series Valve Seat | 800 | 2026-05-25 | Sedang | Line B | Production | Planned | Emily Davis | 2026-05-05 | 2026-05-18 | Move to processing after first-piece approval.
WO-0003 | WO-260508-018 | C-Series Shaft Sleeve | 1,500 | 2026-05-12 | Mendesak | Line C | Materials | Blocked | Michael Brown | 2026-05-07 | 2026-05-18 | Critical bearing shortage is affecting assembly pace.

## Progress Checks
Progress Checks
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Record ID | Progress check no. | Work order record ID | Check date | Progress stage | Progress percent | Progress status | Bottleneck notes | Penanggung Jawab | Created date | Updated date | Catatan
PRG-0001 | PRG-WO0001-01 | WO-0001 | 2026-05-03 | Preparation | 15% | Selesai |  | John Smith | 2026-05-03 | 2026-05-03 | Material preparation completed.
PRG-0002 | PRG-WO0001-02 | WO-0001 | 2026-05-10 | Processing | 55% | On track |  | John Smith | 2026-05-10 | 2026-05-10 | Processing is on track.
PRG-0003 | PRG-WO0001-03 | WO-0001 | 2026-05-17 | Assembly | 72% | Delayed | Seal rings for pump bodies arrived later than planned. | John Smith | 2026-05-17 | 2026-05-18 | Additional night shift is expected.

## Material Issue
Material Issue
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Record ID | Issue record no. | Work order record ID | Material code | Material name | Requested quantity | Issued quantity | Shortage quantity | Unit | Issue date | Issue status | Penanggung Jawab | Created date | Updated date | Catatan
MAT-0001 | MAT-WO0001-001 | WO-0001 | M-PMP-001 | Pump body blank | 1,200 | 1,200 |  | pcs | 2026-05-02 | Issued | Emily Davis | 2026-05-02 | 2026-05-02 | Issued by batch.
MAT-0002 | MAT-WO0001-002 | WO-0001 | M-SEAL-008 | Seal ring | 1,200 | 900 |  | pcs | 2026-05-10 | Shortage | Emily Davis | 2026-05-10 | 2026-05-18 | Remaining 300 pcs are in transit.
MAT-0003 | MAT-WO0001-003 | WO-0001 | M-BOLT-020 | Mounting bolts | 4,800 | 4,800 |  | pcs | 2026-05-09 | Ditutup | John Smith | 2026-05-09 | 2026-05-11 | Completeness confirmed.

## QC Rework and Variance
QC Rework and Variance
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Record ID | QC issue no. | Work order record ID | Inspection date | Issue type | Defective quantity | Rework quantity | Closure due date | Rework status | Corrective action | Penanggung Jawab | Created date | Updated date | Catatan
QAR-0001 | QAR-WO0001-001 | WO-0001 | 2026-05-16 | Quality defect | 18 | 18 | 2026-05-21 | In rework | Reinspect after reworking the sealing surface. | Sarah Wilson | 2026-05-16 | 2026-05-18 | Track closely.
QAR-0002 | QAR-WO0001-002 | WO-0001 | 2026-05-18 | Documentation gap | 0 | 0 | 2026-05-20 | Open | Add missing progress check record. | John Smith | 2026-05-18 | 2026-05-18 | Registration basis supplemented.
QAR-0003 | QAR-WO0002-001 | WO-0002 | 2026-05-18 | Process delay | 0 | 0 | 2026-05-24 | Open | Follow up on first-piece confirmation window. | Emily Davis | 2026-05-18 | 2026-05-18 | Monitor processing start.

## Completion Confirmations
Completion Confirmations
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Record ID | Completion confirmation no. | Work order record ID | Completion date | Actual quantity | Accepted quantity | Confirmation result | Confirmation status | Variance summary | Penanggung Jawab | Created date | Updated date | Catatan
CNF-0001 | CNF-WO0001 | WO-0001 | 2026-05-18 | 900 | 870 | Quantity variance | Under review | Some quantity will be confirmed after reinspection. | Sarah Wilson | 2026-05-18 | 2026-05-18 | Not finally closed.
CNF-0002 | CNF-WO0002 | WO-0002 | 2026-05-25 | 0 | 0 | Pending review | Pending confirmation | Work order is not yet completed. | Emily Davis | 2026-05-18 | 2026-05-18 | Planned.
CNF-0003 | CNF-WO0003 | WO-0003 | 2026-05-18 | 500 | 480 | Quality variance | Returned | Blocked work order needs additional rework notes. | Michael Brown | 2026-05-18 | 2026-05-18 | Returned for supplement.

## Lookup Options
Lookup Options
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Option set key | Worksheet | Field name | Machine option value | Display label | Color meaning | Default | Sort order
option_set_key | worksheet_name | field_name | option_value | option_label | color_semantic | is_default | sort_order
work_order_status | Work Order Register | status | planned | Planned | neutral | Ya | 1
work_order_status | Work Order Register | status | in_progress | Sedang Berlangsung | info | Tidak | 2

## Machine Schema
Machine Schema
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Worksheet name | Table name | Store name | Module key | Module label | Field name | Field label | Field type | Field role | Required | Unique | Default value | Validation rule | Option set key | Searchable | Filterable | Sortable | Show in table | Show on mobile | Show in form | Show in detail | Read-only in form | Export CSV | Related worksheet | Related field | Catatan
worksheet_name | table_name | store_name | module_key | module_label | field_name | field_label | field_type | field_role | required | unique | default_value | validation_rule | option_set_key | is_searchable | is_filterable | is_sortable | show_in_table | show_in_mobile_table | show_in_form | show_in_detail | readonly_in_form | export_in_csv | related_worksheet | related_field | notes
Work Order Register | Work Order Register | Work Order Register | Work Order Register | Work Order Register | record_id | Record ID | text | primary_key | Ya | Ya | auto_sequence:WO-0001 | Auto-generated; format WO-0001. |  | Tidak | Tidak | Ya | Tidak | Tidak | Tidak | Ya | Ya | Ya |  |  | Shared primary key; key_path=record_id.
Work Order Register | Work Order Register | Work Order Register | Work Order Register | Work Order Register | work_order_no | Work order no. | text | display_name | Ya | Ya |  | Required and unique; example WO-260418-024. |  | Ya | Tidak | Ya | Ya | Ya | Ya | Ya | Tidak | Ya |  |  | Business number; does not replace record_id.