## Uso
Modello di tracciamento ordini di lavoro
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Display name | Machine worksheet name | type | Obiettivo | Business data
Note d'uso | Uso | System notes | Explains template steps, field maintenance rules, status definitions, and downstream generation notes. | Non disponibile
Cruscotto | Work Order Dashboard | System dashboard | Summarizes six metrics directly related to work order tracking for regular meeting review. | Non disponibile
Work Order Register | Work Order Register | Business data | Register baseline work order information and standardize order numbers, items, planned quantities, due dates, priorities, lines, and owners. | Si

## Work Order Dashboard
Work Order Dashboard
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Metrica | Valore corrente | Descrizione | Review rule | Data source
Open work orders |  | Counts work orders that are not completed or cancelled. | If the count keeps rising, review scheduling and bottlenecks. | Work Order Register
Overdue open orders |  | Counts work orders past due that are not completed or cancelled. | Any value above 0 should be reviewed in the regular meeting. | Work Order Register
Material shortage items |  | Counts material issue records with a shortage quantity or shortage status. | If above 0, confirm material issue status and alternatives first. | Material Issue

## Work Order Register
Work Order Register
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
ID record | Work order no. | Voce | Quantita pianificata | Due time | Priorità | Riga | Reparto responsabile | Work order status | Responsabile | Data creazione | Data aggiornamento | Note
WO-0001 | WO-260418-024 | A-Series Pump Body | 1,200 | 2026-05-16 | Alta | Line A | Produzione | In corso | John Smith | 2026-05-01 | 2026-05-18 | Customer order prioritized for scheduling; monitor material arrival.
WO-0002 | WO-260505-011 | B-Series Valve Seat | 800 | 2026-05-25 | Media | Line B | Produzione | Stato | Emily Davis | 2026-05-05 | 2026-05-18 | Move to processing after first-piece approval.
WO-0003 | WO-260508-018 | C-Series Shaft Sleeve | 1,500 | 2026-05-12 | Urgente | Line C | Materials | Bloccato | Marco Rossi | 2026-04-14 | 2026-05-18 | Critical bearing shortage is affecting assembly pace.

## Progress Checks
Progress Checks
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
ID record | Progress check no. | Work order record ID | Data controllo | Progress stage | Progress percent | Progress status | Bottleneck notes | Responsabile | Data creazione | Data aggiornamento | Note
PRG-0001 | PRG-WO0001-01 | WO-0001 | 2026-05-03 | Preparation | 15% | Progetto di costruzione centrale |  | John Smith | 2026-05-03 | 2026-05-03 | Material preparation completed.
PRG-0002 | PRG-WO0001-02 | WO-0001 | Bella Miller | In corso | 55% | In linea |  | John Smith | Bella Miller | Bella Miller | Processing is on track.
PRG-0003 | PRG-WO0001-03 | WO-0001 | 2026-05-17 | Assembly | 72% | Revisione design | Seal rings for pump bodies arrived later than planned. | John Smith | 2026-05-17 | 2026-05-18 | Additional night shift is expected.

## Material Issue
Material Issue
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
ID record | Issue record no. | Work order record ID | Material code | Material name | Requested quantity | Issued quantity | Shortage quantity | Unita | Data emissione | Issue status | Responsabile | Data creazione | Data aggiornamento | Note
MAT-0001 | MAT-WO0001-001 | WO-0001 | M-PMP-001 | Pump body blank | 1,200 | 1,200 |  | kg | 2026-05-02 | Issued | Emily Davis | 2026-05-02 | 2026-05-02 | Issued by batch.
MAT-0002 | MAT-WO0001-002 | WO-0001 | M-SEAL-008 | Seal ring | 1,200 | 900 |  | kg | Bella Miller | Carenza | Emily Davis | Bella Miller | 2026-05-18 | Remaining 300 pcs are in transit.
MAT-0003 | MAT-WO0001-003 | WO-0001 | M-BOLT-020 | Mounting bolts | 4,800 | 4,800 |  | kg | 2026-05-09 | Chiuso | John Smith | 2026-05-09 | 2026-05-11 | Completeness confirmed.

## QC Rework and Variance
QC Rework and Variance
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
ID record | QC issue no. | Work order record ID | Data ispezione | Issue type | Defective quantity | Rework quantity | Closure due date | Rework status | In lavorazione | Responsabile | Data creazione | Data aggiornamento | Note
QAR-0001 | QAR-WO0001-001 | WO-0001 | 2026-05-16 | Quality defect | 18 | 18 | 2026-05-21 | In rework | Reinspect after reworking the sealing surface. | Sarah Wilson | 2026-05-16 | 2026-05-18 | Track closely.
QAR-0002 | QAR-WO0001-002 | WO-0001 | 2026-05-18 | Documentation gap | Average Delay Days | Average Delay Days | 2026-05-20 | Pending | Add missing progress check record. | John Smith | 2026-05-18 | 2026-05-18 | Registration basis supplemented.
QAR-0003 | QAR-WO0002-001 | WO-0002 | 2026-05-18 | Process delay | Average Delay Days | Average Delay Days | 2026-05-24 | Pending | Follow up on first-piece confirmation window. | Emily Davis | 2026-05-18 | 2026-05-18 | Monitor processing start.

## Completion Confirmations
Completion Confirmations
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
ID record | Completion confirmation no. | Work order record ID | Completion date | Actual quantity | Accepted quantity | Confirmation result | Registro storico | Variance summary | Responsabile | Data creazione | Data aggiornamento | Note
CNF-0001 | CNF-WO0001 | WO-0001 | 2026-05-18 | 900 | 870 | Quantity variance | Revisione | Some quantity will be confirmed after reinspection. | Sarah Wilson | 2026-05-18 | 2026-05-18 | Not finally closed.
CNF-0002 | CNF-WO0002 | WO-0002 | 2026-05-25 | Average Delay Days | Average Delay Days | Incluso lo smaltimento del terreno | Stato | Work order is not yet completed. | Emily Davis | 2026-05-18 | 2026-05-18 | Planned.
CNF-0003 | CNF-WO0003 | WO-0003 | 2026-05-18 | 500 | 480 | Quality variance | Restituito | Blocked work order needs additional rework notes. | Marco Rossi | 2026-05-18 | 2026-05-18 | Returned for supplement.

## Lookup Options
Lookup Options
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Option set key | Sheetcover Navigationcellse5 | Guida | Machine option value | Display label | Color meaning | Default | Ordine di ordinamento
option_set_key | worksheet_name | field_name | option_value | option_label | color_semantic | is_default | sort_order
work_order_status | Work Order Register | status | planned | Stato | neutral | Si | 43.0%
work_order_status | Work Order Register | status | in_progress | In corso | info | Non disponibile | 3. Inserisci i dati mensili

## Machine Schema
Machine Schema
An English Excel template for managing work order registration, progress checks, material issue, QC and rework, completion confirmations, and variance issues.
Worksheet name | Table name | Nome negozio | Module key | Module label | Guida | Field label | Field type | Field role | Obbligatorio | Unique | Default value | Validation rule | Option set key | Searchable | Filterable | Sortable | Show in table | Show on mobile | Show in form | Show in detail | Read-only in form | Apri | Related worksheet | Related field | Note
worksheet_name | table_name | store_name | module_key | module_label | field_name | field_label | field_type | field_role | required | unique | default_value | validation_rule | option_set_key | is_searchable | is_filterable | is_sortable | show_in_table | show_in_mobile_table | show_in_form | show_in_detail | readonly_in_form | export_in_csv | related_worksheet | related_field | notes
Work Order Register | Work Order Register | Work Order Register | Work Order Register | Work Order Register | record_id | ID record | text | primary_key | Si | Si | auto_sequence:WO-0001 | Auto-generated; format WO-0001. |  | Non disponibile | Non disponibile | Si | Non disponibile | Non disponibile | Non disponibile | Si | Si | Si |  |  | Shared primary key; key_path=record_id.
Work Order Register | Work Order Register | Work Order Register | Work Order Register | Work Order Register | work_order_no | Work order no. | text | display_name | Si | Si |  | Required and unique; example WO-260418-024. |  | Si | Non disponibile | Si | Si | Si | Si | Si | Non disponibile | Si |  |  | Business number; does not replace record_id.