## הוראות
תבנית קידום אירועים
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for he)
Define event details, registration targets, channels, and owners in the 'Event Settings' sheet. | → | Set promotion actions, budgets, and target registrants in the 'Promotion Actions' sheet. | Column4 | Enter new registrations and results in the 'Attraction Log' as emails are sent or ads go live. | Column6 | Check achievement rates, channel-specific CPAs, and status distributions on the 'Dashboard' sheet.
Legend (Cell Color Guide)
Key Input & Monitoring Points
1.

## לוח בקרה
לוח בקרה
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for he)
Channel | Spent | Target Registrants | Actual Registrants | CPA | Achievement Rate | Share of Registrants
Share by Promotion Status
Status | Count | Share
Planned

## פעולות קידום
פעולות קידום
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for he)
Promotion ID | Promotion Name | Channel | Budget | Spent | Target | Actual | Progress | CPA | Status | Owner | Scheduled Date
PRM-001 | House list promo email (Batch 1) | Email Marketing | ¥0 | ¥0 | 150 |  |  |  | Published | Owner 1 | 2026-06-05
PRM-002 | LinkedIn & X Promo Posts | Social Media | ¥50,000 | ¥22,000 | 100 |  |  |  | In Progress | Owner 2 | 2026-06-10
PRM-003 | Search Ad Campaign | Paid Search | ¥180,000 | ¥48,000 | 120 |  |  |  | Published | Owner 3 | 2026-06-12

## יומן רישום
יומן רישום
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for he)
Log ID | Registration Date | Promotion ID | Promotion Name | Registrants | Notes
Log-001 | 2026-06-05 | PRM-001 |  | 80 | Initial promotion email sent
Log-002 | 2026-06-06 | PRM-001 |  | 100 | Reminder sent to non-openers
Log-003 | 2026-06-07 | PRM-002 |  | 55 | Social media post & internal sharing

## הגدرות אירוע
הגدرות אירוע
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for he)
Item | Value | Notes | Channel | Owner | Status
Event Name | 2026 Summer Marketing DX Webinar | Displayed on dashboard and promotion list | In-house Email | Owner 1 | Planned
Date | 2026-06-30 | YYYY-MM-DD format | Email Marketing | Owner 2 | In Progress
Target | 370 | Overall KPI. If blank, targets from each promotion are summed | Social Media | Owner 3 | Published