## Instruksi
Template Rencana Promosi Acara
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for id)
Define event details, registration targets, channels, and owners in the 'Event Settings' sheet. | → | Set promotion actions, budgets, and target registrants in the 'Promotion Actions' sheet. | Column4 | Enter new registrations and results in the 'Attraction Log' as emails are sent or ads go live. | Column6 | Check achievement rates, channel-specific CPAs, and status distributions on the 'Dashboard' sheet.
Legend (Cell Color Coding Guide)
Key Input & Monitoring Points
1.

## Dasbor
Dasbor
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for id)
Kanal | Spent | Target Registrants | Actual Registrants | CPA | Achievement Rate | Share of Registrants
Share by Promotion Status
Respons atau Catatan | Jumlah | Porsi
Status

## Aksi Promosi
Aksi Promosi
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for id)
Promotion ID | Promotion Name | Kanal | Anggaran (USD) | Spent | Fitur utama | Aktual | Progres | CPA | Respons atau Catatan | Batas pengecekan | Tanggal Direncanakan
PRM-001 | House list promo email (Batch 1) | Email Marketing | ¥0 | ¥0 | 150 |  |  |  | Published | Owner 1 | 2026-05-02
PRM-002 | LinkedIn & X Promo Posts | Social Media | ¥50,000 | ¥22,000 | 100 |  |  |  | Status | Owner 2 | 2026-06-10
PRM-003 | Search Ad Campaign | Paid Search | ¥180,000 | ¥48,000 | 120 |  |  |  | Published | Owner 3 | 2026-06-12

## Log Pendaftaran
Log Pendaftaran
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for id)
ID Log | Registration date | Promotion ID | Promotion Name | Registrants | Catatan
Log-001 | 2026-05-02 | PRM-001 |  | 80 | Initial promotion email sent
Log-002 | 2026-06-06 | PRM-001 |  | 100 | Reminder sent to non-openers
Log-003 | 2026-06-07 | PRM-002 |  | 55 | Social media post & internal sharing

## Pengaturan Acara
Pengaturan Acara
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for id)
Elemen | Nilai | Catatan | Kanal | Batas pengecekan | Respons atau Catatan
Event Name | 2026 Summer Marketing DX Webinar | Displayed on dashboard and promotion list | In-house Email | Owner 1 | Status
Tanggal | 2026-06-30 | YYYY-MM-DD format | Email Marketing | Owner 2 | Status
Fitur utama | 370 | Overall KPI. If blank, targets from each promotion are summed | Social Media | Owner 3 | Published