## សេចក្តីណែនាំ
គំរូផែនការផ្សព្វផ្សាយព្រឹត្តិការណ៍
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for km)
Define event details, registration targets, channels, and owners in the 'Event Settings' sheet. | → | Set promotion actions, budgets, and target registrants in the 'Promotion Actions' sheet. | Column4 | Enter new registrations and results in the 'Attraction Log' as emails are sent or ads go live. | Column6 | Check achievement rates, channel-specific CPAs, and status distributions on the 'Dashboard' sheet.
Legend (Cell Color Guide)
Key Input & Monitoring Points
1.

## ផ្ទាំងគ្រប់គ្រង
ផ្ទាំងគ្រប់គ្រង
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for km)
Channel | Spent | Target Registrants | Actual Registrants | CPA | Achievement Rate | Share of Registrants
Share by Promotion Status
Status | Count | Share
Planned

## សកម្មភាពផ្សព្វផ្សាយ
សកម្មភាពផ្សព្វផ្សាយ
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for km)
Promotion ID | Promotion Name | Channel | Budget | Spent | Target | Actual | Progress | CPA | Status | Owner | Scheduled Date
PRM-001 | House list promo email (Batch 1) | Email Marketing | ¥0 | ¥0 | 150 |  |  |  | Published | Owner 1 | 2026-06-05
PRM-002 | LinkedIn & X Promo Posts | Social Media | ¥50,000 | ¥22,000 | 100 |  |  |  | In Progress | Owner 2 | 2026-06-10
PRM-003 | Search Ad Campaign | Paid Search | ¥180,000 | ¥48,000 | 120 |  |  |  | Published | Owner 3 | 2026-06-12

## កំណត់ហេតុចុះឈ្មោះ
កំណត់ហេតុចុះឈ្មោះ
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for km)
Log ID | Registration Date | Promotion ID | Promotion Name | Registrants | Notes
Log-001 | 2026-06-05 | PRM-001 |  | 80 | Initial promotion email sent
Log-002 | 2026-06-06 | PRM-001 |  | 100 | Reminder sent to non-openers
Log-003 | 2026-06-07 | PRM-002 |  | 55 | Social media post & internal sharing

## ការកំណត់ព្រឹត្តិการណ៍
ការកំណត់ព្រឹត្តិการណ៍
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for km)
Item | Value | Notes | Channel | Owner | Status
Event Name | 2026 Summer Marketing DX Webinar | Displayed on dashboard and promotion list | In-house Email | Owner 1 | Planned
Date | 2026-06-30 | YYYY-MM-DD format | Email Marketing | Owner 2 | In Progress
Target | 370 | Overall KPI. If blank, targets from each promotion are summed | Social Media | Owner 3 | Published