## ಸೂಚನೆಗಳು
ಈವೆಂಟ್ ಪ್ರಚಾರ ಯೋಜನೆ ಟೆಂಪ್ಲೇಟ್
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for kn)
Define event details, registration targets, channels, and owners in the 'Event Settings' sheet. | → | Set promotion actions, budgets, and target registrants in the 'Promotion Actions' sheet. | Column4 | Enter new registrations and results in the 'Attraction Log' as emails are sent or ads go live. | Column6 | Check achievement rates, channel-specific CPAs, and status distributions on the 'Dashboard' sheet.
Legend (Cell Color Guide)
Key Input & Monitoring Points
1.

## ಡ್ಯಾಶ್‌ಬೋರ್ಡ್
ಡ್ಯಾಶ್‌ಬೋರ್ಡ್
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for kn)
Channel | Spent | Target Registrants | Actual Registrants | CPA | Achievement Rate | Share of Registrants
Share by Promotion Status
Status | Count | Share
Planned

## ಪ್ರಚಾರದ ಕ್ರಮಗಳು
ಪ್ರಚಾರದ ಕ್ರಮಗಳು
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for kn)
Promotion ID | Promotion Name | Channel | Budget | Spent | Target | Actual | Progress | CPA | Status | Owner | Scheduled Date
PRM-001 | House list promo email (Batch 1) | Email Marketing | ¥0 | ¥0 | 150 |  |  |  | Published | Owner 1 | 2026-06-05
PRM-002 | LinkedIn & X Promo Posts | Social Media | ¥50,000 | ¥22,000 | 100 |  |  |  | In Progress | Owner 2 | 2026-06-10
PRM-003 | Search Ad Campaign | Paid Search | ¥180,000 | ¥48,000 | 120 |  |  |  | Published | Owner 3 | 2026-06-12

## ನೋಂದಣಿ ಲಾಗ್
ನೋಂದಣಿ ಲಾಗ್
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for kn)
Log ID | Registration Date | Promotion ID | Promotion Name | Registrants | Notes
Log-001 | 2026-06-05 | PRM-001 |  | 80 | Initial promotion email sent
Log-002 | 2026-06-06 | PRM-001 |  | 100 | Reminder sent to non-openers
Log-003 | 2026-06-07 | PRM-002 |  | 55 | Social media post & internal sharing

## ಕಾರ್ಯಕ್ರಮ ಸೆಟ್ಟಿಂಗ್‌ಗಳು
ಕಾರ್ಯಕ್ರಮ ಸೆಟ್ಟಿಂಗ್‌ಗಳು
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for kn)
Item | Value | Notes | Channel | Owner | Status
Event Name | 2026 Summer Marketing DX Webinar | Displayed on dashboard and promotion list | In-house Email | Owner 1 | Planned
Date | 2026-06-30 | YYYY-MM-DD format | Email Marketing | Owner 2 | In Progress
Target | 370 | Overall KPI. If blank, targets from each promotion are summed | Social Media | Owner 3 | Published