## Instrukcija
Event Promotion Plan Template
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for lt)
Define event details, registration targets, channels, and owners in the 'Event Settings' sheet. | → | Set promotion actions, budgets, and target registrants in the 'Promotion Actions' sheet. | Column4 | Enter new registrations and results in the 'Attraction Log' as emails are sent or ads go live. | Column6 | Check achievement rates, channel-specific CPAs, and status distributions on the 'Dashboard' sheet.
Legend (Cell Color Guide)
Key Input & Monitoring Points
1.

## Dashboard
Dashboard
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for lt)
Channel | Spent | Target Registrants | Actual Registrants | CPA | Achievement Rate | Share of Registrants
Share by Promotion Status
Status | Count | Share
Planned

## Reklaminės akcijos
Reklaminės akcijos
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for lt)
Promotion ID | Promotion Name | Channel | Budget | Spent | Target | Actual | Progress | CPA | Status | Owner | Scheduled Date
PRM-001 | House list promo email (Batch 1) | Email Marketing | ¥0 | ¥0 | 150 |  |  |  | Published | Owner 1 | 2026-06-05
PRM-002 | LinkedIn & X Promo Posts | Social Media | ¥50,000 | ¥22,000 | 100 |  |  |  | In Progress | Owner 2 | 2026-06-10
PRM-003 | Search Ad Campaign | Paid Search | ¥180,000 | ¥48,000 | 120 |  |  |  | Published | Owner 3 | 2026-06-12

## Registracijos žurnalas
Registracijos žurnalas
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for lt)
Log ID | Registration Date | Promotion ID | Promotion Name | Registrants | Notes
Log-001 | 2026-06-05 | PRM-001 |  | 80 | Initial promotion email sent
Log-002 | 2026-06-06 | PRM-001 |  | 100 | Reminder sent to non-openers
Log-003 | 2026-06-07 | PRM-002 |  | 55 | Social media post & internal sharing

## Renginio nustatymai
Renginio nustatymai
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for lt)
Item | Value | Notes | Channel | Owner | Status
Event Name | 2026 Summer Marketing DX Webinar | Displayed on dashboard and promotion list | In-house Email | Owner 1 | Planned
Date | 2026-06-30 | YYYY-MM-DD format | Email Marketing | Owner 2 | In Progress
Target | 370 | Overall KPI. If blank, targets from each promotion are summed | Social Media | Owner 3 | Published