## നിർദ്ദേശങ്ങൾ
ഇവന്റ് പ്രമോഷൻ പ്ലാൻ ടെംപ്ലേറ്റ്
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for ml)
Define event details, registration targets, channels, and owners in the 'Event Settings' sheet. | → | Set promotion actions, budgets, and target registrants in the 'Promotion Actions' sheet. | Column4 | Enter new registrations and results in the 'Attraction Log' as emails are sent or ads go live. | Column6 | Check achievement rates, channel-specific CPAs, and status distributions on the 'Dashboard' sheet.
Legend (Cell Color Guide)
Key Input & Monitoring Points
1.

## ഡാഷ്‌ബോർഡ്
ഡാഷ്‌ബോർഡ്
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for ml)
Channel | Spent | Target Registrants | Actual Registrants | CPA | Achievement Rate | Share of Registrants
Share by Promotion Status
Status | Count | Share
Planned

## പ്രമോഷനുകൾ
പ്രമോഷനുകൾ
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for ml)
Promotion ID | Promotion Name | Channel | Budget | Spent | Target | Actual | Progress | CPA | Status | Owner | Scheduled Date
PRM-001 | House list promo email (Batch 1) | Email Marketing | ¥0 | ¥0 | 150 |  |  |  | Published | Owner 1 | 2026-06-05
PRM-002 | LinkedIn & X Promo Posts | Social Media | ¥50,000 | ¥22,000 | 100 |  |  |  | In Progress | Owner 2 | 2026-06-10
PRM-003 | Search Ad Campaign | Paid Search | ¥180,000 | ¥48,000 | 120 |  |  |  | Published | Owner 3 | 2026-06-12

## രജിസ്ട്രേഷൻ ലോഗ്
രജിസ്ട്രേഷൻ ലോഗ്
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for ml)
Log ID | Registration Date | Promotion ID | Promotion Name | Registrants | Notes
Log-001 | 2026-06-05 | PRM-001 |  | 80 | Initial promotion email sent
Log-002 | 2026-06-06 | PRM-001 |  | 100 | Reminder sent to non-openers
Log-003 | 2026-06-07 | PRM-002 |  | 55 | Social media post & internal sharing

## ഇവന്റ് ക്രമീകരണങ്ങൾ
ഇവന്റ് ക്രമീകരണങ്ങൾ
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for ml)
Item | Value | Notes | Channel | Owner | Status
Event Name | 2026 Summer Marketing DX Webinar | Displayed on dashboard and promotion list | In-house Email | Owner 1 | Planned
Date | 2026-06-30 | YYYY-MM-DD format | Email Marketing | Owner 2 | In Progress
Target | 370 | Overall KPI. If blank, targets from each promotion are summed | Social Media | Owner 3 | Published