## அறிவுறுத்தல்கள்
நிகழ்வு விளம்பரத் திட்ட டெம்ப்ளேட்
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for ta)
Define event details, registration targets, channels, and owners in the 'Event Settings' sheet. | → | Set promotion actions, budgets, and target registrants in the 'Promotion Actions' sheet. | Column4 | Enter new registrations and results in the 'Attraction Log' as emails are sent or ads go live. | Column6 | Check achievement rates, channel-specific CPAs, and status distributions on the 'Dashboard' sheet.
Legend (Cell Color Guide)
Key Input & Monitoring Points
1.

## டாஷ்போர்டு
டாஷ்போர்டு
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for ta)
Channel | Spent | Target Registrants | Actual Registrants | CPA | Achievement Rate | Share of Registrants
Share by Promotion Status
Status | Count | Share
Planned

## ஊக்குவிப்பு நடவடிக்கைகள்
ஊக்குவிப்பு நடவடிக்கைகள்
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for ta)
Promotion ID | Promotion Name | Channel | Budget | Spent | Target | Actual | Progress | CPA | Status | Owner | Scheduled Date
PRM-001 | House list promo email (Batch 1) | Email Marketing | ¥0 | ¥0 | 150 |  |  |  | Published | Owner 1 | 2026-06-05
PRM-002 | LinkedIn & X Promo Posts | Social Media | ¥50,000 | ¥22,000 | 100 |  |  |  | In Progress | Owner 2 | 2026-06-10
PRM-003 | Search Ad Campaign | Paid Search | ¥180,000 | ¥48,000 | 120 |  |  |  | Published | Owner 3 | 2026-06-12

## பதிவு லாக்
பதிவு லாக்
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for ta)
Log ID | Registration Date | Promotion ID | Promotion Name | Registrants | Notes
Log-001 | 2026-06-05 | PRM-001 |  | 80 | Initial promotion email sent
Log-002 | 2026-06-06 | PRM-001 |  | 100 | Reminder sent to non-openers
Log-003 | 2026-06-07 | PRM-002 |  | 55 | Social media post & internal sharing

## நிகழ்வு அமைப்புகள்
நிகழ்வு அமைப்புகள்
Excel template for managing event promotion plans, budgets, actual registrants, and CPA dashboard. (Localized for ta)
Item | Value | Notes | Channel | Owner | Status
Event Name | 2026 Summer Marketing DX Webinar | Displayed on dashboard and promotion list | In-house Email | Owner 1 | Planned
Date | 2026-06-30 | YYYY-MM-DD format | Email Marketing | Owner 2 | In Progress
Target | 370 | Overall KPI. If blank, targets from each promotion are summed | Social Media | Owner 3 | Published