## Инструкции
How to Use the Product Backlog Prioritization Log Template
Objectively evaluate specifications, features, bug fixes, and technical debt using the RICE framework to reflect them in sprint planning and roadmaps.
RICE Evaluation Rules |  |  |  | Operational Flow (4 Steps)
Metric | Value to Enter | Evaluation Criteria | Role in Calculation | STEP 1 | Settings
Reach (Reach) | Number of users impacted in a quarter | Enter as an estimate. e.g., 5,000 users | Value |  | Define product goals, sprints, development teams, and item categories.
Impact (Impact) | Impact on user experience | 3 = Massive, 2 = High, 1 = Medium, 0.5 = Low, 0.25 = Minimal | Multiplier |  |  | ▼
Confidence (Confidence) | Confidence level in evaluation data | 1 = 100%, 0.8 = 80%, 0.5 = 50%, 0.2 = 20% | Multiplier | STEP 2 | Backlog Evaluation
Effort (Effort) | Person-months required for implementation | e.g., enter 3 if it takes 3 person-months | Denominator |  | Enter backlog item name, type, and the 4 RICE metrics. The RICE score is calculated automatically.
RICE Score | Auto Calculated | (Reach × Impact × Confidence) / Effort | Higher score means higher priority |  |  | ▼
|  |  |  | STEP 3 | Development Status
Add progress changes, such as sprint assignment, development start, and releases, in chronological order.
▼
|  |  |  | STEP 4 | Dashboard
Verify decision-making inputs sorted by RICE score and composition ratios by development status.
Legend (Cell Color Guide)
Input Cell Fields to enter directly, such as Name, Reach, Effort, and Notes. |  |  | Formula / Auto-calculated Cell Fields containing formulas, such as RICE scores or VLOOKUPs. |  | Dropdown Cell Select from options: Type, Impact, Confidence, Status, Assignee, Release, etc. |  | Section / Table Header Main headings. Styled with white text on dark navy.
Key Operational Points
- RICE не е абсолютен отговор, а ос за сравнение за повишаване на прозрачността при вземането на решения. Използвайте отделни критерии за ескалация за ключови клиенти, правни изисквания или прекъсвания на услугата. - Обхватът (Reach) се преоценява лесно. Документирането на базата (данни от измервания, билети за поддръжка, търговски сделки, брой целеви потребители) в бележките улеснява последващата проверка. - За елементи с висок резултат, но ниско доверие (Confidence), е ефективно да ги разбиете на задачи за валидиране или прототипи, вместо да ги внедрявате веднага.

## Табло
Dashboard
Automatically aggregates backlog volume, RICE score, item counts by type, and status composition.
Total Backlog Items |  | In Dev / Sprint Backlog | Average RICE Score | Max RICE Score
Items by Type
Type | Count
Composition by Status
Status | Count
Key Checkpoints
- Дори ако резултатът RICE е висок, елементи с ниска степен на увереност е по-безопасно да се разделят на задачи за валидиране. - Ако има твърде много елементи в процес на разработка, задайте лимит за работа в ход (WIP) и дайте приоритет на завършването на текущите задачи. - Дисбалансът в броя по видове може да се използва за проверка на баланса между краткосрочните инициативи и подобренията на техническия дълг.

## Оценка на беклог
Backlog Evaluation
Evaluate requirements, features, bug fixes, and technical debt using the 4 RICE metrics to quantify priority.
Data Entry Policy
1) Enter Item ID, Name, and Type. 2) Enter Reach, Impact, Confidence, and Effort. 3) The RICE score is calculated automatically. 4) Update Status, Assignee, and Target Release, then check the Dashboard for the overall view.
Item ID | Item Name | Type | Reach (Reach) | Impact (Impact) | Confidence (Confidence) | Effort (Effort) | RICE Score | Status | Assignee | Target Release | Notes
ITM-001 | Single Sign-On (SSO) Integration | New Feature | 5,000 | 3 | 80% | 4 |  | Backlog | Member 1 | v1.2 | Requested by major customer. Assuming integration with auth infrastructure.
ITM-002 | Fix Crash on Image Upload | Bug Fix | 1,200 | 2 | 100% | 0.5 |  | In Development | Member 2 | Sprint 15 | Occurs in some iOS environments. High priority fix.
ITM-003 | Improve First-time Welcome Tutorial | Usability Improvement | 3,000 | 1 | 80% | 1 |  | To Evaluate | Product Owner | v1.1 | Aims to improve onboarding completion rate.

## Статус на разработка
Development Status
Track sprint assignments, status updates, and release history chronologically for prioritized items.
Status Log Notes
Add a new row whenever status changes. Selecting an Item ID automatically retrieves the Item Name from the Backlog Evaluation sheet.
Log ID | Item ID | Item Name | Date | Sprint Name | New Status | Notes
Log-001 | ITM-001 |  | 2026-01-08 | v1.2 | Backlog | Registered as a candidate for the next release based on RICE evaluation.
Log-002 | ITM-002 |  | 2026-01-10 | Sprint 15 | In Development | Confirmed reproduction steps. Work started on the fix branch.
Log-003 | ITM-003 |  | 2026-01-12 | v1.1 | To Evaluate | Insufficient quantitative data. Added an analysis task.

## Настройки
Settings
Manage categories, members, releases, status, impact, and confidence metrics used in RICE evaluation. Referenced as dropdown source data.
RICE Formula and Master Data Policy
RICE Score = (Reach × Impact × Confidence) / Effort Using selection dropdowns for Impact and Confidence helps reduce evaluation bias. Edit master items or release names below to fit your workflow.
Item Type | Team Members | Target Release / Sprint | Status | Impact (Impact) | Impact Description | Confidence (Confidence) | Confidence Description
New Feature | Member 1 | v1.1 | New | 3 | Massive: Strongly affects key KPIs or user retention | 100% | 100%: Measurement data or customer demand is clear
Bug Fix | Member 2 | v1.2 | To Evaluate | 2 | High: Clear improvement is expected | 80% | 80%: Relatively strong evidence supports it
Performance Improvement | Member 3 | v2.0 | Backlog | 1 | Medium: Minor or limited improvement | 50% | 50%: Hypothesis-based
Technical Debt | Product Owner | Sprint 15 | In Development | 0.5 | Low: Niche or very minor improvement | 20% | 20%: High uncertainty
Usability Improvement |  | Sprint 16 | Released | 0.25 | Minimal: Supportive or negligible improvement
Deferred
Settings Notes
- Диапазоните на падащите менюта са съпоставени с първоначалните главни редове. Разширете диапазоните за проверка, ако добавяте още елементи. - Въздействието (Impact) и доверието (Confidence) се използват като числови множители в изчисленията. Използвайте описания, за да съгласувате стандартите за оценка. - Защитата на листа или работната книга не е активирана. Чувствайте се свободни да редактирате, за да съответства на вашите операции.