## Basic settings
Project Schedule Management Template
Project name | XX Apartment Building Project | Total tasks | 20
Site name | 1-2-3 XX, Tokyo | Not started | 14
Site manager | Zhang Wei | In progress | 2
Start date | 2026-04-01 | Done | 4
Planned end date | 2026-06-30 | Average progress | 26%
Progress rate check date | 2026-04-18
Base month for monthly plan (1st day) | 2026-04-01 | How to use 1. Enter the base dates and project name 2. Update the blue cells in the task master 3. Changes are reflected automatically in the monthly and weekly plans
Weekly plan start date (Monday) | 2026-04-13
Legend
Input cell | Cells for direct user input
Control cell | Settings such as base date and base month
Link/auto sync | Displayed by reference from the task master
Attention/delay | Items requiring delay tracking or review
This file is a template that combines a task master, monthly plan, weekly plan, and meeting/delivery milestone into one workbook. You can overwrite the sample rows for your own use. Add rows as needed and copy the formulas downward.

## Task master
Task master
Project name | XX Apartment Building Project | [7 empty] | Total tasks | 20
[9 empty] | Not started | 14
[9 empty] | In progress | 2
No | Task category | Task name | Partner | Crew | Planned start | Planned end | Planned days | Actual start | Actual end | Actual days | Progress rate | Status | Delay days | Priority | Work location | Notes
1 | Temporary works | Initial setup | Aoki Project | 4 | 2026-04-01 | 2026-04-03 | 3 | 2026-04-01 | 2026-04-03 | 3 | 100% | Done | 0 | High | Site perimeter | Pre-start preparation
2 | Earthworks | Setting out/excavation | Aoki Project | 6 | 2026-04-04 | 2026-04-08 | 5 | 2026-04-04 | 2026-04-08 | 5 | 100% | Done | 0 | High | Foundation area | Includes soil disposal
3 | Foundation works | Crushed stone base/lean concrete | Partner E | 5 | 2026-04-09 | 2026-04-10 | 2 | 2026-04-09 | 2026-04-10 | 2 | 100% | Done | 0 | High | Overall foundation
4 | Foundation works | Rebar tying | Tanaka Rebar | 6 | 2026-04-11 | 2026-04-14 | 4 | 2026-04-11 | 2026-04-14 | 4 | 100% | Done | 0 | High | Overall foundation | Includes rebar inspection
5 | Foundation works | Formwork | Partner D | 5 | 2026-04-13 | 2026-04-16 | 4 | 2026-04-13 |  | 6 | 70% | In progress | 2 | High | Overall foundation | Partial rework
6 | Foundation works | Foundation concrete pour | Central Ready-Mix | 8 | 2026-04-17 | 2026-04-18 | 2 | 2026-04-17 |  | 2 | 50% | In progress | 0 | High | Overall foundation | Weather confirmation needed
7 | Foundation works | Strip forms/curing | Partner D | 4 | 2026-04-19 | 2026-04-22 | 4 |  |  |  | 0% | Not started | 0 | Medium | Overall foundation
8 | Main structure | 1F structural work | Yamaguchi Project | 10 | 2026-04-23 | 2026-04-30 | 8 |  |  |  | 0% | Not started | 0 | High | 1F
9 | Waterproofing | Quality check | Partner C | 4 | 2026-05-01 | 2026-05-04 | 4 |  |  |  | 0% | Not started | 0 | Medium | Roof
10 | Doors and windows | Window frame installation | Suzuki Windows | 4 | 2026-05-06 | 2026-05-10 | 5 |  |  |  | 0% | Not started | 0 | Medium | Exterior
11 | Electrical systems | Electrical wiring (rough-in) | Toko Electrical | 5 | 2026-05-08 | 2026-05-16 | 9 |  |  |  | 0% | Not started | 0 | Medium | Each floor
12 | Plumbing and drainage | Plumbing and drainage (embedded piping) | Daiichi Equipment | 5 | 2026-05-08 | 2026-05-15 | 8 |  |  |  | 0% | Not started | 0 | Medium | Each floor
13 | Interior works | Light-gauge framing base | Interior Services | 6 | 2026-05-17 | 2026-05-21 | 5 |  |  |  | 0% | Not started | 0 | Medium | Each floor
14 | Interior works | Gypsum board installation | Interior Services | 7 | 2026-05-22 | 2026-05-27 | 6 |  |  |  | 0% | Not started | 0 | Medium | Each floor
15 | Interior works | Painting | Central Painting | 4 | 2026-05-28 | 2026-05-31 | 4 |  |  |  | 0% | Not started | 0 | Medium | Each floor
16 | Fixture installation/commissioning | Fixture installation/trial run | Daiichi Equipment | 4 | 2026-06-01 | 2026-06-08 | 8 |  |  |  | 0% | Not started | 0 | High | Each floor
17 | Exterior works | Exterior works/paving | Partner E | 5 | 2026-06-09 | 2026-06-16 | 8 |  |  |  | 0% | Not started | 0 | Medium | Outdoor
18 | Inspection | Completion inspection | Supervisor/owner | 3 | 2026-06-20 | 2026-06-22 | 3 |  |  |  | 0% | Not started | 0 | High | Overall
19 | Correction | Rework | All subcontractors | 6 | 2026-06-23 | 2026-06-27 | 5 |  |  |  | 0% | Not started | 0 | High | Overall
20 | Handover | Handover | Prime contractor/owner | 2 | 2026-06-30 | 2026-06-30 | 1 |  |  |  | 0% | Not started | 0 | High | Office
Update the blue and purple cells. Status, days, and delay are calculated automatically. Copy the formulas below row 35 if you need to add more rows.

## Monthly plan
2026/04 Monthly plan
Project name | XX Apartment Building Project |  |  |  |  | Progress rate check date | 2026-04-18 |  |  |  | ■ | Planned | A | Actual
No | Task name | Partner | Status | Crew | Planned start | Planned end | Actual start | Actual end | Progress rate | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30
[10 empty] | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
1 | Initial setup | Aoki Project | Done | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | 100% | bar: 2026-04-01 to 2026-04-03
2 | Setting out/excavation | Aoki Project | Done | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 | 100% | bar: 2026-04-04 to 2026-04-08
3 | Crushed stone base/lean concrete | Partner E | Done | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 100% | bar: 2026-04-09 to 2026-04-10
4 | Rebar tying | Tanaka Rebar | Done | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 | 100% | bar: 2026-04-11 to 2026-04-14
5 | Formwork | Partner D | In progress | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  | 70% | bar: 2026-04-13 to 2026-04-18
6 | Foundation concrete pour | Chuo Ready-Mix Concrete | In progress | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  | 50% | bar: 2026-04-17 to 2026-04-18
7 | Demolding/Curing | Partner D | Not started | 4 | 2026-04-19 | 2026-04-22 |  |  | 0% | bar: 2026-04-19 to 2026-04-22
8 | 1F Structural Frame | Yamaguchi Project | Not started | 10 | 2026-04-23 | 2026-04-30 |  |  | 0% | bar: 2026-04-23 to 2026-04-30
9 | Roof Waterproofing | Partner C | Not started | 4 | 2026-05-01 | 2026-05-04 |  |  | 0%
10 | Sash Installation | Suzuki Sash | Not started | 4 | 2026-05-06 | 2026-05-10 |  |  | 0%
11 | Electrical Wiring (Rough Wiring) | Toko Electrical | Not started | 5 | 2026-05-08 | 2026-05-16 |  |  | 0%
12 | Plumbing/Drainage Pre-piping | Daiichi Equipment | Not started | 5 | 2026-05-08 | 2026-05-15 |  |  | 0%
13 | Light Gauge Framing | Interior Service | Not started | 6 | 2026-05-17 | 2026-05-21 |  |  | 0%
14 | PB Board Installation | Interior Service | Not started | 7 | 2026-05-22 | 2026-05-27 |  |  | 0%
15 | Painting | Chuo Painting | Not started | 4 | 2026-05-28 | 2026-05-31 |  |  | 0%
16 | Fixture Installation/Test Run | Daiichi Equipment | Not started | 4 | 2026-06-01 | 2026-06-08 |  |  | 0%
17 | Exterior Works/Paving | Partner E | Not started | 5 | 2026-06-09 | 2026-06-16 |  |  | 0%
18 | Completion inspection | Supervisor/Owner | Not started | 3 | 2026-06-20 | 2026-06-22 |  |  | 0%
19 | Touch-up | Partner Companies | Not started | 6 | 2026-06-23 | 2026-06-27 |  |  | 0%
20 | Handover | General Contractor/Owner | Not started | 2 | 2026-06-30 | 2026-06-30 |  |  | 0%
Task master details are displayed automatically. Blue "■" indicates Planned, and green "A" indicates Actual. For tasks in progress, Actual progress is shown up to the progress check date.

## Weekly plan
2026/04/13 Weekly plan
Project name | XX Apartment Building Project |  |  |  |  | Week start date | 2026-04-13 |  |  | Planned | Actual | Daily planned crew is calculated automatically
No | Task name | Partner | Crew | Planned start | Planned end | Actual start | Actual end | Priority | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | Notes
[9 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Daily planned crew | [8 empty] | 11 | 11 | 5 | 5 | 8 | 8 | 4
1 | Initial setup | Aoki Project | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | High | [7 empty] | Pre-start preparation
2 | Setting out/excavation | Aoki Project | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 | High | [7 empty] | Includes soil disposal
3 | Crushed stone base/lean concrete | Partner E | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | High
4 | Rebar tying | Tanaka Rebar | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 | High | Actual | Actual | [5 empty] | Includes rebar inspection
5 | Formwork | Partner D | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  | High | Actual | Actual | Actual | Actual | Actual | Actual |  | Partial rework
6 | Foundation concrete pour | Chuo Ready-Mix Concrete | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  | High |  |  |  |  | Actual | Actual |  | Weather Check Required
7 | Demolding/Curing | Partner D | 4 | 2026-04-19 | 2026-04-22 |  |  | Medium | [6 empty] | Planned
8 | 1F Structural Frame | Yamaguchi Project | 10 | 2026-04-23 | 2026-04-30 |  |  | High
9 | Roof Waterproofing | Partner C | 4 | 2026-05-01 | 2026-05-04 |  |  | Medium
10 | Sash Installation | Suzuki Sash | 4 | 2026-05-06 | 2026-05-10 |  |  | Medium
11 | Electrical Wiring (Rough Wiring) | Toko Electrical | 5 | 2026-05-08 | 2026-05-16 |  |  | Medium
12 | Plumbing/Drainage Pre-piping | Daiichi Equipment | 5 | 2026-05-08 | 2026-05-15 |  |  | Medium
13 | Light Gauge Framing | Interior Service | 6 | 2026-05-17 | 2026-05-21 |  |  | Medium
14 | PB Board Installation | Interior Service | 7 | 2026-05-22 | 2026-05-27 |  |  | Medium
15 | Painting | Chuo Painting | 4 | 2026-05-28 | 2026-05-31 |  |  | Medium
16 | Fixture Installation/Test Run | Daiichi Equipment | 4 | 2026-06-01 | 2026-06-08 |  |  | High
17 | Exterior Works/Paving | Partner E | 5 | 2026-06-09 | 2026-06-16 |  |  | Medium
18 | Completion inspection | Supervisor/Owner | 3 | 2026-06-20 | 2026-06-22 |  |  | High
19 | Touch-up | Partner Companies | 6 | 2026-06-23 | 2026-06-27 |  |  | High
20 | Handover | General Contractor/Owner | 2 | 2026-06-30 | 2026-06-30 |  |  | High
Weekly Planned is linked automatically from Task master. Daily planned crew totals the workers assigned to tasks planned for that day.

## Meeting delivery milestone
Meeting delivery milestone
Project name | XX Apartment Building Project |  |  |  |  | Record meeting, inspection, and delivery plans
No | Date | Time | Category | Details | Partner companies | Location | Status | Notes
1 | 2026-04-13 | 8:00 | Safety | Weekly safety meeting | Prime contractor/all subcontractors | Site office | Done | Every Monday
2 | 2026-04-14 | 10:00 | Inspection | Foundation rebar inspection | Supervisor/Tanaka Rebar | Site | Done
3 | 2026-04-17 | 13:00 | Delivery | Ready-mix delivery | Central Ready-Mix | Site | Done | Final pre-pour check
4 | 2026-04-18 | 15:00 | Meeting | Post-pour confirmation for foundation concrete | Prime contractor/Central Ready-Mix | Site | Planned
5 | 2026-05-06 | 9:30 | Delivery | Window frame delivery | Suzuki Windows | External yard | Planned
6 | 2026-06-20 | 10:00 | Inspection | Completion inspection | Owner/supervisor | Site | Planned | Confirmation of corrective items
This sheet is a helper table for managing non-task plans such as meetings, inspections, and deliveries.