## निर्देश
Backlog prioritization log template योजना
Excel template for managing and prioritizing the backlog objectively.
Metric | Value to Enter | Evaluation Criteria | Role in Calculation | STEP 1 | Settings
Reach (Reach) | Number of users impacted in a quarter | Enter as an estimate. e.g., 5,000 users | Value |  | Define product goals, sprints, development teams, and item categories.
Impact (Impact) | Impact on user experience | 3 = Massive, 2 = High, 1 = Medium, 0.5 = Low, 0.25 = Minimal | Multiplier
Confidence (Confidence) | Confidence level in evaluation data | 1 = 100%, 0.8 = 80%, 0.5 = 50%, 0.2 = 20% | Multiplier | STEP 2 | Backlog Evaluation

## डैशबोर्ड
डैशबोर्ड
Excel template for managing and prioritizing the backlog objectively.
Total Backlog Items | In Dev / Sprint Backlog | Average RICE Score | Max RICE Score
Items by Type
Type
Composition by Status

## बैकलॉग मूल्यांकन
बैकलॉग मूल्यांकन
Excel template for managing and prioritizing the backlog objectively.
Item ID | Item Name | Type | Reach (Reach) | Impact (Impact) | Confidence (Confidence) | Effort (Effort) | RICE Score | Status | Assignee | Target Release | Notes
ITM-001 | Single Sign-On (SSO) Integration | New Feature | 5,000 | 3.00 | 80% | 4.0 |  | Backlog | Member 1 | v1.2 | Requested by major customer. Assuming integration with auth infrastructure.
ITM-002 | Fix Crash on Image Upload | Bug Fix | 1,200 | 2.00 | 100% | 0.5 |  | In Development | Member 2 | Sprint 15 | Occurs in some iOS environments. High priority fix.
ITM-003 | Improve First-time Welcome Tutorial | Usability Improvement | 3,000 | 1.00 | 80% | 1.0 |  | To Evaluate | Product Owner | v1.1 | Aims to improve onboarding completion rate.

## विकास की स्थिति
विकास की स्थिति
Excel template for managing and prioritizing the backlog objectively.
Log ID | Item ID | Item Name | Date | Sprint Name | New Status | Notes
Log-001 | ITM-001 |  | 2026-01-08 | v1.2 | Backlog | Registered as a candidate for the next release based on RICE evaluation.
Log-002 | ITM-002 |  | 2026-01-10 | Sprint 15 | In Development | Confirmed reproduction steps. Work started on the fix branch.
Log-003 | ITM-003 |  | 2026-01-12 | v1.1 | To Evaluate | Insufficient quantitative data. Added an analysis task.

## सेटिंग्स
सेटिंग्स
Excel template for managing and prioritizing the backlog objectively.
Item Type | Team Members | Target Release / Sprint | Status | Impact (Impact) | Impact Description | Confidence (Confidence) | Confidence Description
New Feature | Member 1 | v1.1 | New | 3.00 | Massive: Strongly affects key KPIs or user retention | 100% | 100%: Measurement data or customer demand is clear
Bug Fix | Member 2 | v1.2 | To Evaluate | 2.00 | High: Clear improvement is expected | 80% | 80%: Relatively strong evidence supports it
Performance Improvement | Member 3 | v2.0 | Backlog | 1.00 | Medium: Minor or limited improvement | 50% | 50%: Hypothesis-based