## Instructions
Product Management Feature Request Log Template
Excel template for managing product feature requests.
1 | Request Settings | 2 | Receive Requests
instructions_001 | Define request categories, channels, and product owners in the 'Request Settings' sheet. |  | Enter the title of the request, source, channel, and initial priority in the 'Request List' sheet.
3 | Record Status Changes | 4 | Check Status
instructions_003 | Add status changes such as investigation, backlog registration, and development start to the 'Status History' sheet. |  | Visually check the volume of pending requests and identify which categories have the most requests on the 'Dashboard' sheet.

## Dashboard
Dashboard
Excel template for managing product feature requests.
No. | Category | Sayi | paylaş of total | Status Observation Memo | Next Action
1
2
3

## Feature Requests
Feature Requests
Excel template for managing product feature requests.
Request ID | Request Title | Request Source | Category | Kaynak groups | stock issue | Status | Scheduled Release | check results | Alınma tarihi | Request Details | Backlog ID
REQ-001 | Encoding selection for CSV output | Support Desk | UI/UX Improvement | Customer feedback | Orta | Added to Backlog | v1.3 | Owner 1 | 2026-04-01 | Enable selection between UTF-8 and Shift_JIS during CSV export | DEV-984
REQ-002 | Auto-sync with external CRM | Sales Department | External API Integration | Sales Feedback | Yuksek | İnceleniyor | Bilinmiyor | Product Manager | 2026-04-05 | Automatically sync customer information and usage status to the CRM used for deal management
REQ-003 | Dashboard loading speed improvement | Key Customer A | Performance Improvement | Support Ticket | Yuksek | New | v1.4 | Owner 2 | 2026-04-09 | Improve initial dashboard load time in environments with a large number of users

## Status History
Status History
Excel template for managing product feature requests.
Log ID | Request ID | Tarih | New Status | Obsunucu | Comments & Next Actions
Log-001 | REQ-001 | 2026-04-01 | New | Owner 1 | Received via support desk. Confirmed customer need for selecting character encoding on CSV output.
Log-002 | REQ-001 | 2026-04-03 | Added to Backlog | Product Manager | Registered as DEV-984 because of the limited scope of impact and high potential for improving customer satisfaction.
Log-003 | REQ-002 | 2026-04-06 | İnceleniyor | Owner 3 | Detailed inquiry sent to sales for requirements definition. Confirm target CRM, auth method, and sync frequency.

## Request Settings
Request Settings
Excel template for managing product feature requests.
Request Category | Request Channel | Product Owner / Assignee
New Feature Request | Customer feedback | Owner 1
UI/UX Improvement | Support Ticket | Owner 2
External API Integration | Sales Feedback | Owner 3