## භාවිතය
Product Management Feedback Log Template
Excel template for product management feedback log.
1 | Configure Master Settings
instructions_001 | Set up the feedback categories, customer segments, and sentiment levels in the 'Feedback Settings' sheet.
2 | Register Feedback
instructions_003 | Enter the comment, sentiment (negative, positive, etc.), and priority in the 'Feedback List' sheet.

## ඩෑෂ්බෝඩ්
ඩෑෂ්බෝඩ්
Excel template for product management feedback log.
Feedback Count | Resolved Count | Negative Count | Urgent Issues (High)
Sentiment Ratio Summary
Sentiment | අනුපාතය
Positive

## Feedback List
Feedback List
Excel template for product management feedback log.
Feedback ID | Feedback Content | Feedback Type | Customer Segment | Sentiment | Priority ප්‍රමුඛතාව | Status | Assignee | Date Logged | User / Company | Action Taken
FDB-001 | The screen occasionally goes blank and freezes. | Bug | Paid Plan (Standard) | Negative | ඉහළ | අයිතමය | Assignee 1 | 2026-04-01 | John Doe (Company A) | Investigating reproduction steps. Development ticket created.
FDB-002 | Would like to bulk upload booking details via CSV. | Feature Request | Paid Plan (Enterprise) | Neutral | මධ්‍යම | සමාලෝචනය තුළ | Assignee 2 | 2026-04-03 | Jane Smith (Company B) | Logged request and registered as a roadmap candidate.
FDB-003 | Support response was fast, making onboarding smooth. | Praise | Trial | Positive | අඩු | Completed | Support Leader | 2026-04-05 | Bob Johnson | Shared with team. Will also use for FAQ improvement.

## Response History
Response History
Excel template for product management feedback log.
Action ID | Feedback ID | දිනය | Logged By | Action details | Notes
Act-001 | FDB-001 | 2026-04-01 | Assignee 1 | Verified the browser, OS, and steps. Requested a reproduction video from the user. | Priority updated to High.
Act-002 | FDB-001 | 2026-04-02 | Assignee 2 | Created development ticket BUG-204 and sent a workaround to the user. | Candidate for the next release.
Act-003 | FDB-003 | 2026-04-05 | Support Leader | Sent a thank-you reply and shared the feedback with the team as a success story. | To be used for FAQ improvements.

## සැකසුම්
සැකසුම්
Excel template for product management feedback log.
Feedback Type | Type Score | Customer Segment (Plan, etc.) | Segment Multiplier | Product Team Assignee | Assignee Notes | Sentiment | Sentiment Score | Priority ප්‍රමුඛතාව | Priority Score | Status | Sort Order
Bug | 5 | Paid Plan (Enterprise) | 1.5 | Assignee 1 | PM / Spec Writing | Positive | 1 | ඉහළ | 5 | බලාපොරොත්තුවෙන් | 1
Feature Request | 4 | Paid Plan (Standard) | 1.2 | Assignee 2 | Development Alignment | Neutral | 0 | මධ්‍යම | 3 | සමාලෝචනය තුළ | 2
Inquiry | 2 | Free Plan | 1 | Assignee 3 | Technical Investigation | Negative | -2 | අඩු | 1 | අයිතමය | 3