## Инструкции (instructions)
How to Use the Release Readiness Checklist Template
A template to confirm release readiness cross-functionally and objectively make the final GO / NO-GO decision before official release.
Workflow (4 Steps)
STEP 1 | STEP 2 |  | STEP 3 |  | STEP 4
Дефиниране на критерии и членове | Регистриране на елементи от контролния списък |  | Запис на проверка и одобрение |  | Финализиране на GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. |  | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. |  | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)
Input Cell |  | Auto Formula Cell |  | Selection Cell
Тази клетка е за ръчно въвеждане и актуализации. |  | Изчислява се автоматично чрез формули. Ръчно редактиране не се препоръчва. |  | Тази клетка е за избор от предварително дефиниран списък.
Key Operational Points
• If required items are incomplete or blocked items remain, it is treated as NO-GO or Conditional GO in principle.
• In the Evidence column, please record URLs of test results, monitoring configurations, FAQs, contract reviews, etc.
• The Approval History can be used as the minutes of the release decision meeting. In case of Conditional GO, please write down the clearance conditions in the comments.

## Табло за управление (dashboard)
Release Readiness Dashboard
Automatically aggregates readiness of all checklist items, blocked issues, readiness rate by category, and status distribution.
Общ брой елементи от контролния списък |  | Изпълнени елементи |  | Блокирани проблеми | Процент на готовност за пускане
Процент на изпълнение на необходимите елементи |  | Финално разпореждане |  | Decision Logic: If there is 1 or more blocked issues, it is NO-GO. If there are no blocked issues and all required items are 100% completed, it is GO. Otherwise, it is Conditional GO.
Процент на готовност по категории
Category | Общо задачи | Завършени задачи | Процент на завършване
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support
4. Legal y Relaciones Públicas
5. Product & PM
6. Data & Analytics
Разпределение по статус
Статус | Брой | Съотношение
Изчаква
В проверка
Приключено
Блокирано
Blocked

## Контролен списък (регистър)
Контролен списък за готовност за пускане
Centrally manage release requirements, verification status, owner, due date, and evidence for each department.
Име на пускането | Release v1.0 |  | Input Rules: - Select Category, Status, Importance, Owner, and Approver from the dropdowns. - Enter Due Date and Checked Date in YYYY-MM-DD format. - Register URLs of test results, monitoring dashboards, approval docs, etc. in the Evidence field.
Scheduled Release Date | 2026-06-20
Дата на срещата за решение | 2026-06-16
Общо решение (автоматично)
Блокирани проблеми (автоматично)
ID на точка | Позиция за проверка | Category | Статус | Строгост | Отговорник | Проверяващ | Краен срок | Дата на проверка | Evidence | Бележки
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Приключено | Задължително | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | В проверка | Задължително | SRE Lead | Технически отговорник | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Блокирано | Препоръка | Мениджър поддръжка | Продуктов отговорник | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.
RDY-004 | Final approval of Privacy Policy and Terms of Service | 4. Legal y Relaciones Públicas | Blocked | Задължително | Legal Lead | Продуктов отговорник | 2026-06-12 |  | https://example.com/legal/review | Correction check of contract terms is incomplete.

## История на одобренията (лог)
Approval History & Sign-Off Log
Record GO / NO-GO decisions and comments by department heads in the release decision meeting.
Record Rules: - Select Department / Role from the master in the settings sheet. - Select Decision Result from GO / NO-GO / Conditional GO. - In case of Conditional GO, specify clearance conditions, remaining issues, owner, and due date in the comment field.
ID на одобрение | Department/role | Име на одобряващия | Dispositionresult | Дата на одобрение | Коментари и точки за проверка от одобряващия
Sign-001 | Продуктов отдел | Продуктов отговорник | Условно GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Инженерен отдел | Технически отговорник | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Отдел Инфраструктура и SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Настройки на критериите (настро
Настройки на критериите
Manage masters such as category, owner, approval department, and roles used in the release decision.
Категории на решението | Членове за вземане на решение за пускане | Department/role | Statuses | Importance Master
1. Development & QA | Member 1 | Продуктов отдел | Изчаква | Задължително
2. Infrastructure & Operations | Member 2 | Инженерен отдел | В проверка | Препоръка
3. Sales & Customer Support | Продуктов отговорник | Отдел Инфраструктура и SRE | Приключено | По избор
4. Legal y Relaciones Públicas | Технически отговорник | Отдел за поддръжка на клиенти | Блокирано
5. Product & PM | Мениджър поддръжка | Търговски отдел | Blocked
6. Data & Analytics | Legal Lead | Отдел Правни въпроси и PR
| Sales lead | Ръководство и краен одобрител
SRE Lead