## Instrukce (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
Definovat kritéria a členy | Registrovat položky kontrolního seznamu | Záznam ověření a schválení | Finalizovat GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## Přehled (dashboard)
Přehled (dashboard)
Excel template for product management release readiness checklist template.
Category | Celkový počet úkolů | Completed Tasks | Míra dokončení
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Kontrolní seznam (registr)
Kontrolní seznam (registr)
Excel template for product management release readiness checklist template.
Item ID | Položka inspekce | Category | Stav | Závažnost | Vlastník | Kontrolor | Termín | Datum kontroly | Evidence | Poznámky
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Uzavřeno | Povinné | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Ověřuje se | Povinné | SRE Lead | Technical owner | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Blokováno | Doporučení | Support lead | Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## Historie schvalování (záznam)
Historie schvalování (záznam)
Excel template for product management release readiness checklist template.
ID schválení | Department/role | Jméno schvalovatele | Rozhodnutí | Approval date | Komentáře schvalovatele a body ověření
Sign-001 | Produktové oddělení | Product owner | Podmíněné GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Oddělení vývoje | Technical owner | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Oddělení infrastruktury a SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Nastavení kritérií (nastavení)
Nastavení kritérií (nastavení)
Excel template for product management release readiness checklist template.
Kategorie rozhodnutí | Členové rozhodovacího orgánu pro vydání | Department/role | Statuses | Importance Master
1. Development & QA | Member 1 | Produktové oddělení | Čeká | Povinné
2. Infrastructure & Operations | Member 2 | Oddělení vývoje | Ověřuje se | Doporučení
3. Sales & Customer Support | Product owner | Oddělení infrastruktury a SRE | Uzavřeno | Volitelné