## Juhised (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
Määrake kriteeriumid ja liikmed | Registreerige kontroll-loendi kirjed | Salvestage kinnitus ja heakskiit | Lõpetage MINNA / MITTE MINNA
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## Töölaud (dashboard)
Töölaud (dashboard)
Excel template for product management release readiness checklist template.
Category | Ülesanne | Completed Tasks | Lõpetamise määr
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Kontroll-loend (register)
Kontroll-loend (register)
Excel template for product management release readiness checklist template.
Item ID | Kontroll-loendi punkt | Category | Olek | Raskusaste | Vastutaja | Ülevaataja | Sihtkuupäev | Kontrolli kuupäev | Evidence | Märkused
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Lõpetatud | Kohustuslik | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Kontrollimisel | Kohustuslik | SRE Lead | Kliendiliidese väljad pole kinnitatud | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Blokeeritud | Soovitus | Toe juht | Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## Kinnituste ajalugu (logi)
Kinnituste ajalugu (logi)
Excel template for product management release readiness checklist template.
Kinnituse ID | Department/role | Kinnitaja nimi | Käsitlusotsus | Kinnitamise kuupäev | Kinnitaja kommentaarid ja kontrollpunktid
Sign-001 | Toote osakond | Product owner | Tingimuslik MINNA | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Tehnikaosakond | Kliendiliidese väljad pole kinnitatud | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Infrastruktuuri ja SRE osakond | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Kriteeriumide seaded (seaded)
Kriteeriumide seaded (seaded)
Excel template for product management release readiness checklist template.
Otsustus kategooriad | Väljalaske otsustusliikmed | Department/role | Statuses | Importance Master
1. Development & QA | Member 1 | Toote osakond | Ootel | Kohustuslik
2. Infrastructure & Operations | Member 2 | Tehnikaosakond | Kontrollimisel | Soovitus
3. Sales & Customer Support | Product owner | Infrastruktuuri ja SRE osakond | Lõpetatud | Valikuline