## Ohjeet (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
Määritä kriteerit ja jäsenet | Rekisteröi tarkastuslistan kohteet | Tallenna varmennus ja hyväksyntä | Viimeistele GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## Ohjausnäkymä (dashboard)
Ohjausnäkymä (dashboard)
Excel template for product management release readiness checklist template.
Category | Tehtävä | Completed Tasks | Valmistumisaste
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Tarkastuslista (rekisteri)
Tarkastuslista (rekisteri)
Excel template for product management release readiness checklist template.
Item ID | Tarkistuskohde | Category | Tila | Vakavuus | Omistaja | Tarkistaja | Tavoitepäivä | Tarkistuspäivä | Evidence | Huomautukset
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Tila | Pakollinen | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Odottaa | Pakollinen | SRE Lead | Technical owner | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Keskinen rakennushanke | Suositus | Support lead | Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## Hyväksyntähistoria (lokitiedost
Hyväksyntähistoria (lokitiedost
Excel template for product management release readiness checklist template.
Hyväksyntätunnus | Department/role | Hyväksyjän nimi | Päätöstulos | Hyväksyntäpäivä | Hyväksyjän kommentit ja tarkistuspisteet
Sign-001 | Tuoteosasto | Product owner | Ehdollinen GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Tekniikkaosasto | Technical owner | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Infrastruktuuri- ja SRE-osasto | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Kriteeriasetukset (asetukset)
Kriteeriasetukset (asetukset)
Excel template for product management release readiness checklist template.
Päätöskategoriat | Julkaisupäätöksen jäsenet | Department/role | Statuses | Importance Master
1. Development & QA | Member 1 | Tuoteosasto | Vahvistamatta | Pakollinen
2. Infrastructure & Operations | Member 2 | Tekniikkaosasto | Odottaa | Suositus
3. Sales & Customer Support | Product owner | Infrastruktuuri- ja SRE-osasto | Tila | Valinnainen